## Sheet1
Stakeholder analysis matrix |  | BY TACTICALPROJECTMANAGER.COM
STAKEHOLDER | CONTACT PERSON | IMPACT | RELATIONSHIP TO YOUR PROJECT | STRATEGY OF ENGAGEMENT | FEEDBACK | NOTES
name or department | name + contact info | (high, medium, low) | In what way is the stakeholder affected by the project? | How do you plan to get the stakeholder involved? | What is important to the stakeholder? What are his fears? | record any further insights here
Head of Engineering | Paul Smith - 5455 | high | change of IT system for engineers will affect entire engineering unit | - nominate key user from engineering - invite key user to bi-weekly status meeting - add Paul Smith to mgmt. email list | According to Paul, the last software upgrade was a mess. Not enough testing was done, poor communication between IT and engineering. Paul wants to have a more active role for his team. | he seems supportive