## Instructions
Last Update: November, 2017
Instructions for using the Project Stakeholder Communication Templates
If you have any questions, or have found any errors within this Project Stakeholder Template Package, please feel free to contact us through our website: https://research-tools.mun.ca/rpm/ Copyright © 2017 Memorial University of Newfoundland
In planning the project scope it is a good idea to recognize all stakeholders that may be associated with your project. A project stakeholder is any person or organization that has a vested interest in a project’s operation or its outcome. For example, MUN, collaborating universities, associated faculty, funding sponsors, community groups, regulatory bodies, and graduate students could all be project stakeholders. By identifying all relevant stakeholders in advance, the context to which a stakeholder is associated with the project is established and project expectations can be agreed upon with the stakeholder in advance. Based on the nature of the stakeholder and their interest, special requirements may have to be taken into consideration when preparing the research proposal and planning project activities. For example, the involvement of an external entity (academic or industry) in research activities will require special contracts/agreements to be put in place prior to the commencement of project activities in order to protect the intellectual property (IP) rights of both parties.
The 'Stakeholder Register Template' can be used to identify all project stakeholders, along with their project expectations, during the planning of a project. This Register should be re-visited regularly during the execution and monitoring of a project to ensure that all stakeholder are identified.
The 'Stakeholder Communication Plan' template allows the researcher to plan the frequency and method of communication to all project stakeholders. For example, communication with stakeholders could be via telephone, email, formal report, meeting, etc. This plan should be shared with project stakeholders to ensure buy-in and acceptance. This plan should be re-visited regularly during the execution and monitoring of a project to ensure it is up-to-date.
The 'Communication Log' template allows researchers to document communications with stakeholders. This can be useful in documenting feedback, identifying action items, identifying new project risk, or for report writing purposes.
Research Project Management
Memorial University of Newfoundland
Bruneau Centre for Research and Innovation P.O. Box 4200
St. John's, NL. A1C 5S7

## Stakeholder Register Template
Research Project Name:
Principal Investigator:
Project Manager (If Applicable):
Project Start Date:
Project End Date:
Stakeholder Name | Title and Role on Project | Email | Telephone | Comments/Stakeholder Expectations
Research Project Management
Tools and Templates
https://research-tools.mun.ca/rpm/
Stakeholder Register Template

## Stakeholder Communication Plan
Research Project Name:
Principal Investigator:
Project Manager (If Applicable):
Project Start Date:
Project End Date:
Stakeholder Name | Title and Role on Project | Key Issue(s) or Interest(s) | Method of Communication | Frequency | Comments
Research Project Management
Tools and Templates
https://research-tools.mun.ca/rpm/
Stakeholder Communication Template

## Communication Log
Research Project Name:
Principal Investigator:
Project Manager (If Applicable):
Project Start Date:
Project End Date:
Date of Communication | Stakeholder Name | Communication Method | Purpose of Communication | Comments/Identified Risks/Actions Required
Research Project Management
Tools and Templates
https://research-tools.mun.ca/rpm/
Stakeholder Communication Log

## Glossary
Glossary of Terms and Definitions
Project stakeholder | Any person or organization that has a vested interest in a project’s operation or its outcome. For example, MUN, collaborating universities, associated faculty, funding sponsors, community groups, regulatory bodies, and graduate students could all be project stakeholders.

## Labels for boxes (hidden)
High
Med
Low
Being Monitored
Cleared
No status
High risk Level
Other
N/A
Note on A3: Sam: Can we "hide" this sheet from the user or should we just lock it?