|  | COMMERCIAL CONSTRUCTION SCHEDULE |  |  |  |  | SCHEDULE VERSION |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | V2.1 (17/02/2022) |  |  |
|  |  |  |  |  |  | PAGE |  |  |
|  |  |  |  |  |  | #1 |  |  |
|  | PROJECT TITLE |  |  | PROJECT MANAGER |  |  |  |  |
|  | COMMERCIAL CONSTRUCTION XPRESS |  |  | JOHN DOE |  |  |  |  |
|  | LOCATION |  |  | CLIENT |  |  |  |  |
|  | 35 MAIN BUILDING AVENUE, ROSEVELT |  |  | BUILDING INVESTMENT HOLDING LTD |  |  |  |  |
|  | TASK NAME | STATUS | ASSIGNED TO |  | START DATE | END DATE | DURATION in days |  |
|  | 1.0 SITE PREPARATION | Completed | Management |  | 05/01 | 05/30 | 30 |  |
|  | 1.1 Implementation of drainage | Completed | Drainage LLC |  | 05/01 | 05/08 | 8 |  |
|  | 1.2 Removal of vegetation | Completed | Machinery team |  | 05/02 | 05/16 | 15 |  |
|  | 1.3 Inspection of structural lines | Completed | Engineering team |  | 05/18 | 05/30 | 13 |  |
|  | 2.0 FOUNDATION | Completed | Construction team 1 |  | 06/01 | 06/10 | 10 |  |
|  | 3.0 FRAMING | In Process | Construction team 2 |  | 06/11 | 07/20 | 40 |  |
|  | 4.0 ROOFING, SIDING AND HVAC | Pending | Construction team 3 |  | 07/21 | 10/20 | 92 |  |
|  | 4.1 Roofing | Not Started | Construction team 3 |  | 07/21 | 08/04 | 15 |  |
|  | 4.2 Siding | Not Started | Construction team 3 |  | 07/21 | 09/10 | 52 |  |
|  | 4.3 HVAC | Not Started | Construction team 3 |  | 09/10 | 10/20 | 41 |  |
|  | 5.0 INTERIOR | Not Started | Construction team 4 |  | 10/21 | 11/12 | 23 |  |
|  | 5.1 Hardwoods | Not Started | Construction team 4 |  | 10/21 | 10/22 | 2 |  |
|  | 5.2 Tile | Not Started | Construction team 4 |  | 10/22 | 10/25 | 4 |  |
|  | 5.3 Cabinets | Not Started | Construction team 4 |  | 10/22 | 10/28 | 7 |  |
|  | 5.4 Plumbing -hang sinks | Not Started | Construction team 4 |  | 10/26 | 11/01 | 7 |  |
|  | 5.5 Stone Counters | Not Started | Construction team 4 |  | 11/01 | 11/07 | 7 |  |
|  | 5.6 Schedule Buffer | Not Started | Construction team 4 |  | 11/01 | 11/08 | 8 |  |
|  | 5.7 Decks | Not Started | Construction team 4 |  | 11/02 | 11/05 | 4 |  |
|  | 5.8 Laundry/furnace room flooring | Not Started | Construction team 4 |  | 11/05 | 11/12 | 8 |  |
|  | 6.0 EXTERIOR | Not Started | Special team 1 |  | 11/12 | 12/15 | 34 |  |
|  | 7.0 UTILITIES | Not Started | Electrical team |  | 11/12 | 12/18 | 37 |  |
|  | 8.0 LANDSCAPING | Not Started | Landscaping team |  | 01/05 | 01/28 | 24 |  |
|  | 9.0 LOREM IPSUM | Not Started | Person 1 |  | 01/10 | 02/02 | 24 |  |
|  | 9.1 Subtask description | Not Started | Person 1 |  | 01/10 | 01/28 | 19 |  |
|  | 9.2 Subtask description | Not Started | Person 1 |  | 01/29 | 02/02 | 5 |  |
|  | Global Building Corporation LLC ▪201 Norton Street, 23434 Belville ▪ (555) 1241 254541▪gbconlinewebsite.com |  |  |  |  |  |  |  |