## Action Item List
Action Item Number | Action Item | Assigned To | Assigned Date | Estimated Completion Date | Completion Date | Open / Closed | Comment | Attachment 1 | Attachment 2 | Attachment 3 | Attachment 4 | Attachment 5 | Attachment 6 | Attachment 7
MSTA-001 | First Pass Yield Analysis | Glenn | 2006-04-25 | 2006-10-16 | 2006-10-16 | Closed | Analyis will begin after May 15, 2006. During the July meeting the team reviewed the analysis attached at "Attachment 2" . Several action items were assign based on the analysis. The data is influenced by too many variables; No major drivers could be identified.
MSTA-002 | Follow-Up Cycle Time Communication | Heather | 2006-04-25 | 2006-05-12 | 2006-07-12 | Closed | Heather will draft a communication to the task group chairs and the staff engineers stating that the cycle time definition will not change and that the task groups should continue to implement their process while assuring the integrity of the process and not make changes just to achieve green metrics.
MSTA-003 | Failed Audit Cycle Time | Glenn | 2006-04-25 | 2006-07-20 | 2006-07-17 | Closed | Jerry Wahlin suggested that we should consider including failed audits in the data used for calculating cycle time. Currently, cycle time is calculated from audits that have certs issued. Glenn with do an analysis to compare 1. failed audit cycle time alone 2. failed audits included with all cert issued audits The analysis will include audits that had certs issued or failed during January thru April 2006. This will be reported out at the next NMC Metrics Sub-Team Meeting. Presented at the July meeting. Team decided not to included failed audit cycle time in cycle time metrics | Sent to MST on 16June06
MSTA-004 | Action Item List | Glenn | 2006-04-25 | 2006-05-01 | 2006-05-01 | Closed | The team agreed that we should add an action item list to the minutes and it should be reviewed at each meeting. The team would like to see all open action items and those closed during the last quarter.
MSTA-005 | Trendline on BOD FPY data | Glenn | 2006-04-25 | 2006-07-20 | 2006-07-17 | Closed | Glenn will add a trend line to the First Pass Yield Data. For now this will not be a permanent part of this metric. It is only an analysis to see if we do have a positive trend to the data. It will be presented at the next Metrics Sub-Team Meeting. Presented as part of MSTA-001
MSTA-006 | Lapsed Accredition Investigateion | Glenn | 2006-07-17 | 2006-10-16 | 2006-10-16 | Closed | Glenn will look into the causes for the 11% of suppliers that have lapsed accreditations. Results will be presented at the October meeting.
MSTA-007 | Merit Text in Scheduling Emails | Glenn | 2006-07-17 | 2006-10-16 | 2006-07-25 | Closed | Glenn will discuss with eAuditNet Programmers just referencing the appropriate NOP/NIP/NTGOP Apendix in the scheduling emails regarding supplier merit.
MSTA-008 | Send FPY Analysis results to SE's and TG Chairs | Glenn | 2006-07-17 | 2006-07-30 | 2006-07-25 | Closed | Send the FPY analysis (MSTA-001) to the Staff Engineers and Task Group Chairs
MSTA-009 | Forward Top Four SE NCR Responses to NCSI and SE's | Glenn | 2006-07-17 | 2006-07-30 | 2006-07-25 | Closed | Forward the top four SE responses to multiple pass NCR's to the NCSI Administrator and Staff Engineers. These may be included in the NCSI training and used by the staff engineers for auditor training. Heather met with Jenn Gallagher on 25July06. These top four responses will be added to the NCSI training and future Supplier Support Tutorials.
MSTA-010 | FPY Presentation at Planning and Ops Meeting | Glenn | 2006-07-17 | 2006-10-17 | 2006-10-16 | Closed | Glenn will present the First Pass Yield Analysis or a summary of it at the October Planning and Ops Meeting. Planning and Ops agenda was too full. Data was sent SE's and TG chairs.
MSTA-011 | NCR Response Examples | Glenn | 2006-07-17 | 2006-10-17 | 2006-07-25 | Closed | Glenn will investigate NCR response modules that could be used by suppliers when responding to NCR's. Heather met with Jenn Gallagher 25July06. Jenn will revise the RCCA section of the web to be more interactive and have NCR resonses more closely related to Nadcap.
MSTA-012 | Suppliers Not on Merit after 4 Years | Glenn | 2006-10-16 | 2006-12-31 | 2006-12-20 | Closed | Glenn will provide this report by the end of December after some required programming is completed in eAuditNet. List sent to Chet Date and PRI Management with Attachment 3 on 20Dec06. The list was distributed to the BOD, NMC Chair and NESPB Chais on 12Jan07.
MSTA-013 | Send List of Audits Open Over 120 days to Primes | Glenn | 2006-10-16 | 2006-12-31 | 2006-12-08 | Closed | Glenn will send the list of audits that are open over 120 days to the Prime NMC members. List sent on 08Dec06
MSTA-014 | Consistant Use of Failure Policy Comminique | Chet | 2006-10-16 | 2006-11-30 | 2006-12-08 | Closed | Chet will send a communiqué to the task groups Chairs and Staff Engineers to reinforce the consistent use of the Failure Policy. Letter was sent TG Chairs and SE's on 08Dec06
MSTA-015 | Days to have a Follow-Up Audit Conducted | Glenn | 2006-10-16 | 2006-01-31 | 2007-01-22 | Closed | Glenn will do an analysis to determine the average number of days from the time that a supplier is notified that a Follow-Up audit is required until the audit is conducted. This will be reported at the next Metrics Sub-Team meeting or conference call. The team will use this information to propose a time-frame that all Follow-Up audits should be conducted with in.
MSTA-016 | Level 2 & 3 Reporting | Glenn, Chet, John Barrett | 2006-10-16 | 2006-01-31 | 2007-01-22 | Closed | Chet, Glenn, and John Barrett will develop a method to report the Supplier Advisory metric.
MSTA-017 | 120 Day Control Chart | Glenn | 2006-10-16 | 2007-01-31 | 2006-11-13 | Closed | Glenn will develop a control chart to track all certs that are issued over 120 days. This will be included in the 2007 BOD metrics. Included in the Nov 2006 BOD Metrics
MSTA-018 | NDT Baseline Impact Analysis | Glenn | 2006-10-16 | 2007-10-31 | 2007-10-22 | Closed | Glenn will plan to do an analysis of the NDT task group 6 month after impimentation of their Baseline checklist to identify any changes in Cycle Time, Number of NCR’s, and Cycles as a result of the checklist change. Reported at the October 2007 meeting. Baseline haas not influenced health indicators.
MSTA-019 | Objective Evidence Standardization | John Barrett | 2007-01-22 | 2007-02-15 | 2007-04-23 | Closed | John Barrett will request that the Standardization Team look into standardizing the objective evidence requirements for major and minor findings for initial and reaccreditation audits. John reported at the April 23, 2007 meeting that a sub-team of the Standardization team has been formed to work this suggestion.
MSTA-020 | Follow-Up Audit Definition | Glenn | 2007-01-22 | 2007-04-23 | 2007-04-23 | Closed | Glenn will develop a definition for Follow-Up audits. This will include a paretto of the reason for the 102 F/U audits analyzed in MSTA-015 to help with the definition. The proposed definition was presented at the April 23, 2007 meeting. Chet Date will request NMC approval.
MSTA-021 | Closing Audits in 30 Days Informal Pilot | Arshad | 2007-01-22 | 2007-06-30 | 2007-04-23 | Closed | PRI will continue the current informal pilot of closing Follow-Up audits in 30 days. Arshad presented a status update at the April 23, 2007 meeting.
MSTA-022 | Follow-Up Audit Review | Glenn | 2007-01-22 | 2007-10-31 | 2007-10-22 | Closed | Glenn will perform an analysis to determine the effectiveness of MSTA-020 and MSTA-021 after six months. Efforts have dedcreased times to schedule and close VCA audits as well as reduced the number of VCAs requested.
MSTA-023 | Revise Level 2 & 3 Report | Glenn | 2007-01-22 | 29-Feb-07 | 2007-04-23 | Closed | Glenn will reverse the order of Level #2 and Level #3 Advisories in the charts. Cycle time to close advisories will be added(control Chart format). The color of "Open" and "Closed" will be changed. "What is the root cause of increase in advisories" will be added as a goal. This metric will not be added to the BoD Metrics package until the proposal is accepted at the April 2007 BoD Meeting. (see MSTA-016)
MSTA-024 | Task Group Approval Time Proposal | Arshad | 2007-01-22 | 2007-04-23 | 2007-04-23 | Closed | Arshad will present a proposal regarding the amount of time that the task groups have to approve an audit. Arshad presented this at the April 23, 2007 meeting.
MSTA-025 | Supplier Advisory Increase Analysis | Glenn | 2007-01-22 | 2007-12-31 | 2007-10-22 | Closed | Per Deb Harrison. Analyze the root cause of the Level 2 and Level 3 Supplier Advisories to determine what is driving the increase in number (program growth, increased escapes, ….) Initial analyis presented at the July meeting. The task group will review and suggest questions. New Advisories are not increasing, however, advisories are not being closed due to several reasons.
MSTA-026 | Present Follow-Up Audit Definition to NMC Steering Committee | Chet Date | 2007-04-23 | 2007-04-24 | 2007-04-24 | Closed | Chet Date will present the Follow-Up Audit definition from MSTA -018 to the NMC Steering Committee and request NMC approval with Standardization team concurrence if needed. Chet presented at the April Steering Meeting. The definition was accepted as follows and the name was changed to Verification of Corrective Action (VCA) audit. Definition: A supplemental audit to verify that corrective actions have been implemented for a limited number of major findings. It must be linked to a specific main audit. Additional major NCR’s found during a Follow-Up audit are automatic consideration for failure (Failure Mode TBD).
MSTA-027 | Update NOP-002, NOP-011,& NIP 7-03 to Reflect Follow-Up Audit Definition | John Barrett | 2007-04-23 | 2007-10-31 | 2008-02-25 | Closed | Upon NMC approval of the proposed Follow-Up audit definition (MSTA-020), John Barrett will update NOP-002, NOP-011, and NIP 7-03. (MSTA-026 must be completed first). John has committed to have the initial drafts in ballot by the end of August.
MSTA-028 | Develop Flexibility for 2008 Goals | EJ Kegerreis | 2007-10-22 | 2008-02-25 | 2008-02-25 | Closed | Develop a flexibilty plan to for the 2008 NMC Goals. PRI accepted the goals as proposed.
MSTA-029 | Supplier Advisories Issued for Product Impact NCR's | EJ Kegerreis | 2007-10-22 | 2008-02-25 | 2008-02-25 | Closed | Sample NCR's to see if Supplier Advisories were issued for finding that required the supplier to notify their customers. Reported out at the Feb08 Nadcap meeting.
MSTA-030 | Supplier Advisory Compliance to NOP-006 Section 5.7.4 | Glenn | 2007-10-22 | 2008-02-25 | 2008-02-25 | Closed | Analyze Supplier Advisories that were issued after January 2007 to insure that they are compliant to NOP-006 Section 5.7.4. Reported out at the Feb08 Nadcap meeting
MSTA-031 | NOP-006 Section 5.7.5 Clarification | Arne Logan | 2007-10-22 | 2008-11-01 | 2008-10-06 | Closed | Propose clarification to NOP-006 Section 5.7.5 Closure Method (Prime Notification, Audits scheduled with open advisories). Arne will lead a team to determine the User needs of the SA system. A proposal was developed. This project was transferred to the Standardization Sub-team.
MSTA-032 | Supplier Advisories Issued for Potential Product Impact NCR's | Glenn and EJ Kegerreis | 2008-02-25 | 2008-07-31 | 2008-07-21 | Closed | Analyze the NCRs that had the "Supplier to Investigate Impact on Hardware" and/or "Potential Product Impact on Hardware" boxes checked to see if Supplier Advisories were issued. Boeing and Cessna offered to help. Glenn Reported at July 2008 meeting.
MSTA-033 | Analyze Effectiveness of Revised Merit Process | Glenn | 2008-02-25 | 2008-07-31 | 2008-07-21 | Closed | Start Tracking the number of suppliers that do not receive merit due to "other documented reason". Presented at July 2008 meeting
MSTA-034 | NMC Supplier Voting Member Attendance Metric | Jerry Wahlin | 2008-02-25 | 2008-07-21 | 2008-07-21 | Closed | Propose a metric based on the format used for the BoD Metrics to track NMC Supplier Voting member attendance at NMC Sub-Team meetings. Presented at July 2008 Meeting.
MSTA-035 | NMC Supplier Voting Member Participation Survey | EJ Kegerreis | 2008-07-21 | 2008-10-15 | 2008-09-23 | Closed | EJ Kegerreis will survey the the staff engineers to determine why supplier voting member are not attaending NMC admin and sub-team meetings. This action was forwarded to the SSC.
MSTA-036 | Lapsed Certifications | EJ Kegerreis | 2008-10-06 | 2009-02-16 | 2009-02-16 | Closed | EJ Kegerreis will investigate the root causes for audits not being certed on-time and audits open over 90 and 120 days that were certed or failed between January and August 2008. The proposals from this presentation will be considered by the Standardization Team at their July 2009 meeting. This action is closed for this team.
MSTA-037 | Failure Policy Investigation | EJ Kegerreis | 2008-10-06 | 2009-02-16 | 2009-07-13 | Closed | EJ Kegerreis will oversee the actions items given to SE's and task groups to determine if current failure policies are meeting the task groups’ needs and expectations(see 06OCT08 meeting minutes for action Item details). Additional work from the February 2009 meeting: EJ will work with an ad hoc team consisting of Kevin Ward, Richard Vinton, Christian Buck and Mike Coleman to review the 48 overturned failure details. The team will analyze the failures for consistency and recommend potential improvements. The team found the that the process was working and recommended not changing the process.
MSTA-038 | 2009 Metric Goals Proposal | Glenn | 2008-10-06 | 2008-12-31 | 2009-01-07 | Closed | Glenn will arrange a telecon with Mark Rechtsteiner, Chet Date, and PRI Management to develop a 2009 Metrics Proposal
MSTA-039 | Monitor Initial Audit Cycle Time | Glenn | 2009-10-19 | 2010-02-22 | 2010-02-12 | Closed | Glenn will monitor the minimum cycle time for Initial audits. The Initial audit minimum cycle time had been stabilized around 11 days but jumped to 20 days for the month of September 2009.
MSTA-040 | Procedure Change Indicators | Glenn | 2009-10-19 | 2010-02-22 | 2009-11-15 | Closed | Glenn will add an indicator such as an arrow on the charts to show when procedures were changed.
MSTA-041 | Top 5 NCR Commonality | Glenn | 2009-10-19 | 2010-02-22 | 2009-11-23 | Closed | The Board of Directors requested that the top five NCRs for each commodity be analyzed for general commonality across task groups. Glenn will perform this analysis on the largest 3-5 task groups.
MSTA-042 | Over-Turned Staff Engineer Failure Recommendations | EJ Kegerreis | 2009-10-19 | 2010-10-30 | 2010-10-18 | Closed | EJ will report out on the status of the Over-Turned Staff Engineer Failure Recommendations again at the October 2010 meeting.
MSTA-043 | NCRs versus Merit Status Analysis | Glenn | 2009-10-19 | 2010-02-22 | 2010-02-22 | Closed | Jay Park proposed that an analysis be conducted to compare the number of NCRs that suppliers that are on merit receive versus suppliers that are not on merit receive. Glenn will perform this analysis.
MSTA-044 | Merit Status versus Number of Commodity Processes | Glenn and EJ Kegerreis | 2009-10-19 | 2010-02-22 | 2010-02-22 | Closed | Jerry Wahlin proposed that an analysis be conducted to determine if the number of processes that a supplier is audited for affects the supplier’s ability to receive merit. EJ and Glenn will conduct this analysis.
MSTA-045 | Revise Data Analysis Request Form | Glenn and Jay Park | 2010-02-22 | 2010-05-30 | 2010-03-26 | Closed | Make the revision to the Data Analysis Request form and find a place to store the completed forms and data analysis. Also, Jay Park will pilot the revised form with his request for NCRs versus Merit Status Analysis (MSTA-043).
MSTA-046 | Customer Satisfaction Survey of the Metics and Goals | Chet and Mark | 2010-06-21 | 2010-10-30 | 2010-10-18 | Closed | Chet Date and Mark Rechtsteiner will lead a team to survey customer satisfaction with our goals and metrics.
MSTA-047 | Supplier Advisory Distribution | Glenn | 2010-06-21 | 2010-10-30 | 2010-10-18 | Closed | Mark Rechtsteiner requested a Supplier Advisory Distribution by Month or Quarter analysis to be presented at the October meeting. Glenn will perform this analysis after Mark submits a Data Analysis Request Form.
MSTA-048 | NMC and Task Group Dashboards | Pascal Blondet | 2010-10-18 | 2011-10-30 | 2012-06-26 | Closed | Develop a dashboard/dashboards that will display a global overview of the status of Nadcap projects for NMC and Task Group members. . The sub-team includes: Pascal Blondet, Richard Blyth, Chet Date, Martha Hogan-Battisti, Glenn Shultz, and Jon Steffey. Jon presented update at the February 2011 meeting. The group was pleased with the direction and progress of the project. Jon will report on the status of this project during the June 2011 Steering Meeting and request feedback on what should be the initial topics to be included on the dashboards. Jun11 Jon and Glenn will reconvene the Dashboards sub-team to define and prioritize the initial topics that will be included on the dashboards.
MSTA-049 | FPY Analysis | Glenn | 2010-10-18 | 2011-02-28 | 2010-12-17 | Closed | Glenn will analyze the average number of cycles to achieve certificationby month for the current year and the percent that was accredited in one pass (First Pass Yield)
MSTA-050 | Merit Status of Failed Supplier and Suppliers that receive Product Impact NCRs | Glenn | 2011-06-22 | 2011-10-30 | 2011-10-17 | Closed | Glenn will perform an analysis on suppliers that failed or had a potential product impact written against the supplier while on merit. Glenn will work with Joe Pinto on the details of this analysis
MSTA-051 | Metrics Charts Format | Glenn | 2011-06-22 | 2011-07-30 | 2011-10-17 | Closed | Mark Covert requested that the metrics should be reviewed for small font and cluttered axis labels and changed to make the metrics easier to read
MSTA-052 | New Metrics Suggestions | Bob Bodemuller | 2011-10-17 | 2011-02-28 | 2012-02-21 | Closed | Bob Bodemuller will request suggestions for metrics that reflect NMC committees and sub-teams activities.
MSTA-053 | Metrics Committee Charter Revision | John Barrett | 2011-10-17 | 2012-02-28 | 2012-02-21 | Closed | John Barrett to include the proposed Metrics Committee Charter revision in the next revision and ballot of NOP-001.
MSTA-054 | NMC and Task Group Dashboards Feedback | Jon Steffey | 2012-06-26 | 2012-10-31 |  | Open | Jon Steffey should request feedback on the dashboards after a couple months of use and report out at the October meeting
MSTA-055

## Decision List
Action Item Number | Decision | Decision Date | Comment | Attachment 1 | Attachment 2 | Attachment 3 | Attachment 4 | Attachment 5 | Attachment 6 | Attachment 7
MSTD-001 | Follow-Up Audit Cycle Time | 2006-04-25 | The team decided that the cycle time definition will not change to allow the deletion of the Follow-Up Cycle Time from the Main Audit. The Total Cycle Time will continue to be defined as the elapsed time from the audit end date until the cert is issued (See Action Item MTSA-002).
MSTD-002 | Failed Audit Cycle Time | 2006-07-17 | The team decided not to include Failed Audit Cycle time in the Cycle Time metrics. See MSTA-003
MSTD-003 | Merit Email Text | 2006-07-17 | The team decided to only reference the appropriate NOP/NIP/NTGOP Appendix regarding merit in the Scheduling emails rather the actual task group requirements. This will be a "work around" until the Standardization Team can develop a standard merit program. See MSTA-007
MSTD-004 | Proposed 2007 NMC Metrics Goals | 2006-10-16 | It was decided that Merit, Cycle-Time, and On-Time Accreditation metrics will continue to be maintained and reported. First Pass Yield and Backlog metrics will be discontinued. The Failed Audit metric will be replaced with a metric that tracks Level 2 and Level 3 Supplier Advisories issued each month. The proposed goals for 2007 will be: • Merit: > 80% • Cycle Time: Initial Accreditations - 70 days, Reaccreditations – 50 days • On-Time Accreditations: > 90% • Audits Certed Over 120 Days: < 20 • Level 2 and 3 Supplier Advisories: Only Track
MSTD-005 | Critical Operational Health Indicators | 2007-01-22 | The team agreed that the Critical Operational Health Indicators were: Merit, Cycle Time, Audits Over 120 Days, Failed Audits/Level 2&3 Advisories and On-Time Accreditations.
MSTD-006 | VCA Audit Definition Change | 2007-10-22 | The team agreed to change the word "major" to "Identified" in the VCA audit definition.
MSTD-007
MSTD-008
MSTD-009
MSTD-010
MSTD-011
MSTD-012
MSTD-013
MSTD-014
MSTD-015
MSTD-016
MSTD-017
MSTD-018
MSTD-019
MSTD-020
MSTD-021