## Sheet1
2015 Windward Pointe Action Item Tracking Log
Date | Action Item | Assigned To | Due Date | Decision | Status
2015-02-15 | Create a bed bug policy | Eddie | 2015-03-07 | Board approved at march 7 mtg. to send. | Complete
2015-02-15 | Repair tile by elevator. | Shane | 2015-03-14 | Distributor acquiring tile for job. | Complete
2015-02-15 | Upgrade of camera system | Scott | 2015-05-23 | Board will consider at march 7 mtg. Eddie will work with vendor on a new bid. Bid received and accepted with changes.First installment paid to begin project, update on complettion schedule expected by 8/15/15. | In Progress
2015-02-15 | Add keypad & closer to west door at indoor pool area. | Aarons Lock | 2015-02-20 | Also looking at getting a lockout code for all doors. | Complete
2015-02-15 | Replace sign at elevators-worn | Julie | 2015-02-20 | Sign arrived on 2/20 and installed. | Complete
2015-02-15 | Roof work | Julie | 2015-04-07 | Soprema came and made repairs 2/25/2015. Malone came on 3/6/2015 and will schedule repair asap. , C-Sharpe provided pics of repairs needed.Julie will contact another roofing company for a comparison estimate asap. Standard roofing repair completed on 3/16/15. | Complete
2015-02-15 | Monthly Inspection Report | Julie | Monthly | Darryl (SS) does a daily inspection report that Julie will forward to Eddie monthly. | In Progress
2015-02-15 | Parking lot -collapse at 3-way | Julie | 2015-03-07 | Parking lot patch should be completed by 3/15/15. | Complete
2015-02-15 | Pipe leak in indoor pool area | La Pools | 2015-02-19 | Close area, repair leaks and then reopen for guest. | Complete
2015-02-15 | Repair concrete at Hot Tub | La Pools | 2015-03-13 | Patch work needed at entrance to spa from earlier repair work. Checked on 3/6/2015 needs to be redone at North entrance to hot tub. | Complete
2015-02-15 | LED lighting-front wall only | Osborn Electric | 2015-02-22 | Replace lighting at wall by road with LED. | Complete
2015-02-15 | LED lighting-main parking lot | Osborn Electric | 2015-05-23 | Board approved at march 7 mtg. | Complete
2015-02-15 | Ceiling painting of common areas. | Shane | 2015-02-19 | Bleached and painted all common areas. | Complete
2015-02-15 | WiFi for building | Harbor | 2015-03-07 | Accepted Harbor bid and installation has began. Main building completed on 3/5/2015. | Complete
2015-01-10 | Quarterly letters to the owners | Eddie | Quarterly | Will update association members on the qtr. By email. | In Progress
2015-02-15 | Rusted vent indoor pool area. | Shane | 2015-03-10 | Replacing rusted vent & door by pool pumps. | Complete
2015-02-15 | 2nd phase of landscaping. | Kutters/Eddie | 2015-05-23 | Board will discuss at March 7 mtg. Changes being considered. Eddie to get prices, more details to follow. Met onsite 5/6/15 and discussed changes to phase 2. Final walkdown and bids scheduled for 8/6/15. | In Progress
2015-01-15 | Slippery area by trash chutes. | John & Betty Allen | 2015-02-01 | Rubber mats added to all trash chute areas. | Complete
2015-01-30 | Both large light lens dirty at elevators. | Shane | 2015-01-31 | Pull lens covers and clean, re install. | Complete
2015-01-05 | Inside elevator lighting needs repair. | Shane | 2015-01-10 | Replaced lighting as needed. | Complete
2015-01-14 | Repair or replace exit sign, 14th floor. | Osborn Electric | 2015-01-20 | Replaced fixture. | Complete
2015-01-19 | Repair or replace exit sign, 9th floor. | Osborn Electric | 2015-01-25 | Light replacement. | Complete
2015-01-01 | Rusting balcony doors. | Julie | 2015-05-23 | Doors on order for 01 & 06 stacks. Doors arrived 3/6/2015. Installation has began. Phase 1 - 01 and 06 stacks completed. Now planning phase 2 of 3 phases for fall of 2015. | In Progress
!/!/2015 | Spalling issues. | C-Sharpe | 2015-05-01 | Repair all identified areas (weather delayed). C-Sharpe onsite now and working. | Complete
2015-01-10 | Broken switch for sauna timer. | Julie | 2015-01-20 | Knob replaced and working. | Complete
2015-03-07 | Floor covering for main building. | Eddie | 2015-05-23 | Eddie acquiring flooring option prices for building to discuss more in May. Update after May meeting-Planning for fall period will coordinate with other projects after all bids are reviewed by board. Will have bids by fall 2015 board meeting. | In Progress
2015-03-28 | Elevator Issues, reliabilty and long term solution. | Julie | 2015-05-23 | Julie working on bid packages to present to board. One bid in, waiting on second to disburse to board for review. | In Progress
2015-05-03 | Bathroom dividers in IP building. | Shane | 2015-05-23 | Adding kickplates to dividers. | Complete
2015-05-05 | Paint curbs in parking lot. | Kirk Howard | 2015-05-23 | Painting to improve safety around curbed areas. | Complete
2015-05-06 | Paint light fixtures in parking area. | Kirk Howard | 2015-05-23 | Painting fixtures that were upgraded to LED's. | Complete
2015-06-15 | Make parking passes easier to get at night. | Sidwell Security | 2015-06-22 | Guard will begin selling parking passes at night from guardhouse. Will post sign so guest are aware and notify rental agencies of this option. | Complete
2015-06-15 | Make keyed areas easier for owners to access before/after posted hours. | Aarons Locks | 2015-06-22 | A 'owners only code' that can be used before or after posted hours ( 4am-12midnight) will be distributed to all owners for keyed areas. | Complete
2015-06-15 | Address the issue of sand being brought into pool areas. | Printing Pro | 2015-06-22 | Creating signs asking guest to shower before entering pool areas when coming from the beach. | Complete
2015-06-15 | Residents having trouble finding parking spaces. | Printing Pro | 2015-06-22 | Designating 4 parking spots and will mark with signage as resident only parking, two along each fence line. | Complete
2015-07-15 | Pool lighting area (outdoor) not reliable. Constantly changing bulbs and ballast. | Osborn Electric | 2015-07-15 | Replaced flourescent with LED around outdoor pool area. | Complete
2015-08-01 | Safe lockout of indoor pool area. | Aaron's Lock | 2015-08-01 | Acquire a 'lock out' code that will overirde entrance codes to indoor pool area in event building needs to be locked down for safety purposes. | Complete
2015-08-01 | Web design and information exchange. | Rachael Thompson | 2015-08-01 | Create a facebook page and monitor so that pictures and information can be readily exchanged. Also link the drone flyover to facebook page for owners to easily share. | Complete