
[image: image1.jpg]STRATIS HEALTH HEALTH INFORMATION TECHNOLOGY TOOLKIT HOME HEALTH AGENCIES



Section 2.1 Plan  

Communication Plan
Regular communication with all stakeholder groups helps reduce the uncertainty inherent in adopting Health Information Technology (HIT), and engages all stakeholders. Build your Communication Plan using this template.
	Time needed: 4 hours to start – ongoing maintenance of the plan 
Suggested other tools: NA


Introduction– Why Communication Planning is So Important

Regular communication with all stakeholders about new or major events helps reduce the uncertainty about the changes. Engage all stakeholders at the appropriate level of participation in planning, implementing, and identifying opportunities for improvement. 

In small home health care agencies, it may seem like overkill to develop a communication plan. However, too often, key pieces of information get lost in the daily scramble of seeing patients, paying bills, and maintaining the existing IT infrastructure. When you develop a written plan and make sure you check off completed tasks, you reduce the risk of miscommunication. By creating and following a plan, you can be sure that every member of the agency has appropriate awareness, interest, knowledge, and engagement in the project.

The major theme of the communication plan is CHANGE. As soon as the need for change arises, you should begin to build awareness. As the vision for the change unfolds, creating desire for the change or outcome helps turn uncertainty into interest. Throughout the planning process, stakeholders need to become more knowledgeable about the change in order to make decisions. During implementation, stakeholders need to understand change as it is happening and promote celebrating the change. Communication does not end with implementation, since implementation is only the end of the beginning. The road to effective use is a continuous one, and success will require regular and consistent communication.  

For any major project, there should be a Project Plan. The overall project plan will guide your communication plan. Your communication plan should mirror the activities of the project plan and support the goals of that plan through each major phase. Begin by thinking about the 3 W’s:
· What are the steps or phases of your project 

· Who needs to know about what topics, and

· When and how frequently (especially for recurring communication tasks like team updates)
Consider the various types of communication: awareness building, decision-making, project progress and updates, advisories, reminders, encouragement and celebration of milestone achievement. Some communications are two-way, such as meetings, phone calls, and discussions, but many are one-way, including the agency’s website, email, memos, bulletin boards, newsletters, and even social networking sites such as Facebook. One-way communication lacks an immediate feedback mechanism, so plan ways to obtain feedback. Be sure to communicate using plain language, not “techie-speak.” 

Step-by-Step Instructions 

Build your communication plan using the template supplied below. Keep in mind, this is only a template, the stakeholder groups and individuals with whom you need to communicate will be different based on your agency’s needs. The value of the template is in the columns, which help you organize your communication efforts. The types of messages you place in the rows depend on your agency. Perhaps the most important column is the one labeled Done? A communication plan that isn’t implemented is a complete waste of time. 

We have filled in a few samples for each of the project’s phases. The examples may or may not pertain to you. Remember the value of communication is in its relevance to the people whom it affects. Random blah blah is tuned out. Specific information about our lives and the way in which we work is usually heard through the din.
Here are the steps to complete:

· Assemble the team of people who will build and implement the plan. In the case of a small agency this might be one or two. In a larger organization, decide on a sub-team of 3 -5 people.

· Hold a brainstorming session to identify all the constituents and stakeholders you will need to communicate with. Some examples include: 

· Aides, nurses,  physical therapists, and personal care attendants 

· “Super Users” (individuals who have experience and/or aptitude with technology and have learned how to use it), e-health selection team members, IT support staff

· your steering committee, administrative staff

· your project sponsor and board of directors

· clients, the community that you serve and so on 

· This list of constituents will populate the To Whom column of your plan.

· For each of the constituents, brainstorm a list of concerns, issues, and other types of project-specific updated/information they will need or want to know. (Remember to think especially hard about the worries and concerns people will have.) Effective communication addresses emotions as well as facts.

· The hardest step – for each concern/issue/informational topic, create a response. Note that:

· For the plan, you don’t have to write out the entire response. Instead, note the content of the response. You can leave the final details of the message to the person who will deliver it.

· If you have brainstormed many issues and many constituents, you don’t have to complete this step for all issues. Instead, make sure you address the most urgent – either those issues that will come up soonest, or those issues that have the greatest emotional impact. Since you will revisit the communication plan every couple of months, you can add the less urgent or immediate messages to your plan later.

· This list of responses will populate the Key Messages column.

NOTE:  You may already realize that the communication planning process is iterative. At this early stage you won’t know everything all the constituents need or want to know. So, you will need to return to the plan at least every two months. The constituents probably won’t change much – some may drop out and you may realize you’ve identified some new ones – but the messages will change.

· For each Key Message/To Whom combination, assign a From Whom person. In general, the most appropriate person will be the one with the most influence with the specific audience, and who actually has the time to do it!  (If you assign all your communication to the agency director, chances are it won’t all get done). Spread the tasks around, but make sure the person who delivers the most important messages is well respected and highly placed in the organization.

· For each Key Message/To Whom combination, determine a Medium for the message. Email may be appropriate for many routine advisory and project updates, whereas an in-person weekly or monthly meeting is better for decision-making or consensus. Communication to patients may include handouts at home care visits, or even signage at the agency. Don’t forget piggybacking on existing methods of communication, such as internal and external newsletters, the agency’s website, and social networking sites. 

· Determine a date when the communication should go out. Fill this in the Date column.
The first iteration of your communication plan is complete!

Planning Is Wasted Effort without Implementation

As mentioned above, the most important step comes after planning – you need to follow the plan. The project manager should check to see that communication messages go out as planned. When they are completed, put a check mark in the Done column. Review progress on the plan at each team meeting. Review past communication activities:

· Were they completed on time?

· How were they received?

· What could we do better?

Periodically (at least every two months) revise the plan. Add new topics and update any that are ongoing. Make sure you are addressing the real concerns of the people in your agency. 

Communication Plan Template with Sample Activities

Note: depending your agency’s size and structure, “CEO” can mean Chief Executive Officer, Agency Administrator, or Office Manager
	Key Message
	To Whom
	From Whom
	Medium
	Date
	Done?

	All Project Phases

	Weekly project status
	Team members
	Project Manager
	Team Meeting
	Throughout E-HEALTH project
	

	Monthly organizational update
	All staff, management, Board
	Project Manager
	As appropriate (email/meeting/internal web site, etc.)
	Throughout E-HEALTH project
	

	Assess Phase

	The agency is interested in HIT and/or E-HEALTH and we want board support 
	Board of directors
	CEO


	Meeting
	Fill in date based on your project plan
	

	The agency knows we have to adopt an electronic record and other e-health tools to better serve our clients and remain competitive in our market
	All staff
	CEO 


	Various: all staff meeting, newsletters, supervisor communications, other means within your agency
	Fill in date based on your project plan
	

	Who will lead our E-HEALTH project? These are the “go-to” people. Our project manager is <name> and our “provider champion” is <name>
	All staff
	CEO 


	Various: all staff meetings, newsletters, supervisor communications, other means within your agency
	Fill in date based on your project plan
	

	Plan Phase

	e-health means (fill in meaning for agency) 
	E-HEALTH steering committee

All staff and supervisors
	Chair of project steering committee
	Various educational programs
	Fill in date based on your project plan
	

	Here are some concerns we’ve heard about EHRs and how we plan to address them.
	All staff with direct patient contact; especially nursing staff and aides, support/back office staff
	Key supervisor or very respected member of staff with direct patient contact

Project champion


	Lunch and learn roundtable discussions
	Fill in date based on your project plan
	

	Select Phase

	 We are holding a vendor fair/in-house demos and want everyone to participate and complete a score card
	All staff with direct patient contact; especially nursing staff and aids, support/back office staff
	Key supervisor or very respected member of staff with direct patient contact

Project champion


	Memo or newsletter


	Fill in date based on your project plan
	

	 Vendor has been selected and we seek approval to begin contract negotiation
	Board of directors as well as: All staff with direct patient contact; especially nursing staff and aides, support/back office staff
	e-health steering committee
	Meeting

Approval request
	Fill in date based on your project plan
	

	These are the terms of the contract and we request approval to sign
	Board of directors as well as: All staff with direct patient contact; especially nursing staff and aides, support/back office staff
	CEO


	Meeting

Approval request
	Fill in date based on your project plan
	

	Implement and Optimize Phase

	Here is an overview of the implementation plan and how it will impact each stakeholder group 
	All staff
	Project champion

Project manager
	Site and department meetings

Newsletter
	Fill in date based on your project plan
	

	We seek representatives to participate on implementation teams and domain teams 
            
	Clinical and support staff

Department managers

Front line supervisors
	Key supervisor or very respected member of staff with direct patient contact

Project champion

Project manager 
	Personal communications with applicable counterparts

Organization chart for project
	Fill in date based on your project plan
	

	 We are constructing a new system to manage your records and want you to know what this is, how it will help you, how secure it is, how it will affect you during implementation, and answer any questions.


	Patients
	Key supervisor or very respected member of staff with direct patient contact

Project champion

Project manager 
	Brochures

Website

On-hold telephone message for patient care

Article in local newspaper

Under construction signs
	Fill in date based on your project plan
	

	We are the support team to help you during go live 

 
	All staff
	Project manager

Super Users


	Hotline

Badges, hats, coats, or something else to distinguish helpers
	Fill in date based on your project plan
	

	Ongoing Initiative

	Continual process improvement—how is it going?
	Clinical and support staff


	Key supervisor or very respected member of staff with direct patient contact

Project champion

Project manager

CEO 
	Informal feedback 

User satisfaction survey

Check-ins
	Fill in date based on your project plan
	

	Outcomes analysis—here are our quality assurance results
	All staff with direct patient encounters


	CEO


	Meetings

Report cards
	Fill in date based on your project plan
	

	Our next steps for E-HEALTH are: (describe based on your strategic plan)
	All staff
	CEO
	Newsletter
	Fill in date based on your project plan
	


[image: image2.jpg]Funded by Aging Services of Minnesota and its subsidiary, Alliance Purchasing. Produced under contract with the Minnesota Department of Health.

For support using the toolkit
Stratis Health  Health Information Technology Services
952-854-3306 * info@stratishealth.org

www.stratishealth.org

Aging Services Aging Services
ﬂ of Minnesota o GROUP

LEADING CHANCE ® CHANCING LIVES PRODUCT AND SERVICE SOLUTIONS

MDH StratisHealth

[DEPARTMENT oF HEALTH|




Copyright © 2013 Stratis Health. 





Updated 03-10-14
PAGE  
[image: image3.jpg]


Section 2 Plan—Communication Plan - 6 

