Critical Path Method Exercises

Based on the PMBOK® Guide Fifth Edition

Course ID: PMTONDEMAND35

Contact Hours / PDUs: 35

For more information on project management certification training, please visit www.PMTraining.com

Copyright © 2016 PMTraining, SSI Logic. All Rights Reserved.

Duplication of this material is not permitted without express consent of PMTraining, SSI Logic.

Visit www.PMTraining.com for tools and resources on PMP training.

Practice Exercise

Critical Path Method

Exercise 1:

For the following table of information,

1.

2.

3.

4.

Draw the network diagram

List the network paths Determine the critical path(s)

Determine the float for each activity

Copyright © 2016 PMTraining, SSI Logic. All Rights Reserved.

Duplication of this material is not permitted without express consent of PMTraining, SSI Logic.

Visit www.PMTraining.com for tools and resources on PMP training.

Activity

Duration

Dependency

Float

Start

0 days

-

A

5 days

Start

B

2 days

Start

C

3 days

A, B

D

5 days

Start

E

6 days

Start

F

4 days

D, E

G

2 days

C, F

H

5 days

G

I

7 days

G

J

3 days

H

Finish

0 days

I, J

Exercise 2:

1. Perform a Forward Pass and a Backward Pass of the network diagram above

2. Which Activities has the same Early Finish as they have Late Finish?

Note: The project starts on Day “0”

Copyright © 2016 PMTraining, SSI Logic. All Rights Reserved.

Duplication of this material is not permitted without express consent of PMTraining, SSI Logic.

Visit www.PMTraining.com for tools and resources on PMP training.

2

M

8

L

3

N

5

K

7

J

8

I

5

H

5

G

3

F

5

C

3

B

2

A

1

E

1

D

Early Start

Duration

Early Finish

Task Name

Late Start

Slack

Late Finish

Exercise 3:

For the following table of information,

1.

2.

3.

4.

Draw the network diagram

List the network paths Determine the critical path(s)

Determine the float for each activity

Copyright © 2016 PMTraining, SSI Logic. All Rights Reserved.

Duplication of this material is not permitted without express consent of PMTraining, SSI Logic.

Visit www.PMTraining.com for tools and resources on PMP training.

Activity

Duration (Days)

Dependency

Float

Start

0

-

A

8

Start

B

5

A

C

6

B, H

D

8

C

E

9

D, F

F

3

C, I

G

7

Start

H

8

G

I

9

H

J

5

I

K

2

J

L

3

J

Finish

0

Critical Path Method Exercise Solutions

Copyright © 2016 PMTraining, SSI Logic. All Rights Reserved.

Duplication of this material is not permitted without express consent of PMTraining, SSI Logic.

Visit www.PMTraining.com for tools and resources on PMP training.

Exercise 1 Solution:

1.

2. Network paths:

1.

2.

3.

4.

5.

6.

7.

8.

A -> C -> G -> H -> J

A -> C -> G -> I

B -> C -> G -> H -> J B -> C -> G -> I

D -> F -> G -> H -> J D -> F -> G -> I

E -> F -> G -> H -> J E -> F -> G -> I

3. Critical path: E -> F -> G -> H -> J (shown in red)

4. Activity floats shown in the diagram

Copyright © 2016 PMTraining, SSI Logic. All Rights Reserved.

Duplication of this material is not permitted without express consent of PMTraining, SSI Logic.

Visit www.PMTraining.com for tools and resources on PMP training.

0

6

6

E

0

0

6

Early Start

Duration

Early Finish

Task Name

Late Start

Slack

Late Finish

6

4

10

F

6

0

10

0

5

5

D

1

1

6

12

7

19

I

13

1

20

10

2

12

G

10

0

12

0

2

2

B

5

5

7

17

3

20

J

17

0

20

12

5

17

H

12

0

17

5

3

8

C

7

2

10

0

5

5

A

2

2

7

Exercise 2 Solution:

1.

2. Any activity on the critical path will have Late Finish equal to its Early Finish

Copyright © 2016 PMTraining, SSI Logic. All Rights Reserved.

Duplication of this material is not permitted without express consent of PMTraining, SSI Logic.

Visit www.PMTraining.com for tools and resources on PMP training.

21

2

23

M

25

4

27

13

8

21

L

17

4

25

25

3

28

N

27

2

30

20

5

25

K

20

0

25

13

7

20

J

13

0

20

5

8

13

I

5

0

13

0

5

5

H

0

0

5

25

5

30

G

25

0

30

10

3

13

F

22

12

25

5

5

10

C

17

12

22

2

3

5

B

14

12

17

0

2

2

A

12

12

14

11

1

12

E

29

18

30

10

1

11

D

28

18

29

Early Start

Duration

Early Finish

Task Name

Late Start

Slack

Late Finish

Exercise 3 Solution:

1.

2. Network paths:

1.

2.

3.

4.

5.

6.

7.

A  -> B -> C -> D -> E

A  -> B -> C -> F -> E

G -> H -> I -> J -> K

G -> H -> I -> J -> L

G -> H -> C -> D -> E

G -> H -> C -> F -> E

G -> H -> I -> F -> E

3. Critical path: G -> H -> C -> D -> E (shown in red)

4. Activity Floats shown in the network diagram

Copyright © 2016 PMTraining, SSI Logic. All Rights Reserved.

Duplication of this material is not permitted without express consent of PMTraining, SSI Logic.

Visit www.PMTraining.com for tools and resources on PMP training.

29

3

32

L

35

6

38

24

5

29

J

30

6

35

15

9

24

I

17

2

26

7

8

15

H

7

0

15

0

7

7

G

0

0

7

29

2

31

K

36

7

38

24

3

27

F

26

2

29

15

6

21

C

15

0

21

8

5

13

B

10

2

15

0

8

8

A

2

2

10

29

9

38

E

29

0

38

21

8

29

D

21

0

29

Early Start

Duration

Early Finish

Task Name

Late Start

Slack

Late Finish