## Implementation plan
Commercial Food Recycling Implementation Plan/Checklist | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
1. Preparation and planning
Develop a timetable (covering key deliverables outlined below)
Develop and confirm the business case and complete Appendix 1 (‘Cost Model Template’)
Visit WRAP’s website (www.wrap.org.uk/content/sme-food-waste/recycling-guidance) to consider customer expectations and review ‘free’ resources available to you/your customers
Consider ability to weigh the collected food waste (i.e. use of on-board weighing / ready reckoner)
Prepare a monitoring and evaluation plan and associated Key Performance Indicators (KPIs)
Ensure costs are understood and an accounting system in place
Charging structures agreed
Estimate income from confirmed and speculative customers
Debt management process and contracts developed/altered
2. Treatment facility for food waste collected (AD / IVC)
Enter into a Service Agreement / Contract with the treatment facility. Establish an understanding of the capacity and fees over the contract period
Confirm with treatment plant if food waste can be collected using caddy liners (if applicable) and what kind of liners are acceptable
Agree bulking arrangements (if required) and ensure compatibility with collection vehicles
Ensure that bulking arrangements comply with Animal By-Product Regulations (ABPR)
Confirm transportation arrangements of bulked food waste to treatment plant
Identify contingency arrangement should the primary treatment facility suffer a temporary plant closure
3. Procurement of collection equipment
Order external / internal bins and caddies
Order caddy liners
Finalise storage of equipment and programme the distribution to customers
Bin wash facilities in place
4. Vehicles for collection of food waste
Procure vehicles (investigate when order to be placed / expected delivery)
Liaise with trading standards to ensure vehicles meet ABPR requirements
Agree method to avoid overloading the bins (e.g. use of 'on-board' weighing) if bins are >140 litres
Arrange Personal Protective Equipment (PPE) and spill kit for vehicles
Arrange vehicle insurance and tax
Agree maintenance schedule
Agree contingency arrangements in event of breakdown
Decide on vehicle logos/signage
5. Marketing and communications
Establish the budget and programme
Complete Appendix 3 (‘Communications and Marketing Plan Template’) to inform your marketing and promotional strategy
Agree Draft Marketing plan
Produce brand and key messages using RecycleNow iconography for promotional materials
Use WRAP resources to help businesses roll out recycling internally (posters, bin stickers, training materials etc): www.wrap.org.uk/content/sme-food-waste/6-resources
Produce customer information pack (including instructional leaflets, poster and bin stickers)
Mobilise social media campaign linking web site with Twitter, Facebook, Linked In and Google Ad words (if applicable)
6. Customer recruitment and customer management
Recruitment of existing customers (where applicable)
Recruitment of new customers
Undertake individual site surveys to agree specific food waste collection requirements for customers
Issue new customer contracts or, where applicable, amend existing customer contracts
Set up / amend customer data collection systems
Set up / amend customer invoicing systems
7. Staffing
Recruit drivers / loaders. This may require new staff to be recruited or existing employees to be re-deployed
Make additional crew available at the start of a scheme to ensure rounds are completed and contamination issues rectified
Inform admin staff of the new service
Recruit sales and marketing staff
Train all staff
Consider taking collection crew and sales staff to the proposed food waste treatment facility so that they gain a firm understanding of what happens to food waste beyond collection
8. Health & Safety
Complete risk assessments for all aspects of the service
Compile method statement and safe systems of work for proposed collections
Identify training needs for staff (collection crews, contact centre staff etc)
Training of collection crews
Ensure collection crews are provided with appropriate PPE
9. Service launch
Collection method agreed (e.g. co-collected, dedicated rounds)
Collection frequency and timing decided
Ensure vehicle and crew are available, round sheets issued, operatives briefed and trained
Administration complete - agreements signed, waste transfer notes issued, accounts on system, payments confirmed for prepaid elements, etc
Sales staff and other third parties (as appropriate) notified and briefed
Treatment facility notified and briefed as appropriate, e.g. collection vehicle registration numbers supplied to weighbridges
One week before the start date distribute containers, liners and instruction leaflet on how to use the service to residents.
Officially launch the service
Meeting dates set for service review meetings