## Sheet1
IMPLEMENTATION PLAN |  |  |  |  | OWNERSHIP KEY: O = Owner P = Participant I = Inform
Activity # | Area | Task | Additional Information | Supporting Documents | Trust Project Lead | Senior management | NHSD Implementation Manager | Supplier | Women | GP | Planned Start Date | Planned Completion Date | Status
Implementation Pre Go Live Activities
1 | Project Management | Agree Project or Task Group | A project task group within the Trust will be agreed to take the implementation forward and to agree decisions. There should be representation from both the business and IT. | Pre-Engagement Assessemnt | O | P | P | P | I | I
2 | Project Management | Identify & Project Lead/Coordinator | A project lead will be identified for regular communications with NHSD | Pre-Engagement Assessemnt | O | I | I | I
3 | Technical Delivery | Review of release of Women's Digital Care Record functionality with Supplier to agree development timescales & Go Live | Agree Technical Go Live with supplier and Go Live Support with supplier including training and testing etc | Pre-Engagement Assessemnt | O |  |  | P
7 | Business Readiness | Complete Pre Engagement Assessment | To baseline where the Trust is, the processes in place and where NHSD can add value in terms of support | Pre-Engagement Assessemnt | P |  | O
8 | Business Readiness | Map Processes | Map current processes and 'to be' process | Workflow Template | O |  | P | P
4 | Communications & Engagement | Agree communication plans | Develop a communication plan setting out the way to communicate with key stakeholders | Communication Plan template | O | P | P | P | I | I
5 | Communications & Engagement | Implementation Rollout agreed | Inform NHSD Implementation manager and key stakeholders of the plan and date for Go Live | Communication Plan template | O |  | I | P
6 | Communications & Engagement | Inform relevant stakeholders and impacted areas of online record implementation | The named lead will discuss plans and seek commitment with Senior Management within the Trust, key staff alongside external stakeholders including GPs | Communication Plan template | O | I | I | I | I | I
9 | Business Readiness | Identify and start to baseline Problems/Benefits | Benefits - define what benefits the Trust expects to see as a result of implementation/ full roll out of Women's Health Record including a baseline where the trust is so benefits can be measured/ demonstrated | Benefits Realisation template | O |  | P
10 | Testing and assurance | Create a Testing Strategy/Plan | Review and agree plans for local testing with supplier including User Acceptance Testing | User Group Discussion | O |  |  | P
11 | Business Readiness | Update existing business processes | ? | Trust Policy Document Update Workflows | O |  | P
12 | Training and education | Create a Training Strategy | Identify staff to act as champions to cascade training and arrange training sessions with supplier including making materials such as quick reference guides available | Discuss in the user group | O |  | P | P
13 | Training and education | Create a Training Plan | Develop training plan to ensure all stakeholders are identified and method to provide them with appropraite training is in place | User Group Discussion Training Strategy Template | O |  | P | P | P | P
14 | Training and education | Develop training materials | Ensure relevant materials are available for women including information on accessing electronic record and also local education materials | QRG FAQ Web based Videos | O |  | I |  | P | I
14 | Milestone | Technical Go Live (TGL) | Check point |  | O |  | I | P
15 | Reporting | Verify Technical Go Live and successful implementation into Business as Usual (BAU) |  |  | O |  | I
16 | Milestone | Business Go Live (BGL) | Check point | Go-live check list | O | I | I | I | I | I
17 | Training and education | Roll out training: new starters, wider workforce/ stakeholders BAU (Downtime Processes) |  | SOP | O |  | P | P | P | P
Utilisation
18 | Reporting | Number of women with access to their Digital Care Record online |  | Reports from System | O |  | I
19 | Reporting | Number of women able to input into online record |  | Reports from System | O |  |  | P | P
20 | Reporting | Benefits - time saved, cost savings, feedback from women |  | Benefits Realisation template Benefit Report Report | O |  | P |  | P | P