## Instructions
Overview
Included in this document are general and project specific plan outlines to aid CNYCC and its partner organizations to develop plans for the long term success of the DSRIP program. These templates are not meant to be a prescribed set of tasks each partner needs to follow in order to reach DSRIP goals. Instead, they are meant to be a set of steps CNYCC will use to track and maintain our long term goals at the partner level. The methods partners use to reach these goals will often be unique to the organization, developed based on project activities such as DSRIP learning collaborative ,PICs, RPACs and Workgroups, or mandated by the state. In order to best report on progress, aid in best practice, and provide as much support as possible, we put together these general outlines and timelines to draw correlation between partners and drive each partner to a single cohesive end in preparation for value based payment environment.
Instructions
Detailed Implementation Plan Instructions are provided as a separate pdf email attachment. Please fill in the yellow cells below. Refer to the DSRIP Project Readiness reports attached in the email to determine which information needs to be provided on each tab. The links in the Table of Contents will take you to the specific tabs based on the provided reports.
|  | 0.2 | 1.Organizational information:
[ |  | 0.1 | 1.1 Parent organization name e.g. Hospital Health System: | [fill in Parent Organization Name here]
|  | 0.2 | 1.2 Child organization name e.g. Hospital Health System Peds Clinic: | [fill in Child Organization Name here]
|  | 0.2 | 2. Assigned partner contact
|  | 0.4 | 2.1 Name | [fill in Contact Name here]
|  | 0.4 | 2.2 Title | [fill in Contact Title here]
|  | 0.1 | 2.3 Department | [fill in Contact Department here]
|  | 0.2 | 2.4 Company / Business Unit | [fill in Contact Company/Business Unit here]
|  | 0.3 | 2.5 Address | [fill in Contact Address here]
|  | 0.3 | 2.6 Telephone | [fill in Contact Telephone here]
|  |  | 2.7 E-Mail Address | [fill in Contact Email here]
3. Table of Contents (clicking on link below will take you to that worksheet tab)
General Readiness
Contacts
2.a.i-Integrated Delivery System
2.a.iii-Health Home: At Risk Intervention
2.b.iii-ED Triage
2.b.iv-Care Transitions
2.d.i-Patient Activation Measure
3.a.ii-Behavioral Health Stabilization
3.a.i-Primary Care and Behavioral Care Integration
3.b.i-Evidence-Based Disease Mgmt Strategies
3.g.i-Palliative Care Model
4.d.i-Reduce Premature Births

## Contacts
Home
Functional Area | Contact | Email | Notes
RHIO SHIN-NY | Mike DiGiovanni | mdigiovanni@healtheconnections.org
RHIO Data Sharing | Mike DiGiovanni | mdigiovanni@healtheconnections.org
PCMH Recognition | Karen Joncas | karen.joncas@cnycares.org
Direct Messaging | HISPs,Vendor or See RHIO for HealtheConnections Contact
Meaningful Use Certification | Contact Vendor to Ensure Version is MU2 Certified
Electronic Medical Record | Peter Nolan | Peter.Nolan@cnycares.org
Analytics Tool | N/A
Documentation Requirements | Peter Nolan | Peter.Nolan@cnycares.org | Will proivde contact information of Project Managers for project specific requirements.
Electronic Medical Record Reporting and Registries (Data and Performance Project Manager) | Michele Treinin | Michele.Treinin@cnycares.org
Workflow Automation | Peter Nolan | Peter.Nolan@cnycares.org | Will proivde contact information of Project Managers for project specific requirements.
Electronic Medical Record Alerting | Peter Nolan | Peter.Nolan@cnycares.org | Will proivde contact information of Project Managers for project specific requirements.
Alerting using RHIO | Mike DiGiovanni | mdigiovanni@healtheconnections.org
Care Management and Coordination | Peter Nolan | Peter.Nolan@cnycares.org | Will proivde contact information of Project Managers for project specific requirements.
Population Health Management | Peter Nolan | Peter.Nolan@cnycares.org | Will proivde contact information of Project Managers for project specific requirements.
CNY Regional Center for Tobacco Health Systems | Chris Owens | christopher.owens@sjhsyr.org | CNY Regional Center for Tobacco Health Systems is a grant funded program run by St. Josephs Hospital Health System
CNY Regional Center for Tobacco Health Systems | Beth Gero | cheryl.gero@sjhsyr.org | CNY Regional Center for Tobacco Health Systems is a grant funded program run by St. Josephs Hospital Health System
2.a.i-Integrated Delivery System | Peter Nolan Karen Joncas | Peter.Nolan@cnycares.org karen.joncas@cnycares.org | 2.a.i-Integrated Delivery System Project Manager(s)
2.a.iii-Health Home: At Risk Intervention | Kate Weidman | Kate.Weidman@cnycares.org | 2.a.iii-Health Home: At Risk Intervention Project Manager
2.b.iii-ED Triage | Kate Weidman | Kate.Weidman@cnycares.org | 2.b.iii-ED Triage Project Manager
2.b.iv-Care Transitions | Tammy VanEpps | Tammy.VanEpps@cnycars.org | 2.b.iv-Care Transitions Project Manager
2.d.i-Patient Activation Measure | Kelsie Montaque | kelsie.montaque@cnycares.org | 2.d.i-Patient Activation Measure Project Manager
3.a.ii-Behavioral Health Stabilization | Kelly Lane | kelly.lane@cnycares.org | 3.a.ii-Behavioral Health Stabilization Project Manager
3.a.i-Primary Care and Behavioral Care Integration | Kelly Lane | kelly.lane@cnycares.org | 3.a.i-Primary Care and Behavioral Care Integration Project Manager
3.b.i-Evidence-Based Disease Mgmt Strategies | Karen Joncas | karen.joncas@cnycares.org | 3.b.i-Evidence-Based Disease Mgmt Strategies Project Manager
3.g.i-Palliative Care Model | Tammy VanEpps | Tammy.VanEpps@cnycars.org | 3.g.i-Palliative Care Model Project Manager
4.d.i-Reduce Premature Births | Kelsie Montaque | kelsie.montaque@cnycares.org | 4.d.i-Reduce Premature Births Project Manager

## General Readiness
|  | Home | Functional Areas (rows highlighted in orange) will be tracked at the project level. Steps to meet these goals are general within this tab and will be more detailed in the project specific tabs.
High Level Gap to Goal Steps for HIT Related Functional Areas
| RHIO SHIN-NY | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.) Contact RHIO to evaluate their products and services http://www.healtheconnections.org/what-we-do/hie-services/ Contact information for HealtheConnections is located on the contacts tab. | 2016-09-30 | Select an option
| 2.) Contact RHIO (HealtheConnections) in regards to participation agreement | 2016-09-30 | Select an option
| 3.) Sign participation agreement | 2017-03-31 | Select an option
| 4.) Evaluate what other services may benefit your organization | 2018-03-31 | Select an option
| RHIO Data Sharing | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.) Contact RHIO to evaluate their products and services http://www.healtheconnections.org/what-we-do/hie-services/ Contact information for HealtheConnections is located on the contacts tab. | 2016-09-30 | Select an option
| 2.) Contact RHIO (HealtheConnections) in regards to participation agreement, if not in place. | 2016-09-30 | Select an option
| 2a.)If agreement is in place, begin working with RHIO on their integration process | 2017-03-31 | Select an option
| 3.) Contact EMR vendor in regards to RHIO Integration and data sharing use cases | 2017-03-31 | Select an option
| 4.) Work with RHIO and EMR vendor to develop and test data sharing capabilities based on use cases | 2017-06-30 | Select an option
| 5.) Start sending data to RHIO (HealtheConnections) | 2018-03-31 | Select an option
| PCMH Recognition | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.) CNYCC's PCMH expert will be working with you to achieve PCMH Recognition. Please refer to contact tab for PCMH Recognition expert contact information | 2018-03-31 | Select an option
| Direct Messaging | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.) Evaluate if EMR has Direct Messaging capability or if a third party is required. If your organization does not have an EMR, please refer to step 3.1. | 2016-09-30 | Select an option
| 2.) Regardless of EMR capabilities, Direct functionality is contained within EMR, a HISP (Health Information Service Provider) will be required to obtain direct address. Companies who are HISPs include Surescripts and MedAllies. Evaluate HISPs including HealtheConnections as a provider of Direct Services. Contact information for HealtheConnections is located on the contacts tab. | 2016-09-30 | Select an option
| 3.) If Direct capabilities are contained in EMR work with Vendor to configure. | 2016-12-31 | Select an option
| 3.1) If Direct capabilities are not contained in EMR or your organization does not have an EMR, HealtheConnections can provide Direct address services. Contact information for HealtheConnections is located on the contacts tab. | 2016-12-31 | Select an option
| 4.) Begin configuration of Direct Messaging with HISP (and EMR vendor if EMR integration and triggering is taking place ) | 2017-12-31 | Select an option
| 5.) Implement Direct capabilities to send and receive information, based on triggers defined by organization or DSRIP requirements | 2017-03-31 | Select an option
| 6.) Begin sending and receiving Direct Messages | 2018-03-31 | Select an option
| Meaningful Use Certification | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.) Organizations are only required to have a Stage 2 Meaningful Use platform. Please verify with your vendor that your EMR version is MU stage 2 certified. | 2016-12-31 | Select an option
| 2.) Work with your DSRIP Coordinator and CNYCC representatives to evaluate the need to satisfy this requirement. | 2016-12-31 | Select an option
| Electronic Medical Record | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.) If your organization does not have an electronic medical record, please schedule a meeting with CNYCC and request CNYCCs EMR implementation toolset | 2016-09-30 | Select an option
| 1.2) Verify with CNYCC that an EMR is required within your organization. (State data can potentially misclassify organizations) | 2016-09-30 | Select an option
| 2.) Send RFP to EMR vendors to begin selection process |  | Select an option
| 3.) Evaluate best vendor based on organizational needs and best practice defined by local, state and national programs |  | Select an option
| 3.) Develop timeline and project structure for EMR implementation |  | Select an option
| 4.) Validate workflows with end users, physicians, providers and operational staff |  | Select an option
| 5.) Develop system to meet needs of organization, and programs your organization is involved in |  | Select an option
| 6.) Test workflows and train employees on new EMR platform |  | Select an option
| 7.) Go-Live with new EMR system | EMR Related Requirements are due as soon as 3/31/2018. Therefore EMR adoption is required prior to milestone dates. | Select an option
| Documentation Requirements | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.) Work with your DSRIP coordinator and applicable operational and clinical staff to determine the documentation requirements for project activities required to be captured discretely within you Electronic Medical Record | 2016-09-30 | Select an option
| 2.) Review Project Specific Readiness Report and DSRIP Project Activity Inventory Checklist to evaluate where Documentation Requirements may be needed | 2016-09-30 | Select an option
| 3.) Evaluate assessments and tools already in place at your organization and determine which are integrated within your EMR. | 2016-09-30 | Select an option
| 4.) Determine which tools and assessments that are integrated from step 3 are reportable within your EMR | 2016-09-30 | Select an option
| 5.) Create list of documentation requirements that need to be built into your EMR. This list may be more specific than what's included in the DSRIP Project Activity Inventory Checklist. | 2016-09-30 | Select an option
| 6.) Create list of assessments and tools within your organization and their level of integration within your EMR | Due dates for the implementation of this functional area will be determined by project specific requirements | Select an option
| Electronic Medical Record Reporting and Registries | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.) Work with your DSRIP coordinator and applicable operational and clinical staff to determine the reporting requirements for project activities. | 2016-09-30 | Select an option
| 2.) Consult Project Addenda, as well as information from other project activities to evaluate Reporting Requirements | 2016-09-30 | Select an option
| 3.) Review Project Specific Readiness Report and DSRIP Project Activity Inventory Checklist to evaluate where Electronic Medical Record Reporting and Registries may be needed | 2016-09-30 | Select an option
| 4.) Create list of reporting and registry requirements that need to be built into your EMR. This list may be more specific than what's included in the DSRIP Project Activity Inventory Checklist. | 2016-09-30 | Select an option
| 5.) Work with CNYCCs Data and Performance Project Manager on Report Definitions. CNYCCs reporting contact information is located on the contacts tab of this document. | 2016-09-30 | Select an option
| 6.) Create list of reporting and registry requirements within your organization and the data elements required to create new reports | Due dates for the implementation of this functional area will be determined by project specific requirements | Select an option
| Workflow Automation | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.) Work with your DSRIP coordinator and applicable operational and clinical staff to determine the requirements for workflow automation based on project activities | 2016-09-30 | Select an option
| 2.) Review Project Specific Readiness Report and DSRIP Project Activity Inventory Checklist to evaluate where Workflow Automation is required | 2016-09-30 | Select an option
| 3.) Create list of workflow automation requirements that need to be built into your EMR. The baseline list for workflow automation is located within your DSRIP Project Activity Inventory Checklist. | 2016-09-30 | Select an option
| 4.) Work with internal operational and IT staff, as well as your EMR vendor to implement automated workflows required by DSRIP activities, based on needs from step 2 | Due dates for the implementation of this functional area will be determined by project specific requirements | Select an option
| Electronic Medical Record Alerting | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.) Work with your DSRIP coordinator and applicable operational and clinical staff to determine the alerting requirements for project activities. Please note there two separate types of alerting within project activities. a.) The first is related to alerts to downstream providers based on ED Encounters, Hospital Admissions and Hospital Discharges using the RHIO (HealtheConnections) myAlerts functionality. b.)The second type of alerting is associated the ability for the electronic medical records to notify users of best practice or required interventions if certain patient or encounter level criteria are met. | 2016-09-30 | Select an option
| 2.) Review Project Specific Readiness Report and DSRIP Project Activity Inventory Checklist to evaluate where Electronic Medical Record Alerting is required | 2016-09-30 | Select an option
| 3.) Create list of alerting requirements that need to be built into your HIT infrastructure. The baseline list for workflow automation is located within your DSRIP Project Activity Inventory Checklist. | 2016-09-30 | Select an option
| 4.) Work with your IT staff and EMR vendor to integrate necessary requirements into EMR, based on needs from step 2 | Due dates for the implementation of this functional area will be determined by project specific requirements | Select an option
| Care Management and Coordination | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.) Care Management and Coordination is the combination Workflow Automation, Documentation Requirements, and Operational Workflows. It can involve the RHIO and various EMR functions. Work with your DSRIP coordinator and applicable operational and clinical staff to determine care management and coordination requirements for project activities. | 2016-09-30 | Select an option
| 2.) Review Project Specific Readiness Report and DSRIP Project Activity Inventory Checklist to evaluate where Care Management and Coordination is required | 2016-09-30 | Select an option
| 3)Create list of care management and coordination requirements that need to be built or integrated into your HIT infrastructure. The baseline list for workflow automation is located within your DSRIP Project Activity Inventory Checklist. | 2016-09-30 | Select an option
| 4.) Work with your IT staff and EMR vendor to integrate necessary requirements into EMR, based on needs from step 2 | Due dates for the implementation of this functional area will be determined by project specific requirements | Select an option

## 2.a.i-Integrated Delivery Syste
|  | Home | In every section, the last due date of that section aligns with DSRIP related milestones. It is suggested that your organization works to complete these tasks 60-90 days in advance of the milestone where possible
Project Specific HIT Requirement Implementation Plan: 2.a.i-Integrated Delivery System
| Electronic Medical Record Alerting/RHIO Alerting | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.) Work with your DSRIP coordinator and applicable operational and clinical staff to determine the desired workflow and process to obtain alerts directly from Hospitals and Emergency Departments | 2016-09-30 | Select an option
| 2.) If your organization is a non-Hospital or non-Acute facility evaluate your organization's ability to receive alerts directly from Hospitals or Emergency Departments based on the information from step 1 2.)If your an organization is a Hospital or Acute facility evaluate your organization's ability to send alerts directly from Hospitals or Emergency Departments to community providers using the RHIO or other mechanisms based on the information from step 1 **For partners that provide both services, alerting services are required for non-acute locations | 2016-09-30 | Select an option
| 3.) Work with your IT department, EMR vendor, and CNYCC to develop plan to implement necessary alerting use cases into EMR | 2017-03-31 | Select an option
| 4.) Contact and evaluate the RHIO (HealtheConnections) to see if their alerting workflows, products or services are appropriate for your organization. | 2017-06-30 | Select an option
| 5.) Begin implementation of alerting services workflows, including mechanisms to follow up with patients post discharge. |  | Select an option
| 6.) Once alerting is in place, develop process for patient follow up | 2017-09-30 | Select an option
| 7.) Implement patient follow up process for ED and hospital admissions | 2018-03-31 | Select an option
| Care Management and Coordination & Documentation Requirements | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.) Work with your DSRIP coordinator and applicable operational and clinical staff to evaluate your organizations current ability to track referrals to outside organizations including community based organizations. | 2016-09-30 | Select an option
| 2.) Verify your organization has the ability to integrate referral tracking to outside organizations including community based organizations in the electronic medical record. If you do not have an EMR or your vendor cannot support an integrated solution please skip to step 4. | 2016-09-30 | Select an option
| 3.) Work with your IT team and EMR vendor to integrate necessary referral tracking mechanisms into EMR | 2017-03-31 | Select an option
| 4.) Develop operational processes around referral management to community based organizations | 2017-09-30 | Select an option
| 5.) Test new electronic and/or operational processes | 2018-03-31 | Select an option
| 6.) Implement referral tracking to outside organizations including community based organizations | 2019-03-31 | Select an option

## 2.a.iii-Health Home At Risk Int
|  | Home | In every section, the last due date of that section aligns with DSRIP related milestones. It is suggested that your organization works to complete these tasks 60-90 days in advance of the milestone where possible
Project Specific HIT Requirement Implementation Plan: 2.a.iii - Health Home: At Risk Intervention
| Electronic Medical Record Reporting and Registries | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.a) Work with your DSRIP coordinator and applicable operational and clinical staff to determine if your organization has the ability to generate custom clinical and practice management reports regarding the tracking of patients with one or more chronic conditions. | 2016-09-30 | Select an option
| 2.a) Does your organization have the capability to identify patients with one or more chronic conditions? | 2016-09-30 | Select an option
| 3.a)Gather data elements required to evaluate patients' chronic condition. This information will be obtainable through PICs and project workgroups. | 2016-09-30 | Select an option
| 4.a) Develop custom reports based on DSRIP requirements. Test this report to ensure its accuracy. | 2016-12-01 | Select an option
| 5.a) Work with CNYCC's Data and Performance Project Manager as well as the 2.a.iii Project Manager to Determine if report results are accurately capturing relevant information. Contact information is included on the contacts tab. | 2017-03-31 | Select an option
| Workflow Automation | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.) Work with your DSRIP coordinator and applicable operational and clinical staff to determine the desired workflow and process to perform referral management for DSRIP Care Management | 2016-09-30 | Select an option
| 2.Begin the development of a referral management process based on project standards. | 2016-09-30 | Select an option
| 3.) Evaluate if part or all of referral management processes can be automated within EMR | 2016-12-01 | Select an option
| 4.) Work with your IT and EMR vendor to integrate necessary requirements/workflow into EMR | 2016-12-31 | Select an option
| 5.) Begin use of new referral management process | 2017-03-31 | Select an option
| Documentation Requirements | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.a) Work with your DSRIP coordinator and applicable operational and clinical staff to determine what standard assessments and tools are required for care planning to be added to your EMR as part of project activities | 2016-09-30 | Select an option
| 1.b)Work with your DSRIP coordinator and applicable operational and clinical staff to determine what patient educational materials are required as part of DSRIP activities | 2016-09-30 | Select an option
| 2.a) Verify applicable assessments and tools from step 1.a are practiced or implemented within your organization | 2016-09-30 | Select an option
| 2.b) Ensure patient educational materials account for various cultural and educational differences | 2016-09-30 | Select an option
| 3.a) Verify documentation standards and assessments from steps 1.a and 2.a are currently included in your EMR as discrete reportable fields. | 2016-12-01 | Select an option
| 3.b) Verify patient educational materials required within this project activity are currently loaded into your EMR. | 2016-12-01 | Select an option
| 3.b.1) Ensure patient educational materials are available in more than one language | 2016-12-01 | Select an option
| 4.a) Work with your IT department and EMR vendor to integrate necessary requirements/assessments into EMR | 2016-12-31 | Select an option
| 4.b) Work with your IT department and EMR vendor to integrate necessary patient education into EMR | 2016-12-31 | Select an option
| 5.a) Begin using required standard assessments for project activities | 2017-03-31 | Select an option
| 5.b) Begin using required educational materials | 2017-03-31 | Select an option
| Care Management and Coordination | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.a) Work with your DSRIP coordinator and applicable operational and clinical staff to determine your organizations requirements to refer patients to community based organizations | 2016-09-30 | Select an option
| 1.b) Work with your DSRIP coordinator and applicable operational and clinical staff to evaluate your organizations current care plans and their level of standardization. Additionally evaluate the alignment of current care plans compared to the care plan requirements within this project. | 2016-09-30 | Select an option
| 2.a) Determine which parts of your referral workflow can be documented within the electronic medical record. | 2016-12-31 | Select an option
| 2.b) Adjust care plans based on requirements from DSRIP activities including DSRIP learning collaborative and workgroups. | 2016-12-31 | Select an option
| 3.ab.)Work with your IT and EMR vendor to integrate necessary requirements/workflows from step 2 into EMR | 2016-06-30 | Select an option
| 4.a) Begin working with CBOs on referring and reducing patient risk | 2017-12-31 | Select an option
| 4.b) Begin using standard care plan elements | 2017-12-31 | Select an option

## Sheet1 (hidden)
Project Specific HIT Requirement Work Plan: | General Readiness
| 2.a.i-Integrated Delivery System | Project Specific HIT Requirement Work Plan: 2.a.i-Integrated Delivery System
| 2.a.iii-Health Home: At Risk Intervention | Project Specific HIT Requirement Work Plan: 2.a.iii-Health Home: At Risk Intervention
| 2.b.iii-ED Triage | Project Specific HIT Requirement Work Plan: 2.b.iii-ED Triage
| 2.b.iv-Care Transitions | Project Specific HIT Requirement Work Plan: 2.b.iv-Care Transitions
| 2.d.i-Patient Activation Measure | Project Specific HIT Requirement Work Plan: 2.d.i-Patient Activation Measure
| 3.a.ii-Behavioral Health Stabilization | Project Specific HIT Requirement Work Plan: 3.a.ii-Behavioral Health Stabilization
| 3.a.i-Primary Care and Behavioral Care Integration | Project Specific HIT Requirement Work Plan: 3.a.i-Primary Care and Behavioral Care Integration
| 3.b.i-Evidence-Based Disease Mgmt Strategies | Project Specific HIT Requirement Work Plan: 3.b.i-Evidence-Based Disease Mgmt Strategies
| 3.g.i-Palliative Care Model | Project Specific HIT Requirement Work Plan: 3.g.i-Palliative Care Model
| 4.d.i-Reduce Premature Births | Project Specific HIT Requirement Work Plan: 4.d.i-Reduce Premature Births

## 2.b.iii-ED Triage
|  | Home | In every section, the last due date of that section aligns with DSRIP related milestones. It is suggested that your organization works to complete these tasks 60-90 days in advance of the milestone where possible
Project Specific HIT Requirement Implementation Plan: 2.b.iii-ED Triage
| Workflow Automation | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.) Work with your DSRIP coordinator and applicable operational and clinical staff to determine the desired workflow and process to perform referral management and care coordination with PCPs post discharge from the Emergency Department. | 2016-09-30 | Select an option
| 2.) Based on information from step 1 begin development on referral management process. (to pcp) | 2016-09-30 | Select an option
| 3.) Evaluate if part or all of referral management processes can be automated within EMR | 2016-12-01 | Select an option
| 4.) Work with your IT and EMR vendor to integrate necessary requirements/workflow from step 3 into EMR | 2016-12-31 | Select an option
| 5.) Begin use of new referral management process | 2017-03-31 | Select an option
| Documentation Requirements | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.) Work with your DSRIP coordinator and applicable operational and clinical staff to determine the necessary assessments required by project activities to assess patients needs /resources within the community. | 2016-09-30 | Select an option
| 2.)Verify the applicable assessments and tools necessary to help identify needed community resources and enlist the patient into identified services from step 1 are implemented within your organization. | 2016-09-30 | Select an option
| 3.) Ensure documentation standards and assessments from steps 1 and 2 are currently included in your EMR as discrete reportable fields. | 2016-12-01 | Select an option
| 4.) Work with your IT department and EMR vendor to integrate necessary requirements/assessments into EMR | 2016-12-31 | Select an option
| 5.) Test and implement documentation requirements related to Assessing Patient Needs | 2017-03-31 | Select an option

## 2.b.iv-Care Transitions
|  | Home | In every section, the last due date of that section aligns with DSRIP related milestones. It is suggested that your organization works to complete these tasks 60-90 days in advance of the milestone where possible
Project Specific HIT Requirement Implementation Plan: 2.b.iv-Care Transitions
| Electronic Medical Record Alerting: Acute Only | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.) Work with your DSRIP coordinator and applicable operational and clinical staff to determine required alerting mechanisms for care transitions. | 2016-09-30 | Select an option
| 2.)Determine if EMR is capable of sending alerts to PCP prior to discharge | 2016-09-30 | Select an option
| 3.) Based on technical capabilities develop a workflow to notify PCP prior to discharge | 2016-11-04 | Select an option
| 4.) Contact and evaluate the RHIO (HealtheConnections) to see if their alerting workflows, products or services are appropriate for your organization. | 2016-11-04 | Select an option
| 5.) Work with your IT and EMR vendor to integrate necessary requirements/workflow into EMR | 2016-12-01 | Select an option
| 6.) Test and implement workflow | 2017-03-31 | Select an option
| Workflow Automation: Acute Only | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.) Work with your DSRIP coordinator and applicable operational and clinical staff to determine the notifications required to be sent to organizational staff within your facility, as well as outside care managers. | 2016-09-30 | Select an option
| 2.)Determine if EMR is capable of sending alerts, messages or other notifications to care managers prior to discharge | 2016-09-30 | Select an option
| 3.) Based on technical capabilities develop a workflow to notify care manager to set up a visit with the patient prior to discharge | 2016-11-04 | Select an option
| 4.) Work with your IT and EMR vendor to integrate necessary requirements/workflow into EMR | 2016-12-01 | Select an option
| 5.) Test and implement workflow | 2017-03-31 | Select an option
| Workflow Automation | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.)Work with your DSRIP coordinator and applicable operational and clinical staff to determine the desired workflow and process to perform transitions of patient care records from one provider to another which will include the use of evidence based care transitions tools | 2016-09-30 | Select an option
| 2.) Evaluate systems capability to transition care records electronically from on provider to another as well as its ability to implement evidenced based care transitions tools | 2016-09-30 | Select an option
| 3.) Based on technical capabilities develop a workflow to transition patient care records from one provider to another | 2016-11-04 | Select an option
| 4.) Work with your IT and EMR vendor to integrate necessary requirements/workflow into EMR | 2016-12-01 | Select an option
| 5.)Test and implement care transitions process. | 2017-03-31 | Select an option

## 2.d.i Patient Activation Measur
|  | Home | In every section, the last due date of that section aligns with DSRIP related milestones. It is suggested that your organizations work to complete these tasks 60-90 days in advance of the milestone where possible
Project Specific HIT Requirement Implementation Plan: 2.d.i-Patient Activation Measure
| Electronic Medical Record Reporting and Registries | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.) Work with your DSRIP coordinator and applicable operational and clinical staff to determine the reporting specifications for patient utilization. | 2016-09-30 | Select an option
| 2.) Gather data elements required to evaluate patients utilization status. This information should be obtainable through Learning Collaborative and project workgroups | 2016-12-01 | Select an option
| 3.)If possible, develop custom reports based on DSRIP requirements, test reports to ensure its accuracy. CNYCC will also generate reports on patient activation from flourish tool | 2016-12-31 | Select an option
| 4.) Work with CNYCCs Data and Performance Project Manager as well as the 2.d.i Project Manager to Determine if report results are accurately capturing relevant information. Contact information is included on the contacts tab. | 2017-03-31 | Select an option
| Documentation Requirements | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.a) Work with your DSRIP coordinator and applicable operational and clinical staff to determine the level of integration of community based education resources within your HIT systems. | 2016-09-30 | Select an option
| 2.a) Determine if your organization currently has gaps in its use of community based health education resources or programs based on project requirements. | 2016-09-30 | Select an option
| 3.a) Determine if your organizations educational materials can be integrated into your EMR. | 2016-12-01 | Select an option
| 4.a)Work with your IT department and vendor to integrate necessary CBO related materials into your EMR where applicable | 2016-12-31 | Select an option
| 5.a) Test and implement community based organization education materials. | 2017-03-31 | Select an option

## 3.a.i-Primary Care and Behavior
|  | Home | In every section, the last due date of that section aligns with DSRIP related milestones. It is suggested that your organization works to complete these tasks 60-90 days in advance of the milestone where possible
Project Specific HIT Requirement Implementation Plan: 3.a.i-Primary Care and Behavioral Care Integration
| Electronic Medical Record Alerting | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.a)Work with your DSRIP coordinator and applicable operational and clinical staff to determine which behavioral health screenings require an encounter level alert to be performed | 2016-09-30 | Select an option
| 1.b)Work with your DSRIP coordinator and applicable operational and clinical staff to determine protocols required for "warm transfers" between behavioral health provider and primary care when prompted by a positive behavioral health screen. | 2016-09-30 | Select an option
| 2.a) Design alerts or workflows based on best practices and project requirements to prompt end users that a behavioral health screen is required | 2017-03-31 | Select an option
| 2.b) Within designed workflow, account for "warm transfer" between behavioral health provider and primary care when positive screen requires it. | 2017-03-31 | Select an option
| 3.ab) Work with your IT and EMR vendor to integrate necessary requirements into EMR, including alerts for behavioral health screens and warm transfers | 2017-06-30 | Select an option
| 4.ab) Implement alerting mechanisms based on DSRIP alerting use cases, or decided upon workflows, which include warm transfers and prompts for evidence based screens | 2018-03-31 | Select an option
| Workflow Automation | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.) Work with your DSRIP coordinator and applicable operational and clinical staff to determine the desired workflow and process to properly integrate behavioral health and medical records where the project requires. | 2016-09-30 | Select an option
| 2.) Determine if your EMR or system of record is capable of integration based on DSRIP requirements for information integration of behavioral and primary care services | 2016-09-30 | Select an option
| 3.) Work with CNYCC, Vendor and your IT staff to address concerns and map out potential solutions for record integration | 2017-03-31 | Select an option
| 4.) Work with your IT and EMR vendor to integrate necessary requirements/workflow into EMR to allow for more efficient co-location | 2017-06-30 | Select an option
| 5.) Test and implement integration of medical and behavioral health records | 2018-03-31 | Select an option
| Documentation Requirements | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.) Work with your DSRIP coordinator and applicable operational and clinical staff to determine the necessary behavioral health screens/assessments required for this project. | 2016-09-30 | Select an option
| 2.) Are the applicable screens/assessments from step 1 implemented within your organization, inventory gaps based on project requirements | 2016-09-30 | Select an option
| 3.) Are documentation screens and assessments from steps 1 and 2 currently included in your EMR as discrete reportable fields. | 2017-03-31 | Select an option
| 4.) Work with your IT department and EMR vendor to integrate necessary behavioral health screens/assessments into EMR | 2017-06-30 | Select an option
| 5.) Test and implement new documentation requirements | 2018-03-31 | Select an option

## 3.a.ii-Behavioral Health Stabil
|  | Home | In every section, the last due date of that section aligns with DSRIP related milestones. It is suggested that your organization works to complete these tasks 60-90 days in advance of the milestone where possible
Project Specific HIT Requirement Implementation Plan: 3.a.ii-Behavioral Health Stabilization
| Electronic Medical Record Alerting | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.) Work with your DSRIP coordinator and applicable operational and clinical staff to determine required alerting mechanisms for behavioral health crisis intervention. | 2016-09-30 | Select an option
| 2.) Consult DSRIP learning collaborative and DSRIP workgroups regarding required workflows around alerts and messaging pertaining to crisis intervention | 2016-12-31 | Select an option
| 3.) Work with internal IT and CNYCC to develop use cases for EMR alerts | 2017-03-31 | Select an option
| 4.) Work with your IT and EMR vendor to integrate necessary alerting mechanism for crisis stabilization and intervention into EMR | 2017-06-30 | Select an option
| 5.) Test and implement workflows based on project requirements | 2018-03-31 | Select an option

## 3.b.i-Evidence Based Disease Mg
|  | Home | In every section, the last due date of that section aligns with DSRIP related milestones. It is suggested that your organization works to complete these tasks 60-90 days in advance of the milestone where possible
Project Specific HIT Requirement Implementation Plan: 3.b.i-Evidence-Based Disease Mgmt. Strategies
| Electronic Medical Record Reporting and Registries | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.abc) Work with your DSRIP coordinator and applicable operational and clinical staff to determine the reporting specifications for hypertensive patients that have not had a recent visit | 2016-09-30 | Select an option
| 1.b) Work with your DSRIP coordinator and applicable operational and clinical staff to determine the reporting specifications for supporting hot spotting activities | 2016-09-30 | Select an option
| 1.c) Work with your DSRIP coordinator and applicable operational and clinical staff to determine the reporting specifications for patient with elevated blood pressure who are not diagnosed hypertensive. | 2016-09-30 | Select an option
| 2.a) Evaluate capability to generate list of patients with hypertension that have not had a recent visit, based on criteria generated from project activities | 2016-09-30 | Select an option
| 2.b) Evaluate capability to generate list of patients with hypertension in combination with the demographics to support activities in high risk neighborhoods | 2017-06-30 | Select an option
| 2.c) Evaluate capability to generate list of patients with high blood pressure that have not had a diagnosis of hypertension so they can be scheduled for a visit, based on criteria generated from project activities | 2017-06-30 | Select an option
| 3abc.) Work with CNYCCs Data and Performance Project Manager, 3.b.i Project Manager, IT and Vendor on building out Report Definitions. | 12/02/2016 a 9/30/2017 b 9/30/2017 c | Select an option
| 4.abc)Work with your IT and EMR vendor to Build, Run and test reports in EMR | 12/02/2016 a 9/30/2017 b 9/30/2017 c | Select an option
| 5.abc) Work with CNYCCs Data and Performance Project Manager as well as the 3.b.i Project Manager to Determine if report results are accurately capturing relevant information. Contact information is included on the contacts tab. | 3/31/2017 a 3/31/2018 b 3/31/2018 c | Select an option
| Electronic Medical Record Alerting | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.ab) Work with your DSRIP coordinator and applicable operational and clinical staff to determine required alerting mechanisms for the 5 A's of tobacco cessation as well as the NYS Quit line. | 2016-09-30 | Select an option
| 2.ab) Based on project requirements, Identify where in workflow prompts for NYS smoker quit line and 5 A's of tobacco cessation will be placed. | 2016-09-30 | Select an option
| 3.ab) Work with CNYCC and their partner, the CNY Regional Center for Tobacco Health Systems to implement project requirements. Contact information for 3.b.i project manager and Regional Center for Tobacco Health Systems are located on the contacts tab. | 2016-12-01 | Select an option
| 4.ab) Work with Internal IT, Vendor and CNYCC to develop use cases for tobacco cessation processes. | 2016-12-31 | Select an option
| 5.ab) Test, Train and Implement tobacco cessations process mechanisms based on DSRIP requirements | 2017-03-31 | Select an option
| Documentation Requirements: Track A & B | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.a) Work with your DSRIP coordinator and applicable operational and clinical staff to determine the necessary assessments required by project activities to adopt preventive strategies of the Million Hearts | 2016-09-30 | Select an option
| 1.b) Work with your DSRIP coordinator and applicable operational and clinical staff to determine the necessary assessments required by project activities to adopt standardized treatment protocols for patients with hypertension or elevated cholesterol. | 2016-09-30 | Select an option
| 2.a) Evaluate how the preventive strategies of the Million Hearts Campaign can be integrated discreetly into your system of record | 2016-09-30 | Select an option
| 2.b) Evaluate how treatment protocols from step 1.b can be discreelty intergrated into your EMR if they are not already | 2016-09-30 | Select an option
| 3.ab) Ensure documentation standards and assessments from steps 1.a,1.b 2.a, and 2.b are currently included in your EMR as discrete reportable fields. | 2017-12-01 | Select an option
| 4.ab) Work with your IT department and EMR vendor to integrate necessary requirements/assessments into EMR | 2016-12-31 | Select an option
| 5.ab) Test and implement new documentation requirements | 2017-03-31 | Select an option
| Documentation Requirements: Track C | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.c) Work with your DSRIP coordinator and applicable operational and clinical staff to determine the desired workflow and process to perform referral management to community based organization | 2016-09-30 | Select an option
| 2.c) Based on information from step 1 begin work with your team to develop a referral management process to community based organizations. This workflow must include follow up from community based organization back to referring organization regarding participation in CBO's services as well as behavioral health status changes. | 2017-03-31 | Select an option
| 3.c) Evaluate if part or all of referral management processes can be automated within EMR | 2017-06-30 | Select an option
| 4.c) Work with your IT and EMR vendor to integrate necessary requirements/workflow into EMR | 2017-09-30 | Select an option
| 5.c) Begin use of new referral management process | 2018-03-31 | Select an option
| Care Management and Coordination | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.)Work with your DSRIP coordinator and applicable operational and clinical staff to determine projects requirements around the documentation and transmission of patient care team members | 2016-09-30 | Select an option
| 2.) Work with CNYCC to determine care team documentation and coordination requirements | 2016-12-01 | Select an option
| 3.)Work with your IT and EMR vendor to integrate care team documentation as well as necessary requirements/workflows into EMR | 2016-12-01 | Select an option
| 4.) Test documentation of care team, be sure that care team can be reported on discreetly | 2016-12-31 | Select an option
| 5.) Implement the use of care coordination teams | 2017-03-31 | Select an option

## 3.g.i-Palliative Care Model
|  | Home | In every section, the last due date of that section aligns with DSRIP related milestones. It is suggested that your organization works to complete these tasks 60-90 days in advance of the milestone where possible
Project Specific HIT Requirement Implementation Plan: 3.g.i-Palliative Care Model
| Documentation Requirements | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.a) Work with your DSRIP coordinator and applicable operational and clinical staff to determine the required tools for clinical guidelines based on project activities. | 2016-09-30 | Select an option
| 2.b) Work with your DSRIP coordinator and applicable operational and clinical staff to determine the required patient health severity tool based on project activities. | 2016-09-30 | Select an option
| 2.c) Work with your DSRIP coordinator and applicable operational and clinical staff to determine the required palliative care plan template based on project activities. | 2016-09-30 | Select an option
| 2.a) Evaluate assessments, workflows and tools that are already in place at your organization surrounding clinical guidelines | 2016-09-30 | Select an option
| 2.b) Evaluate assessments, workflows and tools that are already in place at your organization surrounding patient health severity tools (SPICT,POS) | 2016-09-30 | Select an option
| 2.c) Evaluate assessments, workflows and tools that are already in place at your organization surrounding palliative care plan templates | 2016-09-30 | Select an option
| 3.abc) Develop strategy to address gaps in assessment, workflow and EMR documentation based on the previous two steps | 2016-12-01 | Select an option
| 4.abc) Are documentation standards and assessments from steps 1.abc and 2.a,2.b,2.c currently included in your EMR as discrete reportable fields. | 2016-12-01 | Select an option
| 5.abc) Work with your IT department and EMR vendor to integrate necessary requirements/assessments into EMR | 2016-12-31 | Select an option
| 5.abc) Begin using required standard assessments for project activities | 3/31/2017 a 3/31/2017 b 3/31/2017 c | Select an option

## 4.d.i-Reduce Premature Births
|  | Home | In every section, the last due date of that section aligns with DSRIP related milestones. It is suggested that your organization works to complete these tasks 60-90 days in advance of the milestone where possible
Project Specific HIT Requirement Implementation Plan: 4.d.i-Reduce Premature Births
| Workflow Automation | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.) Work with your DSRIP coordinator and applicable operational and clinical staff to determine the desired workflow, process, and platform for the management and referrals of high risk pregnancies. | 2016-09-30 | Select an option
| 2.) Work with internal, operational, IT and CNYCC project staff to evaluate the adoption of referral management platform for high risk pregnancies | 2016-12-01 | Select an option
| 3.) Work with CNYCC Staff to address concerns and map out and plan for adoption of referral management solution for high risk pregnancies | 2017-03-31 | Select an option
| 4.) Work with your IT and EMR vendor to integrate necessary requirements/workflow into EMR | 2017-06-30 | Select an option
| 5.) Go live with referral management for at risk pregnancies | 2018-03-31 | Select an option
| Population Health Management | CNYCC Due Date | Completed | Risk Issues and Barriers | Comments and Concerns
| 1.) Work with your DSRIP coordinator and applicable operational and clinical staff to determine the cost and benefits of gaining access to the available regional perinatal databased currently available. | 2016-09-30 | Select an option
| 2.) Work with CNYCC, internal operational staff and project leaders to developed plan to take advantage of perinatal databases | 2017-03-31 | Select an option
| 3.)Execute plan and begin use of database. | 2018-03-31 | Select an option
|  |  |  | Risk Issues and Barriers | Comments and Concerns