## Sheet1
Task Name | Duration | Start | Finish | Predecessors | Resource names
Urgent Care Dashboard - Project Implementation Plan Template v01 | 85 days | 2011-03-02 08:00 | 2011-06-28 17:00
Project Dependencies | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Project / Control Board (or equivalent) established | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Project Team Established | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Metrics design group established | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Business case and financials in place for procurement (if applicable) | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Project Initiation and Scoping | 29 days | 2011-03-02 08:00 | 2011-04-11 17:00
Project Kick Off/MOU meeting | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
PID development and agreement | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Scoping workshop - Metrics, Information Feeds, Additional SW/HW, Benefits, Business Change | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Milestone: Metrics requirements Agreed | 1 day | 2011-03-03 08:00 | 2011-03-03 17:00
Metrics design | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Information Governance | 1 day | 2011-03-21 08:00 | 2011-03-21 17:00
Solution scoping (with supplier if required) | 1 day | 2011-03-23 08:00 | 2011-03-23 17:00
Work order agreed (with supplier if required) | 1 day | 2011-04-11 08:00 | 2011-04-11 17:00
Data Feed Specifications agreed/provided | 1 day | 2011-03-23 08:00 | 2011-03-23 17:00
Define Infrastructure/Environment | 1 day | 2011-03-23 08:00 | 2011-03-23 17:00
MOU signed off by project sponsor | 1 day | 2011-03-23 08:00 | 2011-03-23 17:00
Milestone: Solution design | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Milestone: Production and Sign off PID | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Benefits & Business Change | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Benefits Realisation Strategy/Plan agreed | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Business Change workshop (to develop strategy/approach/model) | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Business Change Planning | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Business Change Delivery - early engagement (practice meetings) comms (newsletters/case studies) | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Benefits tracking & evaluation | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Testing & Training | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Testing & Training Plans developed & agreed | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Communications | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Communications Plan developed & agreed | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Development | 26 days | 2011-03-02 08:00 | 2011-04-06 17:00
Infrastructure and Environment | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Hardware and Software Procurement Readiness (incl procurement if appropriate) | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Local Device and Network Readiness | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Security model (incl use of SmartCard if applicable) | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Agree file transfer approach with providers e.g. DTS or FTP/firewalls | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
N3 Connectivity complete (if applicable), remote access tested | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Delivery of Application Software | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Configuration of Active Directory | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Local / Provider (e.g. Acute) Data | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Delivery for Test Data | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Development of Data Feeds | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Solution Design and Development | 26 days | 2011-03-02 08:00 | 2011-04-06 17:00
Extract Transform and Load Definitions | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Dashboard / metrics solution design - Reports Definition | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Dashboard / metrics solution design - Portal technology / definition (e.g. SharePoint or as part of QlikView type product) | 1 day | 2011-04-06 08:00 | 2011-04-06 17:00
Development | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Implementation | 85 days | 2011-03-02 08:00 | 2011-06-28 17:00
System Testing | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Development area testing | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Integration Testing (including RFO) | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Deploying / Configuring to production / live environment | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Testing | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
PCT / Consortia (Install) | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
GP Practice testing at first GP sites | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
User Assurance Testing | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
End user assurance testing (including development time) | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
User Training | 85 days | 2011-03-02 08:00 | 2011-06-28 17:00
Technical User Training (if applicable) | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Administration User Training (if applicable) | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
End User Training (tailored to need) | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Commence live usage | 1 day | 2011-06-28 08:00 | 2011-06-28 17:00
Go Live at first GP Practices | 85 days | 2011-03-02 08:00 | 2011-06-28 17:00
Commence live usage | 1 day | 2011-06-28 08:00 | 2011-06-28 17:00
Handover Support (if applicable) | 1 day | 2011-06-28 08:00 | 2011-06-28 17:00
Milestone: Go Live at first GP Practices | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Transition | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Post Go Live | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Lessons Learnt | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Benefits Report | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Development & Spread | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Wider roll-out across area to remainder of practices | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Set up at local practices | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Training for practice staff | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Promotional work incl local events and cascade to other local communities e.g. other GP Consortia | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Ongoing review and improvement | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00
Special interest group (SIG) meetings / feedback from users | 1 day | 2011-03-02 08:00 | 2011-03-02 17:00