## Introduction
DIGITAL LEARNING PROJECT PLAN
Purpose: The project plan is meant to give a comprehensive view of the activities planned as part of the program and their associated timeline. Its goal is to ensure that the implementation is tracked in order to keep the project on-track. NOTE: Timelines in the "Project Plan - Pilot" and "Project Plan - Full Program" tabs are meant for illustrative purposes only. They must be modified by the organization to reflect the projected timing of a given digital learning program.
Copyright Accenture 2015

## Project Plan - Pilot
Digital Learning Project Plan
[6 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Make The Case For Digital Learning
Position digital learning within the org. strategy | 1 | 1 | 1 | 1 | 0%
Quantify the business case for a digital learning pilot & the full program to follow suit | 1 | 2 | 1 | 2 | 0%
Present the business case of the pilot, positioning pilot success as a gateway to the full program implementation | 2 | 1 | 2 | 1 | 0%
Gain leadership and organizational alignment & secure funding | 2 | 1 | 2 | 1 | 0%
Design Effective Educational Content
Define beneficiary group for the pilot | 2 | 1 | 2 | 1 | 0%
Select program structure for the pilot best suited to the skill types at the core of the project (1st generation model vs. 2nd generation model) | 3 | 1 | 3 | 1 | 0%
Determine optimal blended learning model option for the pilot (online vs. offline delivery %) | 3 | 1 | 3 | 1 | 0%
Determine optimal delivery timing of the pilot (synchronous/asynchronous) | 3 | 1 | 3 | 1 | 0%
Determine connectivity and device requirements for the pilot and ensure that pilot beneficiaries meet the requirements | 4 | 1 | 4 | 1 | 0%
Define appropriate level of the pilot's digital learning program customization based on objective and costs | 4 | 1 | 4 | 1 | 0%
Determine optimal methods of imparting content during the pilot (e.g. adaptive, gamification, social) | 4 | 2 | 4 | 2 | 0%
Define pedagogical approach needed for the digital learning pilot & the preparatory training/support needed to achieve this | 5 | 1 | 5 | 1 | 0%
Develop learning validation process for the pilot | 5 | 2 | 5 | 2 | 0%
Align digital learning pilot with career services offering | 6 | 1 | 6 | 1 | 0%
Built a Scalable Operation
Determine which cross-sector partnership can be leveraged for the pilot program | 5 | 2 | 5 | 2 | 0%
Design the operating model to support the digital learning pilot | 6 | 2 | 6 | 2 | 0%
Select the supporting technology for the pilot | 7 | 2 | 7 | 2 | 0%
Execute the Program
Design the pilot (objectives, metrics, roll-out plan) | 5 | 5 | 5 | 5 | 0%
Launch/run the pilot | 10 | 6 | 10 | 6 | 0%
Capture Value From Digital Learning
Manage the pilot to ensure it is on-time and on-budget | 10 | 6 | 10 | 6 | 0%
Manage the pilot business case to ensure value is being realized as planned | 10 | 6 | 10 | 6 | 0%
Perform continuous change management to ensure continued buy-in for the pilot | 10 | 6 | 10 | 6 | 0%
Continuously Improve the Digital Learning Program
Gather feedback from the pilot | 11 | 6 | 11 | 6 | 0%
Integrate the feedback from the pilot to continuously adjust and improve it | 11 | 6 | 11 | 6 | 0%

## Project Plan - Full Program
Digital Learning Project Plan
[6 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Make The Case For Digital Learning
Position digital learning within the org. strategy | 1 | 2 | 1 | 2 | 0%
Quantify the business case for digital learning | 1 | 3 | 1 | 3 | 0%
Present the business case for digital learning | 3 | 1 | 3 | 1 | 0%
Gain leadership and organizational alignment | 2 | 2 | 2 | 2 | 0%
Design Effective Educational Content
Define approach for determining which beneficiaries are immediately suited for digital learning | 4 | 2 | 4 | 2 | 0%
Define approach for those not immediately suited for digital learning to get them ready | 4 | 2 | 4 | 2 | 0%
Select program structure best suited to the skill types at the core of the digital learning program (1st generation vs. 2nd generation) | 4 | 2 | 4 | 2 | 0%
Determine optimal blended learning model option for the program (online vs. offline delivery %) | 5 | 2 | 5 | 2 | 0%
Determine optimal delivery timing of the program (synchronous/asynchronous) | 5 | 2 | 5 | 2 | 0%
Determine connectivity and device requirements for the program | 5 | 2 | 5 | 2 | 0%
Define appropriate level of program customization based on objective and costs | 6 | 3 | 6 | 3 | 0%
Determine optimal methods of imparting content (e.g. adaptive, gamification, social) | 6 | 3 | 6 | 3 | 0%
Define pedagogical approach needed for the digital learning program & the preparatory training/support needed to achieve this | 6 | 3 | 6 | 3 | 0%
Develop learning validation process for the program | 7 | 5 | 7 | 5 | 0%
Align digital learning program with career services offering | 7 | 2 | 7 | 2 | 0%
Design process for keeping track and continuously engaging alumni | 7 | 3 | 7 | 3 | 0%
Built a Scalable Operation
Develop cross-sector partnership plan for the program | 9 | 5 | 9 | 5 | 0%
Design the operating model to support the digital learning strategy | 9 | 5 | 9 | 5 | 0%
Select the supporting technology for the program | 9 | 3 | 9 | 3 | 0%
Execute the Program
Design the pilot (objectives, metrics, roll-out plan) | 12 | 4 | 12 | 4 | 0%
Execute the pilot | 15 | 6 | 15 | 6 | 0%
Evaluate the pilot | 20 | 2 | 20 | 2 | 0%
Integrate the pilot findings into the full-scale roll-out plan | 21 | 1 | 21 | 1 | 0%
Launch the full-scale roll-out | 22 | 39 | 22 | 39 | 0%
Capture Value From Digital Learning
Manage the program to ensure it is on-time and on-budget | 12 | 56 | 12 | 56 | 0%
Manage the business case to ensure value is being realized as planned | 12 | 56 | 12 | 56 | 0%
Perform continuous change management to ensure continued buy-in for the program | 12 | 56 | 12 | 56 | 0%
Continuously Improve the Digital Learning Program
Gather feedback from the program | 12 | 56 | 12 | 56 | 0%
Integrate the feedback from the program to continuously adjust and improve it | 12 | 56 | 12 | 56 | 0%