## Cover
Section 4.2 Implement
Project Plan
Use this tool to review the implementation plan provided by the vendor, and prepare to develop a project plan for your organization that reflects milestones from the vendor’s plan and all other tasks you need to perform.
Time Needed: 20 hours, 2 hours per week thereafter for the duration of the project
Suggested Prior Tools: Section 2.2 Project Management
How to Use
1. Review the implementation plan supplied by the vendor, ideally with the vendor’s implementation specialist. Consider the tasks, resources, and timing, and coordinate changes with the vendor.
2. Prepare to develop a project plan for your organization that reflects milestones from the vendor’s plan and all other tasks you need to perform. In some cases, you may have to manage several vendors at one time (e.g., the HIT application vendor, a systems integrator who is writing your interfaces, a chart conversion company, a data conversion company, a construction company, a telecommunications company, an implementation and training consultant). Recording all project milestones from different vendors can help you track their progress as well as the dependencies among them (e.g., you can’t install hardware without some construction being completed).
3. Record the tasks and resources to be used (e.g., names of individuals, committee, team, vendor) and period of time planned for the task.
4. To use the Excel spreadsheet as a Gantt chart to track completion of each task, separate each task with a blank row and record the actual time; or purchase Gantt chart utilities to create a Gantt chart from an Excel file.

## Plan
EHR Implementation Plan
Ref # |  | Resources | Complete | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17 | Wk 18 | Wk 19 | Wk 20 | Wk 21 | Wk 22 | Wk 23 | Wk 24 | Wk 25 | Wk 26
| Meet witheach vendor's implementation specialist | Jim
| Review implementation plan with implementation specialist and harmonize into one master plan for your organization |  | Yes
| Review contract with implementation specialist to ensure full understanding of project scope |  | Yes
| Discuss and plan chart conversion strategy if applicable to application | HIM Team
| Gain internal approval for chart conversion strategy | Jim | Yes
| Discuss and plan roll out strategy | Implementation Team
| Gain approval for roll out strategy | Jim | No
Develop organizational support plan
Establish project structure
Form project implementation steering committee
Identify and populate domain teams
Identify project manager
Identify clinical lead
Staff IT for ongoing support
Identify third party support, if necessary
Identify and prepare super users
Define organization decision making structure
Learn vendor reporting structure
Review communication plan
Review/update communication plan as applicable (incorporate into this project plan)
Insert messages and messengers for communication plan
Develop documentation requirements and standards (e.g., set up directories, file naming conventions, groupware)
Plan for meeting processes, agendas, minutes, and follow up
Initiate issues management process
Start an issues log
Plan for regular review of project progress and milestone completion
Establish escalation process
Initiate change control process
Plan to use a formal change request and approval process
Manage changes to system (e.g., customization, priorities, budget)
Plan to archive system documentation
Review and sign HIO participation agreement
Application design
Affirm goals and metrics
Plan for post-live measurement
Identify workflow and process improvements
Implement chart conversion
Identify specific timing and staff for scanning/abstracting
Identify documents to be scanned
Acquire scanner
Train scanning staff or contract with scanning company
Scan documents according to plan
Quality check scanning results
Identify data to abstract for pre-loading
Train abstract staff, if applicable
Abstract data according to plan
Quality check abstracting results
Mark charts "closed" following scanning/abstracting
Identify work flow changes from process mapping
Review sequencing of tasks and impact on staff
Gain internal approval for changes
Review sequencing of tasks and plan for changes
Admission/registration area (list specifics...)
At the point of care (list specifics...)
In ancillary departments as applicable (list specifics…)
Billing and other back office areas (list specifics...)
In obtaining consent for health information exchange
In transitions of care (list specifics…)
In care coordination (list specifics…)
In other health information exchange (list specifics…)
Identify process changes from process mapping
Plan for using EHR at point of care
Evaluate and select user devices
Role play changes
Standardize basic HIT functionality and vocabulary
Patient directives (e.g., consents, authorizations, requests for restrictions, HIPAA notice)
Problem list vocabulary (list specifics...)
Care planning (list specifics...)
Results vocabulary (list specifics...)
Data sets collection (list specifics...)
Other task names and views (list specifics…)
User roles
User favorites (list specifics…)
Address privacy and security
Authentication
Access controls
Authorizations/restrictions
Audit controls
Destruction
Data backup and restore
Disaster planning and business continuity planning
Design functions
Base application screen layout
Charges
Assessments
Care plans
Visit notes
Medication management
Interdisciplinary notes templates and decision support
OASIS data entry not sourced elsewhere
Orders (CMS-485/others) templates and decision support
Results templates and decision support
Referral communications
Patient education and instructions
Scanned documents and indexing
Letter templates
Report templates
Data warehousing (list specifics...)
Application build
Physical site preparation
Remodel space/construction for new equipment as applicable (list specifics…)
Acquire necessary new furnishings (e.g., shelving, equipment racks, cables, UPS, generator, fire management services)
Install hardware
Plan any necessary data conversion
Master file and table/data dictionary build for:
Base application
Charges
Assessments
Notes
Orders
Medication management
Results
Scanned documents
Letters
Reports
Data warehousing
Load master files and tables into systems
Interface build for:
Demographics
Registration/referral management
Admission-Discharge-Transfer (ADT)
Charges
Registries
Electronic document management system
Determine methodologies: scan, electronic feed, email, efax
Results from external lab
Results from other external sources
Inbound documents/data (about clients)
Inbound documents/data (medications)
Inbound documents/data (hospital)
Inbound documents/data (physicians)
Inbound documents (transcription)
Inbound documents/data (payers)
Outbound documents/data (clients)
Outbound documents/data (medications)
Outbound documents/data (hospital)
Outbound documents/data (payers)
Outbound documents/data (physicians)
Speech dication
Install health information exchange technology
Review person identification data set
Review that providers all have required provider identifiers
Review data for adherence to standard terminology
Install portal
Install Direct
Install CONNECT
Testing
Establish test environment
Develop testing plan
Types of tests and timeline
Write test scenarios
Convert test scenarios to use cases
Define test sign-off requirements
Conduct tests
Conduct unit testing
Conduct system testing
Conduct integration testing, if interfaces
HIE testing
Document:
Data dictionary changes
Changes in policies and procedures based on new work flows and process improvement
Rules engine changes
Training
Develop training plan
Identify trainers
Develop/receive training materials
Identify locations of training
Plan training schedule, time off, compensation (e.g., overtime, revenue)
Plan for evaluation
Plan for certification, as applicable
Conduct orientation and education as applicable
Project team training
Super users training
IT support staff training for:
Transition
Upgrades management
End user training
Phase 1
Phase 2
Phase 3
Go-Live
Develop rehearsal checklist/playbook
Rehearse go live
Conduct live system delivery
Move files and tables from test environment to production environment
Copy interfaces from test environment to production environment
Swarm users with support during initial use
Evaluate go live with users
Evaluate go live with vendor
Monitor adoption milestones
Adoption rate for various users and uses
Provide final payment per contract
Conduct satisfaction surveys
Nursing staff
Other staff
Physicians
Clients
Conduct care management processes
Documentation improvement
Monitor clinical quality improvements as specified in goals (e.g., compliance with clinical guidelines, performance indicators, benchmarking)
Conduct benefits realization studies per goals
Productivity
Paper chart management
Revenue cycle management (e.g., charge capture, A/R management)
Other (specify…)
Reconcile budget vs. actual
Correct course as applicable
Celebrate success
Provide ongoing support for assistance
Maintain issues log for ongoing system management