Public Involvement Advisory Council--Comp Plan Workgroup

2013 Work Plan Timeline

| Outcome Activities to Meet Outcome | Dec 2012 | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Community Survey Report |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1. analyze input | X |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2. write report |  | X |  |  |  |  |  |  |  |  |  |  |  |
| 2. Goal/Policy Language |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1. continue refinement of language | X | X | X | X |  |  |  |  |  |  |  |  |  |
| 2.2. review input from Feb/Mar workshops |  |  |  |  | X |  |  |  |  |  |  |  |  |
| 2.3. continue to refine language |  |  |  |  |  | X | X | X |  |  |  |  |  |
| 2.4. submit final draft to BPS (in August) |  |  |  |  |  |  |  |  | X |  |  |  |  |
| 3. Public Involvement Manual |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1. prepare bibliography | X |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2. develop preliminary document structure |  | X | X | X |  |  |  |  |  |  |  |  |  |
| 3.3. review input from Feb/Mar workshops |  |  |  |  | X |  |  |  |  |  |  |  |  |
| 3.4. hold focus groups (PSC and Planning Staff) |  |  |  |  | X | X |  |  |  |  |  |  |  |
| 3.5. continue drafting |  |  |  |  |  |  | X | X | X | X | X | X | X |
| --------[some sort of community workshop to review?] |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.6. submit final to BPS (by mid 2014) |  |  |  |  |  |  |  |  |  |  |  |  | → |
| 4. Legislative Intent Statements |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1. draft language |  |  |  |  |  |  |  |  |  |  |  | X | X |
| 4.2. submit final draft to BPS (by mid 2014) |  |  |  |  |  |  |  |  |  |  |  |  | → |
| 5. CI PEG “white paper” |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1. develop document structure |  |  |  |  |  |  | X | X |  |  |  |  |  |
| 5.2. draft language |  |  |  |  |  |  |  |  | X | X | X | X | X |
| 5.3. finish final draft (by mid 2014) |  |  |  |  |  |  |  |  |  |  |  |  | → |