## Overview
Coordinate Modeled Asset - Project Summary and Checklist
High level instructions for registering a modeled generator asset
There are 7 categories of requirements that must be met via this process before a modeled asset may participate in the ISO-NE markets. It may take a year or more for all requirements to be completed, with the first deadlines occurring 210 days prior to the projected Initial Sync date. The project coordination timeline is separated into 7 phases which demarcate critical steps of the process.
Categories | Description | Reference Document(s)
Lead Market Participant Registration | All modeled assets must be brought into the ISO-NE market by a registered, fully settleable market participant, known as the Lead Market Participant. You may (1) register as a new market participant, or (2) designate an existing market participant. Note that becoming a new market participant may take up to 3 months to accomplish. Once designated, a representative from this entity is responsible for the submission of registration forms and submittal of data through certificate based applications. | New Customer Registration Instructions User Guides for CAMS
Asset Registration | The project will consist of one or more units, requiring the registration of one or more market assets by the Lead Market Participant. If there are multiple units these may be aggregated into a single asset, or registered separately. All technical requirements must be met at the asset level. Asset registration must be completed prior to the beginning of any associated FCM resource obligation. Additionally, a station service load asset or metering domain registration may be needed for the modeled asset(s). | OP-12 OP-14 OP-23 Appendix E OP-23 Appendix F M-RPA Registration and Performance Auditing
System Planning & Operational Studies | All modeled assets must be studied to ensure a reliable system. The I.3.9 process includes the system impact study (SIS) and submittal of a proposed plan application (PPA) through to the execution of the facility's Interconnection Agreement. | Planning Procedures Schedule 22 - Large Gen Interconnection Schedule 23 - Small Gen Interconnection
Power System Modeling | All modeled assets must be in the ISO-NE power system model prior to operation. NX-9 technical data may be required. There are 3 power system model releases a year, therefore a new modeled asset should be in a release prior to the target operation date. | OP-14 OP-16
Real-Time Telemetry | All modeled assets (except solar) must provide real-time telemetry via a Remote Terminal Unit (RTU) directly connected to ISO-NE, both for reliability of the system and markets data. Dispatch signals are sent via this communications route. Modeled assets providing regulation may have additional requirements. Modeled solar assets are not required to be dispatchable, but must still provide reliability data through telemetry to the Local Control Center (LCC). | OP-14 OP-14, Appendix F (Wind Only) OP-18 CROP.45001
Voice Communications | All modeled assets must have a registered Designated Entity (DE) with a 24 x 7 dedicated phone line. Designated Entities managing over 50 MW of dispatchable generation or managing at least one modeled asset providing regulation are additionally required to have an Auto Ring Down (ARD) in place, which may require the installation of a circuit. | OP-14
RNS/Local Service | The generating facility and the transmission owner must determine the need for Regional Network Service (RNS) or Local Service as it relates to generator output and associated station service load. | OATT RNL Configuration Change Request Form Transmission Service Agreement Transmission Service Types
All reference documents may also be located at: https://www.iso-ne.com/participate
ISO-NE PUBLIC

## Project Summary
| Project Summary |  |  |  | Generator Technical Data
| Project Type: |  |  | * |  | Nameplate (MVA):
| Queue Number: |  |  |  |  | Winter Interconnection Limit:
| Project Name: |  |  | * |  | Summer Interconnection Limit:
| Facility Address: |  |  |  |  | Generator Type:
| Market Asset Name(s): |  |  |  |  | Primary Fuel Type: |  | *
Asset ID(s):
| Projected Dates |  |  |  | Project Description
| In-Service Date: (ready to receive backfeed power) |  |  | *
| Initial Sync Date: (begin trial/test operation) |  |  | *
| Commercial Operation Date (COD): |  |  | *
*Actual dates can be extended, but are subject to the Tariff.
Basic Project Information
|  | Lead Market Participant: |  |  |  |  | New / Existing? | *
|  | Designated Entity: |  |  |  |  | New / Existing? | *
Transmission Owner Market Participant:
Interconnection Point:
Local Control Center:
Checklist Indicators
|  | Participate in Forward Capacity Market?: |  |  |  | FERC Jurisdictional?:
|  | Resource ID: |  |  |  | NX-9 Required?: | *
|  | Obligation Date: |  |  |  | Intermittent?: | *
|  | Resource Lead Participant: |  |  |  | Auto Ring Down (ARD): | *
|  | Participate in VAR Market?: |  |  |  | Ops real-time studies required?:
|  | Participate in Reserve Market?: |  |  |  | Regulation Capable:
|  | Any Load (other than Station Service): |  |  |  | EDC (Dispatchable):
|  | DR behind same retail delivery point?: |  |  |  | DNE Dispatchable:
|  | Composite? (multiple units per asset): |  |  |  | Fast Start Capable:
|  | How many market assets?: |  |  |  | Auto Start Capable:
Project Contacts
| Organization - | Contact |  | Name |  | Email * | Primary Phone
| Project - | Manager
| Lead Participant - | Asset Registration
| Project - | Interconnection Agreement
| Project - | Planning Technical
| Project - | Power System Modeling
| Project - | Generator Technical
| Project - | Communications Technical
| Local Control Center - | Lead
| Local Control Center - | Technical
| Transmission Owner - | Lead
| Transmission Owner - | Technical
| ISO-NE - | Asset Registration & Auditing |  | Chad Nelson †
| ISO-NE - | Modeled Asset Coordinator
| ISO-NE - | Assistant Coordinator | Gen & Load Administration
| ISO-NE - | Customer Support
| ISO-NE - | Membership Coordinator |  | Heather Latka |  | hlatka@iso-ne.com
| ISO-NE - | Resource Adequacy |  | Helve Saarela |  | hsaarela@iso-ne.com
| ISO-NE - | Resource Analysis & Qualification |  | Simmi Chaudhury |  | schaudhury@iso-ne.com
| ISO-NE - | Transmission Strategy & Services | Transmission Strategy & Services | Kevin Mankouski †
| ISO-NE - | Transmission Strategy & Services |  | Cheryl Ruell †
| ISO-NE - | Transmission Planning |  | Peter Bernard †
| ISO-NE - | Transmission Planning |  | Al McBride †
| ISO-NE - | Power System Modeling |  | Osman Bileya †
| ISO-NE - | NX-9 Administration |  | Cathy Simonelli †
| ISO-NE - | Data Communications |  | Brock Nubile |  | bnubile@iso-ne.com
| ISO-NE - | IT Communication Projects |  | IT Comm Dept |  | itcommdept@iso-ne.com
| ISO-NE - | Operations Support Services |  | Jim Helton †
| ISO-NE - | Operations Support Services |  | Dean LaForest †
| ISO-NE - | Transmission Operations Technical Studies |  | Kory Haag |  | khaag@iso-ne.com
| ISO-NE - | Operations Support Services |  | Short-Term Outage Coordination |  | GenerationOutageCoor@iso-ne.com
| ISO-NE - | Ops Performance, Training, and Integration |  | Bill Henson †
| ISO-NE - | Operations Tariff & Agreement Mgr | Reliability & OPS Services | Bruce Kay |  | bkay@iso-ne.com
| ISO-NE - | Market Compliance |  | Gregg Bradley |  | gbradley@iso-ne.com
| ISO-NE - | Interconnection Distribution List |  | Contains names indicated by: † |  | Geninterconn@iso-ne.com
| ISO-NE - | For Meeting Invites Only
| ISO-NE - | For Meeting Invites Only
* - Indicates fields that impact other tabs or functions of this workbook.
ISO-NE CONFIDENTIAL - COMPLETED FORM
1
Note on C36: The external individual single point of contact for all aspects of the project who may be in CAMS under the Lead Market Participant or designated by the Lead Market Participant at the appropriate time .
Note on C37: The Lead Market Participant contact in charge of submitting asset registration forms. Shall have that contact type in CAMS.
Note on C38: The external point of contact for the Interconnection Agreement.
Note on C39: The external point of contact for "as purchased/as built/as tested" submittals and follow-up.
Note on C40: The external point of contact for getting the facility in the ISO-NE power system model.
Note on C41: The external point of contact for NX-12D and NX-9 technical date submittals
Note on C42: The external point of contact from the project for telemetry requirements.
Note on C43: The Local Control Center contact who identifies any LCC requirements needing to be met by the project.
Note on C44: The Local Control Center contact overseeing telemetry requirements needing to be met by the project for the LCC.
Note on C45: The Transmission Owner contact who identifies any TO requirements needing to be met by the project including installation of the revenue quality meter.
Note on C46: The Transmission Owner contact overseeing technical equipment being installed due to the project.

## Itemized Checklist
Itemized Checklist to be used by ISO-NE and the New Gen Project Contacts to help meet requirement deadlines | [8 empty] | Checklist Color Key | Not Applicable
Action Item
Completed
All Email Correspondence related to below items between the Internal ISO Contact and the New Gen Project Contact shall cc: NewGenCoord@iso-ne.com. | [9 empty] | Overdue - Immediate Action Needed
|  |  |  | In-Service Date | Initial Sync Date | COD
|  |  |  | 0 | 0 | 0
Phase | Category | Itemized ISO-NE Requirements | Contingent on: | Driver: | Date: | # days due prior to: | Target/Due Date: | Responsible Party | Date Completed/ Approved: | Comments
1 | Lead Market Participant Registration | 01.a.) Submit market participant application |  | Initial Sync Date | 0 | 270 | -270 | Project - Manager Contact
1 | System Planning & Operational Studies | 01.b) System Impact Study (SIS) complete and As-Studied models uploaded to DDMS |  | Initial Sync Date | 0 | 210 | -210 | Project - Manager Contact
1 | Power System Modeling | 01.c.) One-Line Diagram - Final |  | In-Service Date | 0 | 180 | -180 | Project - Power System Modeling Contact
1 | Real-Time Telemetry | 01.d.) Provide Participant with Confidential OP-18, Appendix F and additional forms |  | In-Service Date | 0 | 180 | -180 | ISO-NE - New Gen Coordinator
1 | Lead Market Participant Registration | 01.e.) Market Participant Registration Completed | 01.a.) | Initial Sync Date | 0 | 180 | -180 | Project - Manager Contact
1 | Lead Market Participant Registration | 01.f.) Designation of Lead Market Participant |  | Initial Sync Date | 0 | 180 | -180 | Project - Manager Contact
1 | System Planning & Operational Studies | 01.g.) Return the Voltage Control Questionnaire |  | Initial Sync Date | 0 | 180 | -180 | Project - Manager Contact
1 | System Planning & Operational Studies | 01.h.) "As-Purchased" Generator Data submitted via DDMS *Subject to material modification review if different than the SIS | 01.f.) | Initial Sync Date | 0 | 180 | -180 | Project - Planning Technical Contact
1 | System Planning & Operational Studies | 01.i.) Determination on scope and schedule - Operations real-time studies required |  | Initial Sync Date | 0 | 180 | -180 | Project - Planning Technical Contact
1 | Real-Time Telemetry | 01.j.) Solar Only: Static Solar Data Form |  | In-Service Date | 0 | 150 | -150 | Project - Generator Technical Contact
1 | Real-Time Telemetry | 01.k.) Wind Only: Static Wind Data Form |  | In-Service Date | 0 | 150 | -150 | Project - Generator Technical Contact
1 | RNS/Local Service | 01.l.) Discuss Regional Network Service ("RNS") and Local Transmission Service as they relate to the generator and its station service load. Prompt Project - Manager Contact to consult with the affected Transmission Owner and determine if a RNS or LS Application is required to be submitted to ISO-NE. |  | COD | 0 | 180 | -180 | ISO-NE - Operations Tariff & Agreement Mgr Contact
1 | Lead Market Participant Registration | 01.m.) Application access provided to the Lead Market Participant | 01.f.) | Initial Sync Date | 0 | 150 | -150 | ISO-NE - New Gen Coordinator
1 | Voice Communications | 01.n.) Auto Ring Down (ARD) Determination |  | Initial Sync Date | 0 | 150 | -150 | ISO-NE - New Gen Coordinator
1 | RNS/Local Service | 01.o.) Consult and determine if an RNS application is required to be submitted to ISO-NE in support of its station service load. If an RNS Application is required, steps 7.f.) needs to be completed. | 01.l.) | In-Service Date | 0 | 120 | -120 | Project - Manager Contact Transmission Owner - Lead Contact
1 | RNS/Local Service | 01.p.) Consult and determine if a Local Transmission Service (LNS or Point to Point) Application is required to be submitted to ISO-NE in support of its (i) station service load and/or (ii) generator output If a Local Service Application is required, steps 8.c.ii. - iv. need to be completed. | 01.l.) | In-Service Date | 0 | 120 | -120 | Project - Manager Contact Transmission Owner - Lead Contact
2 | Power System Modeling | 02.a.) Facility Modeled | 01.c.) | In-Service Date | 0 | 120 | -120 | Project - Power System Modeling Contact
2 | Power System Modeling | 02.b.) Power System Model and Data Communications Model align and meet the Facility Capabilities | 02.a.) | In-Service Date | 0 | 120 | -120 | Project - Power System Modeling Contact
2 | Power System Modeling | 02.c.) NX-9 Preliminary Data *data can be based on preliminary, planned or MP specification data | 01.f.) | In-Service Date | See NX-9 Details | See NX-9 Details | See NX-9 Details Tab | Project - Power System Modeling Contact
2 | Real-Time Telemetry | 02.d.) Received ISO-NE ED - Circuit and Router Order Form | 01.d.) | Initial Sync Date | 0 | 150 | -150 | Project - Manager Contact
2 | Real-Time Telemetry | 02.e.) Develop and send the SCADA points list | 02.b.) | Initial Sync Date | 0 | 140 | -140 | ISO-NE - Data Communications Contact
2 | Real-Time Telemetry | 02.f.) Confirmation on circuits/router quote sent to the participant | 02.d.) | Initial Sync Date | 0 | 130 | -130 | ISO-NE - IT Comm. Projects Contact
2 | Real-Time Telemetry | 02.g.) Approval received on participant bill-back for data circuits | 02.f.) | Initial Sync Date | 0 | 125 | -125 | ISO-NE - New Gen Coordinator
2 | Real-Time Telemetry | 02.h.) RTU Data Circuits and router order placed | 02.g.) | Initial Sync Date | 0 | 120 | -120 | ISO-NE - IT Comm. Projects Contact
2 | Asset Registration | 02.i.) Revenue Quality Metering Requirements understood |  | Initial Sync Date | 0 | 120 | -120 | Project - Manager Contact
2 | Real-Time Telemetry | 02.j.) Participant and LCC confirmation on required Telemetry | 02.e.) | Initial Sync Date | 0 | 120 | -120 | Project - Communications Technical Contact
2 | Voice Communications | 02.k.) ARD approval hand off | 01.n.) | Initial Sync Date | 0 | 120 | -120 | ISO-NE - New Gen Coordinator
2 | Voice Communications | 02.l.) ARD Voice Circuits order placed | 02.k.) | Initial Sync Date | 0 | 120 | -120 | ISO-NE - IT Comm. Projects Contact
2 | Asset Registration | 02.m.) Preliminary Technical Data Form (NX-12) | 01.f.) | Initial Sync Date | 0 | 120 | -120 | ISO-NE - Assistant Coordinator Contact
2 | Asset Registration | 02.n.) Preliminary DERF | 01.f.) | Initial Sync Date | 0 | 120 | -120 | ISO-NE - Assistant Coordinator Contact
2 | Asset Registration | 02.o.) Voltage and Reactive Control Data (NX-12D) | 01.f.) | Initial Sync Date | 0 | 120 | -120 | Project - Generator Technical Contact
2 | System Planning & Operational Studies | 02.p.) Proposed Plan Application (PPA) Submittal | 01.b.) | In-Service Date | 0 | 90 | -90 | ISO-NE - System Planning Technical Contact
2 | RNS/Local Service | 02.q.) Confirm that an RNS Application submitted to ISO-NE | 01.o.) | In-Service Date | 0 | 90 | -90 | Project - Manager Contact
2 | RNS/Local Service | 02.r.) Local Service Application submitted to ISO-NE | 01.p.) | In-Service Date | 0 | 90 | -90 | Project - Manager Contact
2 | Real-Time Telemetry | 02.s.) RTU Vendor selected and RTU Information Form received | 01.d.) | Initial Sync Date | 0 | 110 | -110 | Project - Manager Contact
3 | Real-Time Telemetry | 03.a.) RTU configuration worksheet provided | 02.j.) | Initial Sync Date | 0 | 100 | -100 | ISO-NE - Data Communications Contact
3 | Real-Time Telemetry | 03.b.) Confirmation on RTU configuration | 03.a.) | Initial Sync Date | 0 | 90 | -90 | Project - Manager Contact
3 | Voice Communications | 03.c.) Dedicated 24/7 phone order process begun | 02.n.) | Initial Sync Date | 0 | 90 | -90 | Project - Manager Contact
3 | Real-Time Telemetry | 03.d.) RTU Circuits - Firm Order Commitment (FOC) date received from carrier | 02.h.) | Initial Sync Date | 0 | 80 | -80 | ISO-NE - IT Comm. Projects Contact
3 | Voice Communications | 03.e.) ARD Circuits - Firm Order Commitment (FOC) date received from carrier | 02.l.) | Initial Sync Date | 0 | 80 | -80 | ISO-NE - IT COMM Contact
3 | Power System Modeling | 03.f.) NX-9 Data *data must either be based on as built or derived from specification | 02.c.) | In-Service Date | See NX-9 Details | See NX-9 Details | See NX-9 Details Tab | Project - Power System Modeling Contact
3 | Real-Time Telemetry | 03.g.) Wind Only: Preparing WPF Web Services - WPLP | 01.k.) | Initial Sync Date | 0 | 45 | -45 | ISO-NE - New Gen Coordinator
3 | Real-Time Telemetry | 03.h.) RTU - Data circuits installed | 03.d.) | Initial Sync Date | 0 | 40 | -40 | ISO-NE - IT Comm. Projects Contact
3 | System Planning & Operational Studies | 03.i.) Proposed Plan (PPA) Non-Denial (Letter from VP, System Planning following RC) | 02.p.) | In-Service Date | 0 | 1 | -1 | ISO-NE - System Planning Technical Contact
3 | System Planning & Operational Studies | 03.j.) "As-Purchased" Generator Data confirmed to be in good order | 01.h.) | Initial Sync Date | 0 | 30 | -30 | Project - Planning Technical Contact
3 | Real-Time Telemetry | 03.k.) Schedule installation of the router | 03.d.) | Initial Sync Date | 0 | 30 | -30 | Project - Manager Contact
3 | Real-Time Telemetry | 03.l.) LCC Posts SCADA points to ISO in Bilateral Table | 02.j.) | Initial Sync Date | 0 | 30 | -30 | Local Control Center - Technical Contact
3 | Asset Registration | 03.m.) Preliminary Asset Registration Form(s) | 01.f.) | Initial Sync Date | 0 | 30 | -30 | Lead Participant - Asset Registration Contact
4 | Asset Registration | 04.a.) Asset and PNode System Integration (Activation) Complete | 02.a.) | Initial Sync Date | 0 | 30 | -30 | ISO-NE - New Gen Coordinator
4 | System Planning & Operational Studies | 04.b.) Operational Guides completed for Initial Sync | 01.i.) | Initial Sync Date | 0 | 30 | -30 | ISO-NE - Operations Studies Contact
4 | Voice Communications | 04.c.) ARD - Voice Circuits installed and successfully tested | 03.e.) | Initial Sync Date | 0 | 30 | -30 | ISO-NE - IT COMM Contact
4 | Asset Registration | 04.d.) Multi-Generator Station and No Steam Exports Certifications | 03.m.) | Initial Sync Date | 0 | 30 | -30 | ISO-NE - New Gen Coordinator
4 | Real-Time Telemetry | 04.e.) Wind Only: Wind Plant Initial Sync Form for RPLAN and Web Services | 03.g.) | Initial Sync Date | 0 | 30 | -30 | ISO-NE - New Gen Coordinator
4 | Real-Time Telemetry | 04.f.) Wind Only: Complete WPF Web Services integration | 04.e.) | Initial Sync Date | 0 | 21 | -21 | ISO-NE - New Gen Coordinator
4 | Real-Time Telemetry | 04.g.) Wind Only: Confirm WPF Web Services integration successful | 04.f.) | Initial Sync Date | 0 | 14 | -14 | ISO-NE - New Gen Coordinator
4 | System Planning & Operational Studies | 04.h.) "As-Built" Generator Data *Subject to material modification review if different than the SIS | 03.j.) | COD | 0 | 30 | -30 | ISO-NE - System Planning Technical Contact & Project - Planning Technical Contact
4 | System Planning & Operational Studies | 04.i.) AVR and/or Governor Control requirements met | 01.b.) | Initial Sync Date | 0 | 14 | -14 | Project - Planning Technical Contact
4 | Real-Time Telemetry | 04.j.) Router installed and tested | 03.k.) | Initial Sync Date | 0 | 14 | -14 | ISO-NE - IT Comm. Projects Contact
4 | Real-Time Telemetry | 04.k.) ICCP Database updated with new SCADA Points | 03.l.) | Initial Sync Date | 0 | 14 | -14 | ISO-NE - Data Communications Contact
4 | Real-Time Telemetry | 04.l.) Complete RTU testing | 04.j.) | Initial Sync Date | 0 | 7 | -7 | ISO-NE - Data Communications Contact
4 | Asset Registration | 04.m.) Local Control Center requirements met |  | Initial Sync Date | 0 | 7 | -7 | Local Control Center - Lead Contact
4 | Asset Registration | 04.n.) Revenue Quality Metering (RQM) in place and ready | 02.i.) | Initial Sync Date | 0 | 7 | -7 | Transmission Owner - Lead Contact
4 | Lead Market Participant Registration | 04.o.) Access to eMarket | 01.m.) | Initial Sync Date | 0 | 7 | -7 | ISO-NE - New Gen Coordinator
4 | Lead Market Participant Registration | 04.p.) CCAT access | 01.m.) | Initial Sync Date | 0 | 7 | -7 | ISO-NE - New Gen Coordinator
5 | Real-Time Telemetry | 05.a.) Verify telemetry data comm links and scaling accuracy and good quality | 04.k.) | Initial Sync Date | 0 | 7 | -7 | ISO-NE - Data Communications Contact
5 | Asset Registration | 05.b.) Signed Modeled ARF | 03.m.) | Initial Sync Date | 0 | 7 | -7 | Lead Participant - Asset Registration Contact
5 | Asset Registration | 05.c.) Signed LARF (Station Service Load Asset) | 03.m.) | Initial Sync Date | 0 | 7 | -7 | Lead Participant - Asset Registration Contact
5 | Asset Registration | 05.d.) Signed TARF (Tie-Line Asset) | 03.m.) | Initial Sync Date | 0 | 7 | -7 | Lead Participant - Asset Registration Contact
5 | Asset Registration | 05.e.) Technical Data (NX-12) Final Revision | 02.m.) | Initial Sync Date | 0 | 7 | -7 | Lead Participant - Asset Registration Contact
5 | Asset Registration | 05.f.) Designated Entity (DE) Registration Form | 02.n.) | Initial Sync Date | 0 | 7 | -7 | Lead Participant - Asset Registration Contact
5 | Voice Communications | 05.g.) Dedicated 24/7 phone in place and successfully tested | 03.c.) | Initial Sync Date | 0 | 7 | -7 | ISO-NE - Assistant Coordinator Contact
5 | System Planning & Operational Studies | 05.h.) Voltage Schedule agreed upon | 01.i.) | Initial Sync Date | 0 | 7 | -7 | ISO-NE - Operations Studies Contact
5 | System Planning & Operational Studies | 05.i.) Operations and Operations Support Services Approval | 04.b.)/05.h.) | Initial Sync Date | 0 | 7 | -7 | ISO-NE - New Gen Coordinator
5 | Asset Registration | 05.j.) Provide Non-Commericial Testing Communications protocol to Lead Participant and Designated Entity | 05.f.) | Initial Sync Date | 0 | 7 | -7 | ISO-NE - New Gen Coordinator
5 | System Planning & Operational Studies | 05.k.) IA Executed | 03.i.) | Initial Sync Date | 0 | 1 | -1 | ISO-NE - Transmission Strategy & Services Contact
6 | Real-Time Telemetry | 06.a.) RTU Contact information received from the Lead Participant | 04.l.) | Initial Sync Date | 0 | 1 | -1 | Project - Manager Contact
6 | Voice Communications | 06.b.) ISO Control Room phone system programmed | 05.f.) | Initial Sync Date | 0 | 1 | -1 | ISO-NE - Assistant Coordinator Contact
6 | Asset Registration | 06.c.) ISO-NE Control Room Asset Initial Sync (or Minimal Responsiveness Test for ATRRs) Notification | 05.b.) | Initial Sync Date | 0 | 1 | -1 | ISO-NE - New Gen Coordinator
6 | Asset Registration | 06.d.) Lead Market Participant Confirmation | 05.b.) | Initial Sync Date | 0 | 1 | -1 | ISO-NE - New Gen Coordinator
6 | Real-Time Telemetry | 06.e.) RTU moved onto the production Electronic Dispatch Server | 04.l.) | Initial Sync Date | 0 | 0 | 0 | ISO-NE - Data Communications Contact
6 | Real-Time Telemetry | 06.f.) Verify good telemetry from asset(s) | 06.e.) | Initial Sync Date | 0 | 0 | 0 | ISO-NE - Data Communications Contact
6 | Real-Time Telemetry | 06.g.) Wind Only: Once RTU in production, trigger production web services | 04.g.) | Initial Sync Date | 0 | 0 | 0 | ISO-NE - New Gen Coordinator
6 | Real-Time Telemetry | 06.h.) Wind Only: Confirm WPF Web Services production successful | 06.g.) | Initial Sync Date | 0 | 0 | 0 | ISO-NE - New Gen Coordinator
6 | Real-Time Telemetry | 06.i.) Wind Only: PI tags added to the config file for CaseBuilder TARA | 06.h.) | Initial Sync Date | 0 | 0 | 0 | ISO-NE - New Gen Coordinator
6 | Asset Registration | 06.j.) IMMAC Prompt for Commercial Operation | 04.a.) | COD | 0 | 13 | -13 | ISO-NE - Market Compliance Contact
6 | System Planning & Operational Studies | 06.k.) Lagging and leading reactive capability testing completed | 01.i.) | COD | 0 | 13 | -13 | ISO-NE - Operations Studies Contact
6 | System Planning & Operational Studies | 06.l.) Operational Guides completed for Commercial Operation | 04.b.) | COD | 0 | 7 | -7 | ISO-NE - Operations Studies Contact
6 | System Planning & Operational Studies | 06.m.) Step Test, "As-built" *Subject to material modification review if different than the SIS | 04.h.) | COD | 0 | 7 | -7 | ISO-NE - System Planning Technical Contact & Project - Planning Technical Contact
6 | Power System Modeling | 06.n.) Transmission System NX-9 As Built Data* *Within 3 months of equipment In-Service Date | 03.f.) | In-Service Date | See NX-9 Details | See NX-9 Details | See NX-9 Details Tab | Project - Power System Modeling Contact
6 | Power System Modeling | 06.o.) NX-9 data matches "As-Built" final submittal | 06.n.) | COD | 0 | 7 | -7 | ISO-NE - System Planning Technical Contact & Project - Planning Technical Contact
6 | System Planning & Operational Studies | 06.p.) Voltage Task Force approval granted | 05.h.) | COD | 0 | 7 | -7 | ISO-NE - Operations Studies Contact
6 | Asset Registration | 06.q.) Verify Voltage and Reactive Control Data (NX 12D) | 02.o.) | COD | 0 | 7 | -7 | ISO-NE - Transmission Operations Technical Studies Contact & Project - Generator Technical Contact
6 | Real-Time Telemetry | 06.r.) ATRR: Minimal Responsiveness Test | 06.c.) | Initial Sync Date | 0 | 1 | -1 | ISO-NE - Ops Performance, Training, and Integration Contact
6 | Real-Time Telemetry | 06.s.) ATRR: Evaluation Phase (may last a maximum of 90 days) | 06.r.) | COD | 0 | 3 | -3 | ISO-NE - Ops Performance, Training, and Integration Contact
7 | Asset Registration | 07.a.) Submittal of Ask ISO Issue declaring Commercial Operation |  | COD | 0 | 3 | -3 | ISO-NE - Assistant Coordinator Contact & Lead Participant - Asset Registration Contact
7 | Asset Registration | 07.b.) Process in CAMS, SMS and APF MOI (for ATRRs only) for Commercial Operation | 07.a.) | COD | 0 | 2 | -2 | ISO-NE - Assistant Coordinator Contact
7 | Real-Time Telemetry | 07.c.) Verify good telemetry from asset(s) | 07.a.) | COD | 0 | 1 | -1 | ISO-NE - Data Communications Contact & Project - Communications Technical Contact
7 | Asset Registration | 07.d.) ISO-NE Control Room and LMP COD Notification | 07.a.) | COD | 0 | 1 | -1 | ISO-NE - New Gen Coordinator
7 | Asset Registration | 07.e.) Prompt scheduling an Establish CCA within AR&A | 07.a.) | COD | 0 | 1 | -1 | ISO-NE - New Gen Coordinator
7 | RNS/Local Service | 07.f.) Confirm that an RNS Application received, acknowledged and approved by ISO-NE | 02.q.) | COD | 0 | 0 | 0 | ISO-NE - Operations Tariff & Agreement Mgr Contact
7 | RNS/Local Service | 07.g.) Non-Participant RNS Agreement executed (only required if the entity is a non-Participant) | 02.q.) | COD | 0 | 0 | 0 | ISO-NE - Operations Tariff & Agreement Mgr Contact
7 | RNS/Local Service | 07.h.) Regional Network Load Reconfiguration Form submitted | 02.q.) | COD | 0 | 0 | 0 | Transmission Owner - Lead Contact
7 | RNS/Local Service | 07.i.) Local Service Application receipt is acknowledged by ISO-NE | 02.r.) | COD | 0 | 0 | 0 | ISO-NE - Operations Tariff & Agreement Mgr Contact
7 | RNS/Local Service | 07.j) Local Service Agreement executed | 07.i.) | COD | 0 | 0 | 0 | Transmission Owner - Lead Contact
7 | Asset Registration | 07.k.) Lead Market Participant Commercial Operation Authorization | 07.b.) | COD | 0 | 0 | 0 | ISO-NE - New Gen Coordinator
7 | System Planning & Operational Studies | 07.l.) Amendment to the Interconnection Agreement submitted | 05.k.) | COD | 0 | 0 | 0 | ISO-NE - Transmission Strategy & Services Contact & Project - Interconnection Agreement Contact
ISO-NE CONFIDENTIAL - COMPLETED FORM
Formulas:
Initial Sync Date = HLOOKUP([In-Service Date],E5:G6,2,FALSE)
Target/Due Date: = [Initial Sync Date]-[COD]

## NX-9 Details
NX-9 Details Checklist
Step 1: Choose the NX-9 form category type for each piece of equipment requiring an NX-9 data submission
Step 2: Enter the equipment owner; this determines the party responsible for NX-9 submittal
Step 3: Enter the name/make/model of the equipment
Step 4: Enter the In-Service date for the equipment to calculate the due dates
|  |  |  | Preliminary Data |  | NX-9 Data |  | As-Built Data
|  |  |  | Days prior: | -120 | Days prior: | -21 | Days after: | 90
Major Category | Equipment Owner | Equipment Name | Equipment In-Service Date | Due Date: | Approved: | Due Date: | Approved: | Due Date: | Approved:
|  |  |  | - |  | - |  | -
|  |  |  | - |  | - |  | -
|  |  |  | - |  | - |  | -
|  |  |  | - |  | - |  | -
|  |  |  | - |  | - |  | -
|  |  |  | - |  | - |  | -
|  |  |  | - |  | - |  | -
|  |  |  | - |  | - |  | -
|  |  |  | - |  | - |  | -
|  |  |  | - |  | - |  | -
|  |  |  | - |  | - |  | -
ISO-NE CONFIDENTIAL - COMPLETED FORM

## Meeting Notes
Project: | 0
Meeting Date/Time:
Meeting Type:
Next Meeting Date:
Next Meeting Start Time:
Location or Conference Call Info: | Dial 866-692-4541, passcode 277-5899
Attendance
Organization | Name | Present?
ISO-NE | Coordinator
ISO-NE | Asst Coordinator
ISO-NE | Data Comms Contact
ISO-NE | PSM Contact
ISO-NE | Ops Studies Contact
ISO-NE | Project Lead
ISO-NE | Engineer
Project | PSM Support
Project | Data Comms SME
Project | Other
Project | Other
Project | Project Lead
TO | Data Comms SME
TO | Other
Project Update:
Current In-Service Date: | 0
Current Initial Sync Date: | 0
Current Commercial Operation Date: | 0
Checklist Item | Action Item | Responsible Party