## Cover Sheet
Enter Project Name Here
Enter Project Name Here
Enter Department Name Here
OE-PM RACI Workbook
Status: Published or Draft
Version: X.0 (Published) or 0.X (Draft)
Prepared by:
Date Created:
Date Last Revised:

## Instructions
Enter Project Name Here
Enter Department Name Here
Guide to the RACI Workbook
Introduction A key component to building an effective and efficient project team is the early establishment of expectations for each member of the team. To that end, documents and processes that define roles and responsibilities are critical project planning deliverables. This worksheet serves to define roles and deliverables, documents which individuals will play which roles, and describes all the roles who will be involved in each task (doing the work, reviewing the results, approving the deliverable, etc.).
What is RACI? Different organizations may use different variations of the acronym; for projects at UC Davis, the standard version is RACI. Each part of the acronym is described below:
Responsible | The person who is assigned to do the work.
Accountable | The person who makes the final decision and has ultimate ownership.
Consulted | The person who must be consulted before a decision or action is taken.
Informed | The person who must be informed that a decision or action has been taken.
RACI Matrix
Accountability: The Project Manager is responsible for reviewing roles and responsibilities with the project team. The people assigned to each role must review their own assignments and indicate agreement with the role and the associated responsibilities.
Timing: Roles and Responsibilities should be completed in Planning and updated during Execution: Design. They typically remain fairly static unless new tasks/activities are added, or resources change.
Reference: Definitions for each role, and background information for each deliverable (activity or work product) are available on separate tabs within the RACI Workbook.
Instructions: • Use the UC Davis standard RACI template as a starting point. Values in the matrix should stay fairly static and serve as a guide. • Add, modify or eliminate roles and/or activities as appropriate to your project. • For each role that your project will require, record at least one name in the Role Description tab, unless the role has not yet been filled. There may be multiple people playing one role, and/or multiple roles assigned to one person. • If it is determined that the RACI needs customization for your project - - On the first pass, assign one and only one A role for each deliverable. - Assign “highest” level value for each role/task combination: typically the order would be R, A, C, I. • Review the responsibilities assigned to each role with the person or group assigned to that role, and obtain their agreement. • Update the Roles & Responsibilities pages of the Project Management Plan, based on your RACI work, for review during the project kickoff. • Publish this workbook on the project site.
Role Description
• Lists all the key project management roles and corresponding responsibilities. • Identifies who is responsible (R) and accountability (A) for each key work product. • There is a column to add the actual resource that will fill each role. • The list can be reduced to reflect only the roles that are key for your project. This list of key project roles will need to be documented on the Project Management Plan (PMP) as well.
Deliverable Matrix
• Lists all the key artifacts with a description of each artifact. • Identifies the owner of the artifact. This information does not change. • Identifies whether the process or artifact is required for the various size projects (High, Medium, Low, Mini). • Highlight those processes and artifacts that are applicable to your project. • Deviations to the standards should be documented in the text box at the bottom of the sheet. • This document does not require input from the user (other than highlighting the applicable processes and artifacts and/or identifying any exceptions.

## RACI Matrix
PM-COP RACI Matrix
R | RESPONSIBLE Person responsible for completing the assigned deliverable | Deliverables by Project Phase
|  | Initiation |  |  | Planning | [25 empty] | Execution | [31 empty] | Monitoring & Control
A | ACCOUNTABLE Ultimate Owner, Accountable for final decision | Project Proposal--Submission Form | Sizing Matrix | Initiation Business Case | Kickoff | SharePoint Site Set-up | Project Charter | Risk Management Workbook | SR/ITPL/DPR Project Initiation Requests | Communication Request Form | Business Brief (Marketing Project) | Marketing Brief (Marketing Projects) | Business Workflows/Process Model | Request for Information (RFI) | Business Requirements | Requirements Catalog (embedded in Req. Workbook) | Request for Proposal (RFP) | EIS Security Questionnaire | TAC Review | Deliverables Matrix | Communication Plan | TCoE Test Requirements | TCoE Test Estimation | Marketing Plan | Corp & RBG Communication Plan | Training Needs Assessment | Project Schedule (thru Execution: Design) | Project Management Plan | Planning Bus. Case | Measurement Plan | Vendor Design Document (Vendor) | System Documentation (Vendor) | IT Network & Systems Diagrams | IT Tech Specifications | IT Operational Guide | Business Continuity Plan | Policies and Procedures | Procure Hardware/Software | Vendor Contract | Vendor Statement of Work | NAC Risk Assessment | Project Schedule (through Completion) | Execution Bus. Case | Solution Build (Coding & Unit Testing) | Install Hardware/Software | Training Plan | Implementation Plan | TCoE Test Strategy & Plan | TCoE Test Automation Feasibility | TCoE Test Scenario & Test Case Design(Test Scenario Details) | TCoE Test Scenario & Test Case Design(Test Case Details) | TCoE Test Progress Report | TCoE Defect Report | TCoE Test Summary Report | Escalation Level Agreement | Project Test Status Report | Training Materials Finalized | User Training | Execute Communication Plan | Execute Marketing Plan | Project Closure Workbook | Measurement Plan Execution | Change Management Plan | Resource Plan | RACI Workbook | Issue Management | Financial Management | Risk Management Plan | Toll Gate Workbook (Planning, Execution, Closure) | Control Log | Monthly Status Report
C | CONSULTED Person consulted before action or decision taken | [54 empty] | Execute Test Cases/Scripts
I | INFORMED Person informed after action or decision taken | [54 empty] | Execute Test Cases/Scripts
Project Participants | [55 empty] | Execute Test Cases/Scripts
Project Sponsor |  | A | A | I | I |  | I | I | [18 empty] | I | I | I | A | [5 empty] | I |  |  | R | I | A | I | I |  | I |  | I | [8 empty] | I | I | I | I | I |  | I |  |  | I |  | A |  | I |  | I
Business Owner |  | R | R | R | A | C | A | A | A | A | A | I | A | A | A | A | A | I | I | A | A |  |  | I | I | I | A | A | A | R |  |  |  | I | I | R A | A | I | R | C | R | A | A |  | I | A | A | [7 empty] | R | I | R | R | A | A | A | A/R | A | A | A | A | I | A | A | A | A
Technology Owner |  |  | C | C | I | I | C | C | I |  |  |  | I | C | I | I | C | C | A | C | I | [5 empty] | A | C | C |  | I | I | A | A | A |  |  | A | I | C | C | A | I | A | A | C | C | [7 empty] | C | I | I | I | I | I |  |  | A | A | C | A | I | A | A |  | A
Overall Project Manager |  |  | I | I | R | R A | R | R | R | R | I | I | C | C | C | I | C | I | I | R | R | I | C | A | A | A | R | R | R | I | I | I | I | I | I | C | I | I | A | A | I | R | R | I | I | I | R | C | I | I | I | I | I | A | I | I | A | A | I | I | R |  | R | R | R | R | R | R | R | R | R
Technical Project Manager |  |  |  |  | C | I | C | C | C |  |  |  | I | C | I | I | C | A | I | I | I | C | I |  |  |  | R | C | C |  | A | A | I | I | I |  |  | R | I | I | I | R | I | A | A | I | C | I | C | C | C | I | I | I | A | I | I | I | I | I | C |  | I | C | C | C | C | I | I | C | C
Architect |  |  | I |  | I | I | I | C |  |  |  |  | I | C | I |  | C | R | R | I | I | [5 empty] | C | C |  |  | I | I | R | R | R |  |  | A I: I; A I: I; I I: I; R R: C; I A: R; I A: R; R C: I; I A: R; I I: I; A I: I; A I: I; I I: I; I I: I |  | I | C | I | C | I | I | I | C | I
Business Analyst |  |  | I | C | C | I | C | C | C |  |  |  | C | R | R | R | R | I | I | I | I | C |  |  |  |  | C | C | C |  |  | I |  | I | I |  |  |  | I | C | I | C |  |  | I |  | C |  | I | C | C | C |  | A |  | I | I | I | I | I | C |  | I | C | I | C | I | I | I | C | C
Business Project Manager |  |  | C | C | C | I | C | C | I |  |  |  | C | C | C | I | C | I | I | I | I | [5 empty] | C | C | C |  |  | I |  | I | I | [27 empty] | I | C | C | C | I | I | I | C | C | bar: A I to R R; I A to R C; I I to R C
Product Manager |  |  | C | C | C | I | C | C | I | R | I | I | C | C | C | C | C | I | I | I | C |  |  | I | I |  | C | C |  |  |  | I |  | I | I |  | C | A I: I; A I: I; I I: C; R R: C; I A: I; I I: C; R C: C; I I: I; A I: I; A I: I; I I: R; I I: R; R C: C |  | I | C | I | C | I | I | I | C | C
Technical Writer | [36 empty] | R | bar: I I; R C
Project Reviewer |  |  | I |  | I | I | I | I |  |  |  |  | I |  | I | I | I | I | I | I | I | [5 empty] | I | I |  |  |  | I |  | I | I | [27 empty] | I | I | I | I | I | I | I | I | I | bar: A I to R R; I A; R C; R C
Test Manager |  |  | I |  | I | I | I | C |  |  |  |  | I |  | I | I | I | I | I | I | I | I | R |  |  |  | C | C |  |  |  | I |  | I | I |  |  |  | I | I | I | C |  |  | I |  | I | A | C | I | I | A | A | A |  | A | I | I | I | I | C |  | I | C | I | C | I | I | I | C | C
Technical Analyst |  |  | I |  | I | I | I | C |  |  |  |  | I |  | I | I | I | I | I | I | I | [5 empty] | C | C |  |  |  | I |  | I | I | [27 empty] | I | I | I | C | I | I | I | I | C | bar: A I to R R; I A; R C; I I to R C
Engineer |  |  | I |  | I | I | I | C |  |  |  |  | I |  | I | I | I | I | I | I | I | [5 empty] | C | I |  |  |  | I |  | I | I |  |  | A I: I; A I: I; I I: I; R R: C; I A: R; I A: I; R C: I; A I: I; A I: I; I I: I; I I: I; R C: C |  | I | I | I | C | I | I | I | I | C
Test Lead | [21 empty] | R,A | C |  |  |  | C | [10 empty] | R R: C; C I: R; I C: R; I C: A; I C: A; I I: R,A; I I: C; A I: R,A; I I: R; R C: C | [8 empty] | I
User Acceptance Tester |  |  | I |  | I | I | I | C |  |  |  |  | I |  |  | I | I | I | I | I | I | [5 empty] | I | I |  |  | I | I |  | I | I |  |  | A I: I; A I: I; I I: I; R R: C; I A: I; R C: I; I I: R; A I: I; A I: I; I I: I; I I: I; R C: C |  | I | I | I | C | I | I | I | I | C
Test Engineer |  |  | I |  | I | I | I | C |  |  |  |  | I |  |  | I | I | I | I | I | I | [5 empty] | C | I |  |  | I | I |  | I | I |  |  |  | I | I | I | C |  |  | I |  | I | C | C | R | R | C | R | C |  | R | I | I | I | I | C |  | I | I | I | C | I | I | I | I | C
Business Process Analyst |  |  | I |  | I | I | I | C |  |  |  |  | R |  | I | I | I | I | I | I | I | [5 empty] | C | C |  |  |  | I |  | I | I | [27 empty] | I | I | I | C | I | I | I | I | C | bar: A I to R R; I A; R C; I I to R C
Subject Matter Expert |  |  | I | C | I | I | C | C | C |  |  |  | C | C | C | C | C | I | I | I | I | [5 empty] | C | C | C |  |  | I |  | I | I | C | R | A I: I; A I: C; I I: C; R R: C; I A: I; I I: C; R C: C; I I: I; A I: R; A I: R; I I: I; I I: I; R C: C |  | I | I | I | C | I | I | I | C | C
Project Management Office |  | I | I | I |  |  |  | I | [11 empty] | I | [45 empty] | I | I |  | I | I | I | bar: R C
Project Steering Committee |  |  |  |  | I |  | I | I | [8 empty] | I | I |  | I | I | [5 empty] | I |  |  | I | [33 empty] | I | I | C | I |  | I | I | I | bar: A I; I I to I A
Technical Architecture Committee | [18 empty] | I
Division Finance Officer |  |  |  | C
Enterprise Information Security | [17 empty] | I | [14 empty] | I
Communications | [9 empty] | I | [14 empty] | R | bar: I I
Training Partner | [6 empty] | I | [18 empty] | R | bar: I I; A I to A I
Legal | bar: A I
Compliance |  |  |  | I |  |  |  | I | [11 empty] | C
Marketing | [10 empty] | R | A R | [11 empty] | R | bar: I I
Vendor |  |  |  | C | [13 empty] | R | [12 empty] | R | R | bar: A I to A I; I A to I A; R C; I A
Financial Accounting/Controller |  |  |  | C | [10 empty] | I
Internal Audit
Contract Admin & Procurement | [13 empty] | R C |  |  | R C | bar: A I to A I
Risk |  |  |  | I |  |  |  | C | bar: A I; I I
Artifact Approvers (artifact approvers not limited to those who are highlighted )

## Role Description
Enter Project Name Here
Enter Department Name Here
RACI Role Descriptions
Role | Name | Description | Key Work Products (A's and R's)
Auditor |  | Serves as an independent oversight over bank wide operations, including project
Business Analyst |  | Investigates and analyzes business problems and manages the discovery and documentation of business requirements - Investigates and analyzes business problems and manages the discovery and documentation of requirements - Facilitates communication between the business and technical teams - Ensures traceability from requirements to technical design | - Request for Information (R) - Request for Proposal (R) - Business Requirements (R) - Requirements Traceability Matrix (R) - Functional Spec Workbook (R)
Business Owner |  | Usually reports into the Project Sponsor. May delegate some approval authority, especially to the Business Lead: - Defines project scope, objectives and success criteria - Provides direction and high level business requirements - Provides oversight of the integrity of the value proposition throughout the project lifecycle - Provides oversight of project progress and direction through review and approval of key work products - Participates in project-level governance activities - Resolves escalated business issues - Accountable for Business Case - Contract Management - Communicates the needs of the group they represent to the project | - Submission Document (R) - Business Case (A) - Change Management Plan (A) - Resource Plan (A) - Issue and Risk Management (A) - Risk Management Plan (A) - Toll Gates (A) - Monthly Status Report (A) - Project Charter (A) - SR/ITPL/DPR Project Initiation Req. (A) - Communication Request Form (A) - Business Brief (A) - Business Workflows (A) - RFI/RFP (A) - Project Schedule (A) - Project Management Plan (A) - NAC Risk Assessment (R)
Business Owner - continued |  |  | - Deliverables Matrix (A) - Project Kickoff (A) - Functional Specs (A) - Communication Plan (A) - Training Plan (A) - Business Case (A) - Business Requirements (A) - Business Continuity Plan (A/R) - Policies and Procedures (A) - Develop Test Strategy (A) - UA Test Plan (A) - Vendor Negotiations (R) - Sign Vendor Contract (R) - Escalation Level Agreement (R) - Implementation Plan (A) - UAT Signoff (A) - Post Prod Checkout (A) - Execute Communication Plan (A) - Execute Marketing Plan (A) - User Training (R)
Business Process Analyst |  | Business Process Professional responsible for working with internal clients to identify and eliminate duplicate, inefficient and unreliable processes in an effort to boost operational efficiency and performance - Elicits and document existing workflows (Current State) - Elicits new workflow requirements (Future State) - Documents business requirements for future state and may include leveraging technology - Supports defect impact analysis and assessment - Supports maintenance of a Business Process Library | - Business Process Flows (R)
Business Project Manager |  | Reports to overall project manager for all assigned project deliverables - Manages business activities of the project - Provides cost and schedule estimates for business deliverables - Assigns and monitors the work of business personnel, providing support and interpretation of instructions/objectives, and ensuring completion of the business deliverables - Negotiates with project team regarding business resource constraints - Coordinates acceptance from business stakeholders for technology design - Manages business-specific risks and issues, from identification through resolution. - Participates in project level governance - Supports overall project manager in monitoring and reporting project health/status
Business Unit Compliance Officer (BUCO) |  | - Consults with the project team to ensure the product delivered by the project team is within industry rules and regulations - Responsible for reviewing and approving key project deliverables, as appropriate
Compliance |  | - Consults with the project team to ensure the product delivered by the project team is compliant with industry rules and regulations - Responsible for reviewing and approving key documents, as appropriate
Contract Administration and Procurement |  | - Process Purchase Requisitions - Create Purchase Orders - Administer Vendor Management - Administer Vendor Risk Assessment - Write Request for Proposals and Request for Information (RFP,RFI) Contract Administration: - Administer, review, and negotiate contracts; coordinate contract review process with Legal, EIS, OSG Compliance, Insurance, etc. - Review executed BOTW standard vendor contracts and SOWs including Amendments, Addendum or Work Orders - Centralized contract record retention - Contract renewal/termination notifications - Contract compliance & standardization | - RFP/RFI's for larger initiatives (R) - Vendor Negotiations (R)
Engineer |  | - Participates in design of technical solution, in accordance to technical standards - Develops and Unit Tests software | - Solution Build (R)
Division Finance Officer |  | - Report quarterly financial data for project.
EIS |  | - Perform Security Reviews of any new or significantly modified system - Provide Information Security consultancy - Develop and/or consult on user access provisioning requirements | - Information Security Review Findings (R)
Architect |  | - Leads the development of the project’s technical solution - Coordinate with critical technical stakeholders to validate project’s technical design - Ensures adherence to technical standards across the project - Identifies key integration points between domains - Maintains the architectural vision of the solution throughout the project life - Sets up environments | - IT Network and Systems Diagram (R) - IT Tech Spec (R) - IT Operational Guide (R) - TAC Approval (R) - EIS Security Review (R) - Solution Build (R) - Install Hardware/Software (R) - SIT Plan (R) - Install Production Environment ®
Learning and Development |  | - Consults with project team on training requirements - Develops end user training materials - Delivers training | - End User Training (R)
Legal |  | - Consults with the project team to ensure the product delivered by the project team is within industry rules and regulations - Responsible for reviewing and approving key project deliverables, as appropriate - Responsible for reviewing and approving contracts | - Contract Reviews (R)
Overall Project Manager |  | Accountable for the overall execution, management and delivery of a project (scope, budget, and schedule). - Accountable for overall execution, management and delivery of a project (scope, budget, and schedule) - Establishes and facilitates the project level governance team - Provides leadership of project team - Responsible for project artifacts - Plans and manages project activities - Manages project schedule and costs - Tracks and reports project progress - Manages stakeholders - Manages and resolves issues and risks | - Business Case (if PM assigned) (R) - Change Management Plan (R) - Resource Plan (R) - Risk Management Workbook (R) - Risk Management Plan (R) - Toll Gate Workbook (R) - Project Charter (R) - Project Management Plan (R) - Project Schedule (R) - Project Status Reports (R) - Project Controls (Risk, Issues, Change Requests, Action Items) (R) - Communication Request Forms (R) - Marketing Brief (A) - SharePoint Set Up (R) - SR/ITPL/DPR Project Initiation Request (R) - Deliverables Matrix (R) - Communication Plan (R) - Implementation Plan (R) - Project Closure Workbook (R) - Training Request Form (A) - Implementation Communication Plan (R) - Request for testing services in the project(R, A) - Post Implementation Analysis(R, A)
PMO (Central or Business Unit) |  | Projects will be accountable to one or more PMOs, depending on funding and execution model - Facilitates the portfolio planning process - Facilitates the portfolio level governance process - Produces reporting and analysis on portfolio of projects - Facilitates resolution of escalated project issues and change requests - Manages the project initiation process (front door, prioritization, approvals) - Creates and maintains project management processes - Audits project management process quality | - Portfolio Dashboards (R)
Project Sponsor |  | - Secures organizational support and funding for the project - Defines strategic objective of the project - Participates in project level governance - Makes final, critical project decisions, when needed | - Submission Document (A) - Financial Management (A) - Risk Management Workbook (A) - Sign Vendor Contracts (A) - Vendor Negotiation (A)
Product Manager |  | Generally members of Product ownership team, Service Team, etc., participating in all phases of the project. - Proposes new product or service features and updates - Identifies business stakeholders, including representatives for each stakeholder group - Work with the Business Owner to document the project’s vision and scope, using standard requirements work products - Act as an SME for the business group | - Communication Request Forms (R) - Business Brief (Request) (R) - Execute Communication and Marketing Plans (R)
Project Steering Committee |  | Should include project executives: PS, BO, TO. - Represents executive stakeholder interest in the project - Provides strategic advice to Project Sponsor and Business Owner regarding trade off decisions and issue resolution - Acts as Change Control Board for project change requests - Actively participates in regular assessment of overall project health discussions and meetings to ensure: - Project vision is on track - Approval of Change Requests - Impact to customer/employee experience - On track with budget allocation
Project Reviewer |  | May also be the “resource manager” for the Overall PM, Business PM or Tech PM - Ensures use of project management best practice, including adherence to standard methodology - Reviews key project work products for quality - Provides perspective and direction on resolution of project issues
Test Manager |  | Accountable for ensuring the Quality standards are being followed. - Participates in the project level and technical governance - Acts as the second escalation point for all testing related issues - Attends weekly meeting of projects to provide a QC perspective - Manages appropriate measurements and metrics for the project. - Participates in sizing effort - Accountable overall Test Plan, Test Cases and Test Evaluation Summary - Coordinates obtaining Testing resources | - Test Strategy (R) - Test Plan (A) - Test Cases/Scripts (A) - Test Execution (A) - Defect Logs (A) - Test Signoff (R) - Post Prod Checkout ® - Provide initial estimation on resources, effort, schedule and cost for testing(R, A) - Test schedule aligned to project schedule(R, A) - Test Progress Report - Test Sumary Report
Test Lead |  | Responsible for ensuring the Quality standards are being followed. - Participates in the project execution level activities - Acts as the first escalation point for all testing related issues - Implements and manages appropriate measurements and metrics for the project. - Assigns tasks to Test Team members - Develops Test Plan, Test Cases and Test Evaluation Summary - Coordinates the development of Testing scripts - Manages deliverables of the Test engineers - Tracks and reports on testing activities - Prepares Test Plan - Attends weekly project meetings to track activities - Facilitates Testing meetings | - Test Plan(R) - Requirement Ambiguity Report(R) - Test Effort Estimation(R) - Business Scenarios(R) - Test Cases (A) - Defect Report(A) - Weekly Status Report(R) - Test Summary Report(R) - Metrics Dashboard(R) - Understanding of the project by test team(R) - Defect Management Plan(R) - Environment setup for testing(A) - Test Data and Test script preparation - Test Execution Results(R) - Test Progress Report(R, A) - Test Summary Report(R, A)
Test Engineer |  | - Prepares and updates test cases document to cover various test types and test scenarios - Executes test scripts - Publishes test execution results - Logs defects in the defect tracking tool | - Test Execution (R) - Test Cases (R) - Defect Logs (R) - Document Reviews ® - Test data and test scripts preparation® - Updated Requirements Traceability Matrix
Stakeholder |  | Any individual or group who has a stake in the outcome of the project: People or groups whose actions (support, resistance, etc.) can impact the success of your projects; People or groups who may be impacted, either positively or negatively, by the project. - Reviews the project at a high level for impact on their group - Communicates key information about the project to the group they represent - Exerts influence over the project and its deliverables | - Various depending on specific role
Subject Matter Expert (SME) |  | - Person who is expert in a particular area - Contributes to specialized requirements - Reviews project solution in the context of their area of expertise - May participate in UAT and/or Deployment - Writes test scripts - Updates Policies and Procedures - May deliver end user training (as appropriate) | - Marketing Brief (R) - UAT Cases/Scripts (R) - Policies and Procedures (R) - User Training (R)
Technical Analyst |  | Serves as a domain-specific bridge liaison between the functional requirements and the Developer. - Supports identification of technical stakeholders - Participates in discovery and documentation of technical requirements - Ensures traceability from requirements to technical design - Assists with development of Test Strategy and Test Plan | - Functional Specs (R)
Technical Architecture Committee |  | - Provides technical advice during Execution - Defines and maintains technology standards - Manages approval process for new technology introduced by a business unit and project | - TAC Approval (R)
Technical Project Manager |  | Reports to overall project manager for all assigned project deliverables : - Manages IT services regarding the development and implementation of the project - Coordinates departmental or cross-functional technical teams - Ensures completion of the technical deliverables within the triple constraints - Coordinates and aggregates project sizing efforts across IT - Manages IT activities and tasks and updates project schedule - Supports overall project manager in monitoring and reporting project health and status - Responsible for procuring hardware and software | - Vendor Design Docs (A) - System Documentation (A) - EIS Security Review (A) - Procure Hardware/Software (R) - Project Schedule (R) - Solution Build (A) - Escalation Level Agreement (R)
Technical Writer |  | - Produces end-user support material such as user guides, help texts, etc. | - Policies and Procedures (R)
Technology Owner |  | Usually an officer in technology responsible for the majority of the project’s technology work: - Provides oversight of the overall quality of the technology deliverables - Ensures adherence to technical governance processes - Resolves escalated technology issues, including technology resource contention - Leads the development activities from inception through transition, including the development of prototype solutions - Coordinates the production and sign-off of technical artifacts - Participates in design reviews to ensure proposal is technically feasible - Ensures the development of the code to specifications by scheduling and holding code reviews & code inspections - Defines application deployment strategy - Documents the technical operation’s guide - Ensures adequate SIT Testing | - Change Management Plan (A) - Resource Plan (A) - Issues and Risk Management (A) - Risk Management Plan (A) - Monthly Status Report (A) - Toll Gates (A) - Project Schedule (A) - IT Network and System Diagrams (A) - IT Tech Specs (A) - IT Operational Guide (A) - TAC Approval (A) - Procure Hardware/Software (A) - Install Hardware/Software (A) - SIT Plan (A) - Install Production Environment (A)

## Deliverable Matrix
Enter Project Name Here
Enter Department Name Here
Deliverables Matrix
Artifact | Description | Artifact/ Process Owner | Mini | Small | Medium | Large
Initiation
Submission Document | Document completed by the Business Owner that explains the proposal in some detail. | PM-COP |  | X | X | X
Business Case | Documents the value proposition for the project, including the valuation of expected benefits vs. the cost of development. Serves as the yardstick against which the project's Benefits, Costs and Timeline are measured. Serves as the basis for the Measurement Plan. | PM-COP |  |  | X | X
Sizing Matrix (in BC Workbook) | Matrix that helps the Project Manager or Business Owner determine which size the project is going to be (Small, Medium, and Large projects), which in turn, determines required artifacts and processes. | PM-COP | X | X | X | X
Planning
Project Charter | Defines the stakeholders' view of the expected outcomes to be developed, specified in terms of the stakeholders' key needs and features. It contains an outline of the envisioned core requirements, so it provides a contractual basis for the more detailed technical requirements (scope of the project). It communicates the fundamental "why and what" for the project and is a gauge against which all future decisions should be validated. | PM-COP |  | X | X | X
Risk Management Workbook | Recurring process of evaluating the project's risks against a standardized set of risk scenarios, which serves as a foundation for more detailed risk identification and results in a risk profile for the project. The Risk Management Workbook should be completed during Inception, as soon as details of the project are discovered, and updated by the end of Execution: Design, as well as any time the project experiences significant change in scope and/or approach. | PM-COP |  |  | X | X
SR/ITPL/DPR Project Initiation Request | Required if IT or Fidelity data processing services are needed. | IT |  | As Applicable
Communication Request Form | Used to describe the communication needs of a project. | Communications |  | As Applicable
Business Brief (Marketing Projects) | Used to request marketing support for your project. | Marketing |  | As Applicable
Marketing Brief (Marketing Projects) | Marketing responses to the Business Brief and outlines their support of the effort. | Marketing |  | As Applicable
Business Workflows | Documentation of step-by-step activities (including those of clients and reps) within a specific business process, using a formal business process notation. | Business |  | As Applicable
Request for Information | Request for Information, to be supplied to proposed vendors when performing a vendor selection for a new service or application. For further information, refer to the Request for Proposal Procedures Manual. | Procurement |  | As Applicable
Detailed Project Schedule (though Execution: Design) | Detailed schedule of activities necessary to complete the Execution: Design phase, including timing, duration and resources. | PM-COP |  | X | X | X
Project Management Plan | Communicates what the project is and how it will be managed, including summary of scope, roles, risks/issues, process and deliverables. | PM-COP |  |  | X | X
Deliverable Matrix (Static Document) | Matrix that identifies which project artifacts and processes need to be followed for Small, Medium, and Large projects. | PM-COP | X | X | X | X
Request for Proposal | Request for Proposal, to be supplied to proposed vendors. For further information, refer to the Request for Proposal Procedures Manual. | Procurement |  | As Applicable
TAC Approval | Review and approval by IT of the proposed system architecture. | IT |  | As Applicable
EIS Security Review | Enterprise Information Security (EIS) Engineering Security Review. To be completed when performing a major upgrade of an application or implementing a new application. | EIS |  | As Applicable
Functional Specifications | Detailed business requirements document. The Business Analyst works closely with the business partner to collect and document the business requirements. | PM-COP |  |  | X | X
Marketing Plan | Document produced by Marketing that identifies the marketing activities required to meet the needs of the effort. | Marketing |  | As Applicable
Test Approach - In Pilot | Defines the approach for how the test effort will be conducted, inclusive of both technology and user acceptance test efforts. It includes overall timing and resource requirements. | TCOE |  |  |  | X
Test Plan - In Pilot | Defines the type of testing effort to be conducted (test cases), specifying coordination points between business testers and technology support, and including test environment and test data requirements. This plan describes the effort to demonstrate that the technology team has delivered the system to the business owner in accordance with the requirements. | TCOE |  | X | X | X
Communication Plan | Document that describes the activities that will occur to satisfy the communication needs of the project at implementation. | Communications |  |  | X | X
Training Plan | Document that describes the activities that will occur to satisfy the training requirements of the effort. | Training |  | As Applicable
Business Requirements | Documentation of the requirements of business users such as customers, employees, vendors, etc. early in the development cycle to specifically design and develop the future system, process, or product. | PM-COP |  |  | X | X
Measurement Plan | Document that describes how the business is going to define success. | Business |  | As Applicable
Execution
Vendor Design Docs | Documents received from the vendor that collectively outlines the design of the system. | Vendor |  | As Applicable
System Documentation | Misc. documents received from the vendor that outline various aspects of the system. | Vendor |  | As Applicable
Test Case/Defect Workbook | Template to log all test cases needed to be tested during the testing cycles. | TCOE |  | X | X | X
IT System and Network Diagrams | Central repository for all diagrams in Information Technology. New applications and changes to existing network environments (i.e., upgrades) must be documented. | IT |  | As Applicable
Project Control Log Workbook | Log that tracks all Issues, Risks, Change Controls and Action Items. | COP-PM | X | X | X | X
IT Technical Specifications | Document is used for defining how the team will code for the transformation. | IT |  | As Applicable
IT Operational Guide | Document is provided for every release. It has information such as specific database names, required data elements, etc. It’s really a summary of the various documents listed above. It is still TBD if release notes will be included in this document or a separate document. | IT |  | As Applicable
Business Continuity Plan | Document that captures how the business unit will maintain business in the event of a disaster. | Business |  | As Applicable
Policies and Procedures (new or updated) | Effort to define or redefine policies associated with product or service being delivered by the project. | Business |  | As Applicable
Vendor Statement of Work | Document that captures and defines the work activities, deliverables and timeline a vendor will execute against. | Procurement |  | As Applicable
Project Schedule | Iterative schedule of activities necessary to complete the entire project, including timing, duration and resources. By the end of Inception, the project schedule should be detailed enough to estimate how the project will spend money in each quarter of the project's lifecycle (if this information is not detailed enough for a monthly breakdown, the quarterly funds will be spread evenly across the 3 months of the quarter). | COP-PM |  | X | X | X
SIT Plan | Systems Integration Test Plan document. To be completed by IT Application/Development Support Team. | IT |  | As Applicable
Implementation Plan | Used to identify activities associated with an implementation to ensure adequate preparation has taken place and adequate contingencies are in place. | COP-PM |  |  | X | X
Implementation Schedule | Microsoft Project Schedule that identifies all activities and tasks for the implementation. The Implementation Schedule can be part of the Project Schedule or a separate schedule and is left up to the discretion of the Project Manager. | COP-PM |  |  | X | X
Escalation Level Agreement (ELA) | Escalation Level Agreement (ELA). required depending on type of project. | IT |  | As Applicable
Service Level Agreement (SLA) | Document that captures the agreement between two parties, where one is the customer and one is the service provider. e.g. An SLA specifically between the business unit and the Help Desk. | Business |  | As Applicable
Closure
Closure Workbook | Ongoing process of identifying, analyzing and communicating the successes and challenges related to project execution, in an attempt to continuously improve the process of project execution. Survey that results in a standardized, statistical measurement of project execution. PER results can be a useful basis for a Lessons Learned discussion with the project team. | PM-COP |  | Closure Checklist only | X | X
Monitoring and Control
Change Management Plan (Static Document) | Document that communicates the project team's approach to identifying, analyzing, approving and incorporating change to project scope, time, cost or benefits. Includes effective utilization of an escalation process, when appropriate. | PM-COP |  |  | X | X
Resource Plan | Resource sheet in Microsoft Project which communicates resource requirements and the individuals who will fill required roles. | PM-COP |  | X | X | X
RACI/Roles & Responsibilities | Matrix that documents expectations regarding the participation of various roles in the activities necessary to successfully complete the project. | PM-COP |  |  | X | X
Issue Management | Ongoing process of identifying, documenting, analyzing, monitoring and resolving issues impacting the project. | PM-COP |  |  | X | X
Financial Management | Ongoing process of managing the project financials. Expectations vary depending on phase. End of Execution:Design phase the commitment is a +/- 10% range that is no more than 10% greater or less than the total number in the baseline. | PM-COP |  |  | X | X
Risk Management Plan (Static Document) | Document that communicates the project team's approach to identifying, analyzing, monitoring and responding to risk that may impact the project. | PM-COP |  |  | X | X
Toll Gate Workbook | Review by the Business Owner and Technology Owner (as appropriate) to evaluate the project team's successful completion of the previous phase objectives, their readiness to execute on the next phase objectives, and the validity of the value proposition of the project. | PM-COP |  |  | X | X
PM-COP Risk Management Workbook | Provide a list of different type of risks with their impacts, mitigation actions and tracking mechanism. | PM-COP | X | X | X | X
Test Guidelines (Static Document) - In Pilot | Provides guidelines for Test Authoring, Test Execution, and Test Defect Tracking. | TCOE |  | X | X | X
Metrics Handbook (Static Document) - In Pilot | Document that describes metrics that can be used throughout the test process to capture progress and quality. | TCOE |  | X | X | X
Test Status Report Template - In Pilot | Template to be used to report weekly test status. | TCOE |  |  | X | X
Project Status Report | Standardized report of the project's health. | PM-COP |  |  | X | X
Document Deviations: 1) If artifact is required, but not being used. 2) If artifact is not required, but is being used.
Explanation:

## Gov'rn Definition (hidden)
Governance Role (category) The process of ensuring the organization realizes an acceptable value from its investment (project) by either or both of the following:
· Ensuring the project fits within the organization’s overall strategy
· Defining or adapting processes that support the benefit realization
Specific Project Governance Bodies
o Corporate level governance (PRB): Controls resources, directs strategy
o Enterprise level governance (TGT, SLT, etc): Controls resources, directs process, influences strategy
o Portfolio level governance (PMO): Influences process decision makers, regulates process adherence
o Project level governance (Steering Committee, etc): Controls output of process
o Technology governance (TechStar, Domain groups, etc): Restrains and regulates technology decisions

## Role Definitions (hidden)
Role | Definiton (5 - 7 crisp points)
Project Management Role (category or sub-category): | Person who has accountability, whether direct or through oversight, for the successful execution and outcome of the project.
Project Role or Project Team Role (category or sub-category): | Person whose time and effort is significantly committed to specifically assigned project deliverables.
Stakeholder Role (category): | Person or organization that is actively involved in the project, or whose interests may be positively or negatively affected by execution or completion of the project, or who may exert influence over the project and its deliverables - PMBOK (In our context, I'd say that we're looking at the group of stakeholders beyond those committed to the project team.)

## QA-TCoE RACI
<Enter Project Name on Cover Sheet>
QA-TCoE RACI* Matrix (Project Activity Details are described in the QA Process Manual)
|  | QA-TCoE Project Participants | [5 empty] | Output Work Product
QA-TCoE Project Activities |  | Test Manager | Test Lead | Tester | Business System Analyst | Dev Technical Lead | Project Manager
Phase 1: Test Initiation
1. Conduct Testing Activities Initiation |  | R | I |  |  |  | A | Request for testing services in the project
2. Conduct the Kick off Meeting |  | A | R |  | C |  | C | Understanding of project by test team
3. Perform review and analysis of requirements for testability |  | A | R |  | C | C | I | Test Requirements template
4. Prepare the High Level Scope & Estimation |  | A | R |  | C | C | C | Test Effort Estimation template (initial estimation on resourcing, effort, schedule and cost for testing)
5. Prepare the High Level Test Schedule |  | A | R |  | C |  | C | Test Plan template (initial test schedule aligned to project schedule)
Phase 2: Test Planning
1. Prepare the Detailed Test Estimation |  | A | R |  | I | I | C | Test Effort Estimation template(test estimates for testing activities)
2. Develop the Test Strategy & Plan for each testing type |  | A | R |  | I | C | I | Test Strategy & Plan template
3. Prepare the Defect Management Plan |  | A | R |  | I | I | I | Defect Management Plan template
4. Prepare the Test Plan/Schedule |  | A | R |  | C | I | C | Detailed Test Plan template (test schedule aligned to project schedule)
5. Plan Test Environment(s) |  | A | R |  | I | I | C | Plan for test environment setup and procurement of hardware, software, network, and/or tools
Phase 3: Test Design & Preparation
1. Test Scenario Preparation & Review |  | I | A | R | C | C | I | Test Scenario & Test Case Design template, Test Scenario Details tab
2. Test Scenario Defect Reporting, Tracking & Closure |  | A | R | I | C | C | I | Test Scenario & Test Case Design template, Test Summary Details tab
3. Requirement Traceability Matrix Completion |  | A | R | C | C | C | I | Test Requirements template update
4. Test Case Preparation & Review |  | I | A | R | C | C | I | Test Scenario & Test Case Design template, Test Case Details tab
5. Test Environment Setup |  | I | A | R | I | I | I | Environment setup for testing
6. Test Data Setup |  | I | A | R | I | I | I | Test Data Management Process Workflow
7. PT / PE Requirements Definition |  | A | R | C | C | C | I | Test Scenario & Test Case Design template, Test Scenario Details tab
8. Test Estimation Update |  | A | R | C | I | I | I | Test Effort Estimation template (update)
Phase 4: Test Execution & Monitoring
1. Test Execution |  | I | A | R | C | I | I | Test Execution results
2. Defect Tracking |  | A | R | R | C | I | I | Test Progress Report template
3. Test Progress Reporting |  | A | R | C | C | I | I | Test Progress Report template
4. Test Summary Reporting |  | A | R | C | C | I | I | Test Summary Report template
Phase 5: Test Closure & Reporting
1. Test Closure & Reporting |  | A | R | C | C | C | C | Lessons Learned, Final Test Progress and Summary Reports
2. Post Production Defect Analysis |  | A | R | C | C | C | C | Post production defect analysis
3. Post Implementation Review |  | C | C | C | C | C | R | Post Implementation analysis
* - RACI
R | RESPONSIBLE Person responsible for completing the assigned deliverable
A | ACCOUNTABLE Ultimate Owner, Accountable for final decision
C | CONSULTED Person consulted before action or decision taken
I | INFORMED Person informed after action or decision taken