## Simple RACI
RACI Chart (Roles and Responsibilities Matrix)
For instructions / training material visit http://www.racichart.org
Process Name / Description: | Describe the process that this RACI addresses
Created On: | Date | Revision: | Date last revised
Created by: | Note all team members/functions/roles who developed and agreed to this RACI
(sequence of tasks/initiaitves in order of execution) | Who/Role | Who/Role | Who/Role | Who/Role | Who/Role
First Responsibility
Second…
Third…
Fourth…
Fifth…
Sixth…
R = Responsible, A = Accountable, C = Consulted, I = Informed
© 2012 racichart.org

## Example
RACI Chart (Roles and Responsibilities Matrix)
For instructions / training material visit http://www.racichart.org
Process Name / Description: | Plant maintenance project: Repair and resurface plant parking lot during plant shutdown in July
Created On: | 1912-01-01 | Revision: | 2012-04-01
Created by: | Kelly Bradley (facilities mgr), Mike Cole (plant manager), Joe Pallino (HR), Brian Sullivan (security), Billy Ownens (project manager)
| Facilities Mgr | Plant Mgr | HR | Security | Project Mgr
Identify a minimum of three asphalt contractors from Angie's List | C | - | - | - | R
Arrange for contractor visits and quotes | I | - | - | - | R
Review quotes and references, make contractor selection | A | I | I | - | R
Review and finalize contract, lock in plant shutdown week | I | I | - | - | R
Communicate project to shutdown maintenance crew, make sure all vehicles are removed from the lot | I | I | R | I | I
Provide security gate access codes for asphalt crew by June 15 | I | - | A | R | I
Oversee the project during the plant shutdown week, ensure it is completed on time | A | I | I | - | R
R = Responsible, A = Accountable, C = Consulted, I = Informed
© 2012 racichart.org

## Matrix Template
RACI Matrix Template
| Project Leadership |  |  |  |  | Project Team Members |  |  |  |  | Project Sub-Teams |  |  |  |  | External Contributors
| Role #1 | Role #2 | Role #3 | Role #4 | Role #5 | Role #1 | Role #2 | Role #3 | Role #4 | Role #5 | Role #1 | Role #2 | Role #3 | Role #4 | Role #5 | Role #1 | Role #2 | Role #3 | Role #4 | Role #5
Project deliverable or activity
Initiate Phase Activities
Plan Phase Activities
Execute Phase Activities
Monitor/Control Phase Activities
Close Phase Activities
Instructional Notes for the RACI Matrix:
The RACI Matrix is a powerful tool to assist in the identification of roles and assigning of cross-functional responsibilities to a project deliverable or activity.
RACI represents: R - Responsibility, A - Accountable, C - Consulted, and I - Informed
Simply place an R, A, C, I or any appropriate combination in each of the applicable roles for each activity
Each Activity should have at least one individual Accountable while there may be shared responsibilities depending on the activity.
RACI Definitions:
Responsibility = person or role responsible for ensuring that the item is completed
Accountable = person or role responsible for actually doing or completing the item
Consulted = person or role whose subject matter expertise is required in order to complete the item
Informed = person or role that needs to be kept informed of the status of item completion
Role