## 1. Risk Register Template
Objective of the risk assessment.
| CATEGORY | [5 empty] | RISK IDENTIFICATION |  |  | INHERENT RISK RATING (Risk rated in the absence of any controls. Serves to illustrate the severity of the risk, before controls, and criticality of existing controls - of particular interest to ministry executive and Internal Audit) |  |  |  |  | INITIAL RISK RATING (Risk rated based on effectiveness of current controls at the time of the initial risk assessment) |  |  |  | EVALUATION |  | MITIGATIONS MANAGEMENT | [5 empty] | TRACKING |  |  |  | RESIDUAL RISK RATING (Risk rating expected / predicted once all mitigations Additional Mitigations are in place.) |  |  |  | CURRENT RISK RATING (Current level of risk in light of mitigations implemented at this report period.) |  |  |  | RISK TOLERANCE RATING (Maximum level of risk executive is willing to accept. This should be provided by executive after having been briefed on the risk, existing and planned mitigations, and associated costs)
# | [5 empty] | OBJECTIVE | RISK EVENT | RISK CAUSE | IMPACT/ CONSEQUENCE |  | C (1-5) | SUM | RISK RATING | EXISTING MITIGATIONS | L (1-5) | C (1-5) | SUM | RISK RATING | ADEQUACY OF EXISTING MITIGATIONS | ACTION | ADDITIONAL MITIGATIONS | DELIVERABLE | REQUIRED RESOURCES | TASK OWNER | DUE DATE | DEPENDENCIES/ INTER-RELATIONSHIPS | PROGRESS % | COMMENTS/ ISSUES | FURTHER ACTION | COMPLETION DATE | L (1-5) | C (1-5) | SUM | L (1-5) | C (1-5) | SUM | L (1-5) | C (1-5) | SUM | L (1-5) | C (1-5) | SUM
This prompt row can be hidden to provide more page space. | e.g. Systems | e.g. Budget | e.g. Stakeholders | e.g. Policy | OBJECTIVE (State the plan objective this event effects.) | What planning objective does this event affect. | What is it that you are working to avoid or reduce the likelihood or impact of occurring? Risks are future events that could interfere with achievement of objectives. | What are the triggers, sources or circumstances that could act alone or together to increase the likelihood of the Risk Event occurring? There are usually multiple causes leading to a Risk Event. | If this Risk Event did occur, how would it impact objectives? What are the longer-term or cumulative consequences? | How likely? | How severe? |  |  | What are you doing now to reduce the likelihood or impact of the event? | How likely? | How severe? |  |  | Non-existent, Inadequate, Adequate, Robust, Excessive | Will you treat, monitor, transfer or avoid the risk? | What else are you going to do to better manage the risk? | What form will this mitigation take e.g. a project plan, a report, Treasury Board submission, other? | What is needed to develop and implement the mitigation? | Who will take the lead on this mitigation? | When is the deliverable to be ready? | Does the event or mitigation rely on another team or organization? Does it impact another group?
Sample | [5 empty] | 1.3 Timely service delivery to citizens. | Invoice delivery to clients is slow and inaccurate. | - Legacy system is incompatible with data input requirements. - Data entry practices inconsistent - Manual data checks | - Unmet client service quality performance - Increased A/R - Increased risk of loss - Increased cost of recovery | 5 | 4 | 20 | EXTREME | - Manual data checks - Training manual | 3 | 4 | 12 | HIGH | Inadequate | Treat | Long term: - System replacement Short term: - Update training manual - Commit more staff time. | - re System replacement strategy - Revised training manual and web counterpart - Staffing solution for short term | re System replacement strategy: Confer with IT Director and budget shop to confirm process and criteria for business case. Re Training manual: Assign lead Re Staff assignment: Review workload breakdown and skills set. | re Systems replacement: Tom re Training manual: Sarah re Staff review: Tom | re System replacement strategy: - End of fiscal re Training manual: - February 14th re Staffing review and recommendation: - February 7th | System shared with MFAS. | 25% - Initial planning complete. Implementation expected once additional staff sourced. | Further progress is dependant upon staffing approval |  |  | 2 | 4 | 8 | MEDIUM | 3 | 4 | 12 | HIGH | 2 | 4 | 8 | MEDIUM
[12 empty] | 0 | UNRATED |  |  |  | 0 | UNRATED | [14 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[12 empty] | 0 | UNRATED |  |  |  | 0 | UNRATED | [14 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[12 empty] | 0 | UNRATED |  |  |  | 0 | UNRATED | [14 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[12 empty] | 0 | UNRATED |  |  |  | 0 | UNRATED | [14 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[12 empty] | 0 | UNRATED |  |  |  | 0 | UNRATED | [14 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[12 empty] | 0 | UNRATED |  |  |  | 0 | UNRATED | [14 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[12 empty] | 0 | UNRATED |  |  |  | 0 | UNRATED | [14 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[12 empty] | 0 | UNRATED |  |  |  | 0 | UNRATED | [14 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[12 empty] | 0 | UNRATED |  |  |  | 0 | UNRATED | [14 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[12 empty] | 0 | UNRATED |  |  |  | 0 | UNRATED | [14 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[12 empty] | 0 | UNRATED |  |  |  | 0 | UNRATED | [14 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[12 empty] | 0 | UNRATED |  |  |  | 0 | UNRATED | [14 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[12 empty] | 0 | UNRATED |  |  |  | 0 | UNRATED | [14 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[12 empty] | 0 | UNRATED |  |  |  | 0 | UNRATED | [14 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[12 empty] | 0 | UNRATED |  |  |  | 0 | UNRATED | [14 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[12 empty] | 0 | UNRATED |  |  |  | 0 | UNRATED | [14 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[12 empty] | 0 | UNRATED |  |  |  | 0 | UNRATED | [14 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[12 empty] | 0 | UNRATED |  |  |  | 0 | UNRATED | [14 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[12 empty] | 0 | UNRATED |  |  |  | 0 | UNRATED | [14 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[12 empty] | 0 | UNRATED |  |  |  | 0 | UNRATED | [14 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[12 empty] | 0 | UNRATED |  |  |  | 0 | UNRATED | [14 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[12 empty] | 0 | UNRATED |  |  |  | 0 | UNRATED | [14 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[12 empty] | 0 | UNRATED |  |  |  | 0 | UNRATED | [14 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED

## 2. L&C Matrix
LIKELIHOOD AND CONSEQUENCE DESCRIPTORS FOR RISK ASSESSMENTS
Likelihood | Rating | Criteria | Probability
Almost certain | 5 | It is expected to happen. Will certainly happen this fiscal year or during the three year period of the Service Plan. | 80% to 100% or once a year or more frequently
Likely | 4 | We expect it to happen. It would be surprising if this did not happen. | 61% to 79% or once every 3 yrs
Possible | 3 | Just as likely to happen as not. We don't expect it to happen, but there is a chance. | 40% to 60% or once every 5 yrs
Unlikely | 2 | Not anticipated. We won't worry about it happening. | 11% to 39% or once every 15 years
Almost certain not to happen | 1 | It would be surprising if this happened. There would have to be a combination of unlikely events for it to happen. | 0 to 10% or once every 25 yrs
Consequence | Rating | Criteria / Examples
Catastrophic | 5 | - Major problem from which there is no recovery. - Significant damage to ministry credibility or integrity. - Complete loss of ability to deliver a critical program.
Major | 4 | - Event that requires a major realignment of how service is delivered. - Significant event which has a long recovery period. - Failure to deliver a major political commitment.
Moderate | 3 | - Recovery from the event requires cooperation across departments. - May generate media attention.
Minor | 2 | - Can be dealt with at a department level but requires Executive notification. - Delay in funding or change in funding criteria. - Stakeholder or client would take note.
Insignificant | 1 | - Can be dealt with internally at the branch level. - No escalation of the issue required. - No media attention. - No or manageable stakeholder or client interest.
Risk Rating Matrix

## 3. Project Context
CONTEXT TEMPLATE
ESTABLISH CONTEXT Purpose: establish scope, criteria, and deliverable for a particular risk assessment
1. State the subject of the risk analysis (e.g., strategic plan; business case; project agreement) and its scope with respect to organisations involved, intended audience and time frame.
Text text text.
2. State goals and objectives of the program or plan in question.
Text text text.
3. State the mission, vision, operating principles and any other value criteria.
Text text text.
4. Identify stakeholders; determine their influence on the process; methods of consultation and communciation, as appropriate.
Text text text.
5. Set out assumptions and constraints (deadlines, time-frames, environmental factors, executive or political directives).
Text text text.

## 4. Process Help
RISK MANAGEMENT PROCESS: OVERVIEW
1. The CONTEXT defines the scope and objectives of the risk management exercise. See tab 3 for details.
2. IDENTIFY risks by asking ,"What could occur that would have an impact on our objectives?" Risks have three key elements: Event, causes, impacts.
3. Risks ANALYSIS involves ranking the likelihood and consequence using a 1-5 scale See tab 2 for guidance.
4. In order to EVALUATE risks the group reviews the effectiveness and appropriateness of currents controls and determines what action to take, if any.
5. Risk TREATMENT is the activity (s) you are going to implement to better manage your exposures. Your mitigations will reduce the likelihood and/or consequence of the risk event occurring.