## Subcontractor Billing Procedure
Subcontractor Billing Procedure
XL CONSTRUCTION
To be paid in a timely manner, please follow this procedure carefully
Payment Terms
Each month you perform work:
1. Upon approval of your monthly invoice as outlined in the contract documents, Exhibit B 1.2, payment will be made
to Subcontractor within 7 days after XL Construction receives payment from the Owner.
Progress Billings
Each month you perform work:
1. Update the Subcontractor Invoice and Release Form located on separate tabs in this Excel workbook.
2. When submitting your invoice for payment, also submit a Schedule of Values (SOV tab).
3. Complete and attach the Release Form with the “Conditional Waiver and Release Upon Progress Payment” side completed for the net amount of the billing (As it appears on line E).
Releases for Your Suppliers and Subcontractors
1. Before your check is released, we must receive an Unconditional Lien Release from all of your suppliers/subcontractors through the prior billing period.
OR
2. Unconditional Final Lien Release, if they have been paid in full.
OR
3. If the amount owed to your suppliers/subcontractors approaches the remaining unpaid balance of your Subcontract, then XL may require Unconditional Progress Lien Release through the current month.
OR
4. If you cannot pre-pay your suppliers/subcontractors, or if XL has not received a satisfactory pre-qualification, XL may issue joint checks.
Retention Billing
1. Complete the XL Subcontractor Invoice form after you are 100% complete and have billed 100% less retention.
2. Line D (“Less 10% Retention”) should be $0.
3. The net amount (line E) should be the total retention held on the project.
4. Attach the invoice form with the “Conditional Waiver and Release Upon Final Payment” completed for the net amount of the billing (As it appears on line E).
5. Before your final payment is released, we must have received Unconditional Final Lien Releases from all of your suppliers/subcontractors.
Submission of Invoice and Supporting Documents
1. All invoices must be submitted on an XL Subcontractor Invoice Form. Print or type invoice information; handwritten invoices will not be processed. A Microsoft Excel version of the XL Subcontractor Invoice Form is available for download at www.xlconstruction.com/trade-partner/
2. Deliver your Invoice on or before the 20th of the month via email to AP@xlconstruction.com
3. Invoices delivered via USPS will not be processed.
Billing Inquiries
For payment status updates, please visit the XL Subcontractor Center at www.xlconstruction.com/subcontractor/paymentschedule.html
PLEASE NOTE:
If your invoice does not meet the above requirements, your billing and payment may be delayed. XL will not delay its own billing in order to wait for correct invoices and releases.

## Sub Invoice by Percent Complete
SUBCONTRACTOR INVOICE | [5 empty] | 2012-01-01 | 2012-01-31
Monthly Progress Billing | [5 empty] | 2012-02-01 | 2012-02-29
Subcontractor Information |  |  | Invoice Information |  |  | 2012-04-01 | 2012-04-30
ENTER COMPANY NAME HERE |  |  | Invoice Date: |  |  | 2012-05-01 | 2012-05-31
ENTER ADDRESS HERE |  |  | Your Invoice #: |  |  | 2012-06-01 | 2012-06-30
ENTER CITY, STATE AND ZIP CODE HERE |  |  | Invoice Period: |  |  | 2012-07-01 | 2012-07-31
[6 empty] | 2012-08-01 | 2012-08-31
Submission of Invoice and Supporting Documents | [5 empty] | 2012-09-01 | 2012-09-30
All invoices must be submitted on an XL Subcontractor Invoice Form. Print or type invoice information; handwritten invoices will not be processed. | [5 empty] | 2012-10-01 | 2012-10-31
Deliver your invoice on or before the 20th of the month via email to ap@xlconstruction.com. | [5 empty] | 2012-11-01 | 2012-11-30
Invoices delivered via USPS will not be processed.
To receive payment XL must receive the following: 1) Conditional Progress Release for the net amount due (line E); 2) Insurance Certs/Endorsements; 3) Signed Subcontract Agreement; 4) Schedule of Values.
Project Information
XL Project Number:
Project Name:
Subcontract Number:
Billing Details |  |  | Total Amount | %Complete | $ Complete
Original Subcontract |  |  |  |  | 0
XL SCO # |  |  |  |  | 0
XL SCO # |  |  |  |  | 0
XL SCO # |  |  |  |  | 0
XL SCO # |  |  |  |  | 0
XL SCO # |  |  |  |  | 0
XL SCO # |  |  |  |  | 0
XL SCO # |  |  |  |  | 0
XL SCO # |  |  |  |  | 0
XL SCO # |  |  |  |  | 0
XL SCO # |  |  |  |  | 0
XL SCO # |  |  |  |  | 0
XL SCO # |  |  |  |  | 0
Total Revised Contract | 0 |  |  | Total % Complete: | 0%
Total Complete to Date |  |  | A | 0
Less previous gross billings (Line A on prior invoice) |  |  | B | 0
Gross billing this period (Line A minus line B) |  |  | C | 0
Less retention | % | of line C | D | #VALUE!
** Net Amount Due (Line C minus line D) |  |  | E | #VALUE!

## Sub Invoice by Amount Complete
SUBCONTRACTOR INVOICE | [5 empty] | 2012-01-01 | 2012-01-31
Monthly Progress Billing | [5 empty] | 2012-02-01 | 2012-02-29
Subcontractor Information |  |  | Invoice Information |  |  | 2012-04-01 | 2012-04-30
ENTER COMPANY NAME HERE |  |  | Invoice Date: |  |  | 2012-05-01 | 2012-05-31
ENTER ADDRESS HERE |  |  | Your Invoice #: |  |  | 2012-06-01 | 2012-06-30
ENTER CITY, STATE AND ZIP CODE HERE |  |  | Invoice Period: |  |  | 2012-07-01 | 2012-07-31
Submission of Invoice and Supporting Documents
All invoices must be submitted on an XL Subcontractor Invoice Form. Print or type invoice information; handwritten invoices will not be processed. | [5 empty] | 2012-10-01 | 2012-10-31
Deliver your invoice on or before the 20th of the month via email to ap@xlconstruction.com | [5 empty] | 2012-11-01 | 2012-11-30
Invoices delivered via USPS will not be processed. | [5 empty] | 2012-12-01 | 2012-12-31
To receive payment XL must receive the following: 1) Conditional Progress Release for the net amount due (line E); 2) Insurance Certs/Endorsements; 3) Signed Subcontract Agreement; 4) Schedule of Values.
Project Information
XL Project Number:
Project Name:
Subcontract Number:
Billing Details |  |  | Total Amount | %Complete | $ Complete
Original Subcontract |  |  |  | 0%
XL SCO # |  |  |  | 0%
XL SCO # |  |  |  | 0%
XL SCO # |  |  |  | 0%
XL SCO # |  |  |  | 0%
XL SCO # |  |  |  | 0%
XL SCO # |  |  |  | 0%
XL SCO # |  |  |  | 0%
XL SCO # |  |  |  | 0%
XL SCO # |  |  |  | 0%
XL SCO # |  |  |  | 0%
XL SCO # |  |  |  | 0%
XL SCO # |  |  |  | 0%
Total Revised Contract | 0 |  |  | Total % Complete: | 0%
Total Complete to Date |  |  | A | 0
Less previous gross billings (Line A on prior invoice) |  |  | B | 0
Gross billing this period (Line A minus line B) |  |  | C | 0
Less retention | % | of line C | D | #VALUE!
** Net Amount Due (Line C minus line D) |  |  | E | #VALUE!

## SOV
Subcontractor Name |  |  |  | Project Name |  |  |  | General Contractor:
Subcontractor Address Line 1 |  |  |  | Project Address Line 1 |  |  |  | Application Number:
Subcontractor Address Line 2 |  |  |  | Project Address Line 2 |  |  |  | Application Date:
A | B | C | D | E | F | G | H | I | J | K
Item # | Description of Work | Phase Code | Scheduled Value | From Previous Application | This Period | Materials Persently Stored | Total Completed & Stored To Date | % Complete (G/C) | Balance to Finish (C-G) | Retainage
1 | Item 1 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0
2 | Item 2 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0
3 | Item 3 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0
4 | Item 4 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0
5 | Item 5 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0
6 | [6 empty] | 0 | #DIV/0! | 0 | 0
7 | [6 empty] | 0 | #DIV/0! | 0 | 0
8 | [6 empty] | 0 | #DIV/0! | 0 | 0
9 | [6 empty] | 0 | #DIV/0! | 0 | 0
10 | [6 empty] | 0 | #DIV/0! | 0 | 0
11 | [6 empty] | 0 | #DIV/0! | 0 | 0
12 | [6 empty] | 0 | #DIV/0! | 0 | 0
13 | [6 empty] | 0 | #DIV/0! | 0 | 0
14 | [6 empty] | 0 | #DIV/0! | 0 | 0
15 | [6 empty] | 0 | #DIV/0! | 0 | 0
|  | TOTALS: | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0
* Materials Stored Off Site Require an Affidavit/ Bill of sales, vendor invoices & insurance of facility where material is stored.

## SOV Sample
Best Buliders |  |  |  | Sample Project - #1234 |  |  |  | General Contractor: | XL Construction
123 Excellence Ave |  |  |  | 123 Sample Lane |  |  |  | Application Number: | 2
Wally World, CA |  |  |  | Wally World, CA |  |  |  | Application Date: | 2017-09-20
A | B | C | D | E | F | G | H | I | J | K
Item # | Description of Work | Phase Code | Scheduled Value | From Previous Application | This Period | Materials Persently Stored* | Total Completed & Stored To Date | % Complete (G/C) | Balance to Finish (C-G) | Retainage
1 | PreCon/BIM | 15500 | 8000 | 8000 | 0 | 0 | 8000 | 100% | 0 | 800
2 | Shop Drawings/Submittals | 15500 | 10000 | 5000 | 5000 | 0 | 10000 | 100% | 0 | 1000
3 | Mobilization | 15500 | 15000 | 15000 | 0 | 0 | 15000 | 100% | 0 | 1500
6 | Level 1 Sheet Metal Material (on-site) | 15500.01 | 45000 | 10000 | 35000 | 0 | 45000 | 100% | 0 | 4500
7 | Level 1 Sheet Metal Labor | 15500.01 | 8000 | 4000 | 0 | 0 | 4000 | 50% | 4000 | 400
8 | Level 1 Sheet Metal Overhead Rough In | 15500.01 | 15000 | 15000 | 0 | 0 | 15000 | 100% | 0 | 1500
9 | Level 1 Piping Inserts & Hangers | 15500.01 | 20000 | 0 | 8000 | 0 | 8000 | 40% | 12000 | 800
10 | Level 2 Sheet Metal Material (on-site) | 15500.02 | 45000 | 0 | 10000 | 0 | 10000 | 22.22% | 35000 | 1000
11 | Level 2 Sheet Metal Labor | 15500.02 | 8000 | 0 | 8000 | 0 | 8000 | 100% | 0 | 800
12 | Level 2 Sheet Metal Overhead Rough In | 15500.02 | 15000 | 0 | 5000 | 0 | 5000 | 33.33% | 10000 | 500
13 | Level 2 Piping Inserts & Hangers | 15500.02 | 20000 | 0 | 0 | 0 | 0 | 0% | 20000 | 0
14
15
|  | TOTALS: | 209000 | 57000 | 71000 | 0 | 128000 | 61.24% | 81000 | 12800
* Materials Stored Off Site Require an Affidavit/ Bill of sales, vendor invoices & insurance of facility where material is stored.

## Conditional Progress LR
CONDITIONAL WAIVER AND RELEASE ON PROGRESS PAYMENT California Civil Code Section 8132
NOTICE: THIS DOCUMENT WAIVES THE CLAIMANT'S LIEN, STOP PAYMENT NOTICE, AND PAYMENT BOND RIGHTS EFFECTIVE ON RECEIPT OF PAYMENT. A PERSON SHOULD NOT RELY ON THIS DOCUMENT UNLESS SATISFIED THAT THE CLAIMANT HAS RECEIVED PAYMENT.
Identifying Information:
| Name of Claimant: | ENTER COMPANY NAME
| Name of Customer: | XL CONSTRUCTION
| Job Location: | JOB NAME
JOB ADDRESS
JOB ADDRESS
| Owner: | OWNER
Through Date:
Conditional Waiver and Release:
This document waives and releases lien, stop payment notice, and payment bond rights the claimant has for labor and service provided, and equipment and material delivered, to the customer on this job through the Through Date of this document. Rights based upon labor or service provided, or equipment or material delivered, pursuant to a written change order that has been fully executed by the parties prior to the date that this document is signed by the claimant, are waived and released by this document, unless listed as an Exception below. This document is effective only on the claimant's receipt of payment from the financial institution on which the following check is drawn:
Maker of Check:
Amount of Check:
Check Payable to:
Exceptions: This document does not affect any of the following: (1) Retentions. (2) Extras for which the claimant has not received payment. (3) The following progress payments for which the claimant has previously given a conditional waiver and release but has not received payment: Date(s) of waiver and release: _________________________________ Amount(s) of unpaid progress payment(s): $____________________ (4) Contract rights, including (A) a right based on rescission, abandonment, or breach of contract, and (B) the right to recover compensation for work not compensated by the payment.
Signature:
Claimant's Signature:
Claimant's Title:
Date of Signature:

## Conditional Final LR
CONDITIONAL WAIVER AND RELEASE ON FINAL PAYMENT California Civil Code Section 8136
NOTICE: THIS DOCUMENT WAIVES THE CLAIMANT'S LIEN, STOP PAYMENT NOTICE, AND PAYMENT BOND RIGHTS EFFECTIVE ON RECEIPT OF PAYMENT. A PERSON SHOULD NOT RELY ON THIS DOCUMENT UNLESS SATISFIED THAT THE CLAIMANT HAS RECEIVED PAYMENT.
Identifying Information:
| Name of Claimant: | ENTER COMPANY NAME
| Name of Customer: | XL CONSTRUCTION
| Job Location: | JOB NAME
JOB ADDRESS
JOB ADDRESS
| Owner: | OWNER
Conditional Waiver and Release:
This document waives and releases lien, stop payment notice, and payment bond rights the claimant has for labor and service provided, and equipment and material delivered, to the customer on this job. Rights based upon labor or service provided, or equipment or material delivered, pursuant to a written change order that has been fully executed by the parties prior to the date that this document is signed by the claimant, are waived and released by this document, unless listed as an Exception below. This document is effective only on the claimant's receipt of payment from the financial institution on which the following check is drawn:
Maker of Check:
| Amount of Check: | $
Check Payable to:
Exceptions: This document does not affect any of the following:
This document does not affect any of the following:
Disputed claims for extras in the amount of: |  |  | $
Signature:
Claimant's Signature:
Claimant's Title:
Date of Signature:

## Unconditional Final LR
UNCONDITIONAL WAIVER AND RELEASE ON FINAL PAYMENT California Civil Code Section 8138
NOTICE TO CLAIMANT: THIS DOCUMENT WAIVES AND RELEASES LIEN, STOP PAYMENT NOTICE, AND PAYMENT BOND RIGHTS UNCONDITIONALLY AND STATES THAT YOU HAVE BEEN PAID FOR GIVING UP THOSE RIGHTS. THIS DOCUMENT IS ENFORCEABLE AGAINST YOU IF YOU SIGN IT, EVEN IF YOU HAVE NOT BEEN PAID. IF YOU HAVE NOT BEEN PAID, USE A CONDITIONAL WAIVER AND RELEASE FORM
Identifying Information:
| Name of Claimant: | ENTER COMPANY NAME
| Name of Customer: | XL CONSTRUCTION
| Job Location: | JOB NAME
JOB ADDRESS
JOB ADDRESS
| Owner: | OWNER
Unconditional Waiver and Release:
This document waives and releases lien, stop payment notice, and payment bond rights the claimant has for all labor and service provided, and equipment and material delivered, to the customer on this job. Rights based upon labor or service provided, or equipment or material delivered, pursuant to a written change order that has been fully executed by the parties prior to the date that this document is signed by the claimant, are waived and released by this document, unless listed as an Exception below. The claimant has been paid in full.
Exceptions: This document does not affect any of the following:
This document does not affect any of the following:
Disputed claims for extras in the amount of: |  |  | $
Signature:
Claimant's Signature:
Claimant's Title:
Date of Signature:

## Unconditional Progress LR
UNCONDITIONAL WAIVER AND RELEASE ON PROGRESS PAYMENT California Civil Code Section 8134
NOTICE TO CLAIMANT: THIS DOCUMENT WAIVES AND RELEASES LIEN, STOP PAYMENT NOTICE, AND PAYMENT BOND RIGHTS UNCONDITIONALLY AND STATES THAT YOU HAVE BEEN PAID FOR GIVING UP THOSE RIGHTS. THIS DOCUMENT IS ENFORCEABLE AGAINST YOU IF YOU SIGN IT, EVEN IF YOU HAVE NOT BEEN PAID. IF YOU HAVE NOT BEEN PAID, USE A CONDITIONAL WAIVER AND RELEASE FORM
Identifying Information:
| Name of Claimant: | XL CONSTRUCTION
| Name of Customer: | CUSTOMER NAME
| Job Location: | JOB NAME
JOB ADDRESS
JOB ADDRESS
| Owner: | OWNER
Through Date:
Unconditional Waiver and Release:
This document waives and releases lien, stop payment notice, and payment bond rights the claimant has for labor and service provided, and equipment and material delivered, to the customer on this job through the Through Date of this document. Rights based upon labor or service provided, or equipment or material delivered, pursuant to a written change order that has been fully executed by the parties prior to the date that this document is signed by the claimant, are waived and released by this document, unless listed as an Exception below. The claimant has received the following progress payment:
Maker of Check:
Amount of Check:
Check Payable to:
Exceptions: This document does not affect any of the following: (1) Retentions. (2) Extras for which the claimant has not received payment. (3) Contract rights, including (A) a right based on rescission, abandonment, or breach of contract, and (B) the right to recover compensation for work not compensated by the payment.
Signature:
Claimant's Signature:
Claimant's Title:
Date of Signature:

## SAMPLE BILLING
Subcontractor Invoice |  |  |  |  | 2012-01-01 | 2012-01-31
Monthly Progress Billing |  |  |  |  | 2012-02-01 | 2012-02-29
[5 empty] | 2012-03-01 | 2012-03-31
Subcontractor Information |  | Invoice Information |  |  | 2012-04-01 | 2012-04-30
Your Company Name |  | Invoice Date: | 2012-05-30 |  | 2012-05-01 | 2012-05-31
Your Company Address |  | Your Invoice #: | 12345 |  | 2012-06-01 | 2012-06-30
Your Company City, State, Zip |  | Invoice Period: | 2012-05-01 |  | 2012-07-01 | 2012-07-31
[5 empty] | 2012-08-01 | 2012-08-31
Submission of Invoice and Supporting Documents |  |  |  |  | 2012-09-01 | 2012-09-30
All invoices must be submitted on an XL Subcontractor Invoice Form. Print or type invoice information; handwritten invoices will not be processed. |  |  |  |  | 2012-10-01 | 2012-10-31
Deliver your invoice on or before the 20th of the month via email to ap@xlconstruction.com |  |  |  |  | 2012-11-01 | 2012-11-30
Invoices delivered via USPS will not be processed. |  |  |  |  | 2012-12-01 | 2012-12-31
To receive payment XL must receive the following: 1) Conditional Progress Release for the net amount due (line E); 2) Insurance Certs/Endorsements; 3) Signed Subcontract Agreement; 4) Schedule of Values.
Project Information
XL Project Number: | 12345
Project Name: | XL Test Project
Subcontract Number: | 12345-10001
Billing Details |  | Total Amount | %Complete | $ Complete
Original Subcontract | 12345-10001 | 10000000 | 10% | 1000000
XL ACO # | 1 | 50000 | 50% | 25000
XL ACO # | 2 | 20000 | 25% | 5000
XL ACO # | 3 | 500 | 30% | 150
XL ACO # | 4 | 25000 |  | 0
XL ACO # |  |  |  | 0
XL ACO # |  |  |  | 0
XL ACO # |  |  |  | 0
XL ACO # |  |  |  | 0
XL ACO # |  |  |  | 0
XL ACO # |  |  |  | 0
XL ACO # |  |  |  | 0
XL ACO # |  |  |  | 0
Total Revised Contract | 10095500 |  | Total % Complete: | 10.2%
Total Complete to Date |  | A | 1030150
Less previous gross billings (Line A on prior invoice) |  | B | 0
Gross billing this period (Line A minus line B) |  | C | 1030150
Less 10% retention (10% of line C) |  | D | -103015
** Net Amount Due (Line C minus line D) |  | E | 927135