| Organization Name: |  |
| --- | --- |
| Project Title: | Linkage Lab |
| GOAL STATEMENT: | Develop contractual relationships with the health plans from the eight duals counties. |

| Objective 1: Participate in organizational capacity building, including executive leadership and management development as well as organizational readiness preparation through participation in 4 seminars (up to 10 days total) |  |  |
| --- | --- | --- |
| ACTIVITIES/TASKS | TIMELINE | OUTPUTS (Tangible products that result from a program’s activities or tasks) |
| - Finalize senior management team selection: Required: - Executive Director or Chief Executive Officer - Chief Financial Officer/Director of Finance - Chief Operating Officer/ Director of Programs Plus staff in charge of: - Outreach - Marketing - Operations Point of Contact for project team – must be one of the project team members. | January 1, 2015 | - Completed contact sheet including names, titles, phone numbers and email addresses. |
| Status: |  |  |
| 1.2 Attend 3 – day kick-off seminar in Southern California | January 14 – 16, 2015 | - Team member attendance - Assessment of organizational capabilities - Development of strategic plan to offer Long-Term Service and Supports on a contractual basis with health care partner |
| Status: |  |  |
| 1.3 Attend three additional 2 - 3day seminars in locations to be determined | June 2015 December 2015 May 2016 | - Team member attendance - Work Assignment from previous seminar has been completed and turned in - Organizational capacities are improved and the organization is prepared to enter into a contractual partnership with a health care provider |
| Status: |  |  |

| Objective 2: Select 1 member for participation in Advisory Board |  |  |
| --- | --- | --- |
| ACTIVITIES/TASKS | TIMELINE | OUTPUTS (Tangible products that result from a program’s activities or tasks) |
| 2.1 Attend twelve, 1-hour Advisory Board calls. | Feb 2014 March 2014 April 2014 May 2014 July 2014 August 2014 September 2014 October 2014 November 2014 January 2016 February 2016 March 2016 April 2016 June 2016 | - Team member attendance - Reports on progress towards assigned tasks - Preparation for upcoming seminars |
| Status: |  |  |

| Objective 3: Participate in Learning Collaborative through use of web based platform |  |  |
| --- | --- | --- |
| ACTIVITIES/TASKS | TIMELINE | OUTPUTS (Tangible products that result from a program’s activities or tasks) |
| 3.1 Provide monthly updates on activities and progress via web based platform | January 2015 – June 2016 | - Monthly Reports |
| Status: |  |  |

| Objective 4: Participate in technical assistance activities with identified consultants. |  |  |
| --- | --- | --- |
| ACTIVITIES/TASKS | TIMELINE | OUTPUTS (Tangible products that result from a program’s activities or tasks) |
| - Host two in-person technical assistance meetings for your organization ranging from 3-5 hours | February 2015 August 2015 | - Agenda - Technical assistance summary - Team member attendance |
| Status: |  |  |
| 4.2 Participate in monthly technical assistance support calls | January 2015 – June 2016 | - Agenda - Technical assistance summary - Team member attendance |
| Status: |  |  |

| Objective 5: Complete a Root Cause Analysis (RCA) to determine what causes high costs and low quality care for the target population |  |  |
| --- | --- | --- |
| ACTIVITIES/TASKS | TIMELINE | OUTPUTS (Tangible products that result from a program’s activities or tasks) |
| - Consumer interviews, potential partner discussions, chart reviews, review of QIO data (if applicable), etc. - Hone in on Target Population - Identification of needs of the target population - Identification of potential health care partner’s needs - Understanding of what the new models/ interventions are needed to address the issues revealed in the RCA |  | - Final Report |
| Status: |  |  |
| - Conduct an external scan of the market to understand existing health care and community-based services, resources, under-utilized assets, gaps in service areas, potential areas of duplication, etc. - Understanding of existing services and gaps - Identification of potentially needed CBO partnerships |  | - Final Report |
| Status: |  |  |

| Objective 6: Identify Potential Partnership with the Health Care Sector (represent new business opportunity) |  |  |
| --- | --- | --- |
| ACTIVITIES/TASKS | TIMELINE | OUTPUTS (Tangible products that result from a program’s activities or tasks) |
| 6.1 Identify potential partners (health care and managed care providers) |  | - List of identification of potential partnerships |
| Status: |  |  |
| - Facilitate an assessment of your organization’s core offerings / gaps, consider what the potential partners might need from your organization, and create a framework for strategic-oriented partnership discussions |  | - Final strategy and plan for ongoing partnership development |
| Status: |  |  |
| - Determine messaging around core offerings and strategies for new service development |  | - Initial concept paper / executive summary that can be shared with potential partners |
| Status: |  |  |
| - Schedule and host meetings; determine follow up and ongoing communication plan with potential partner |  | - Dates, agendas and summaries of partner meetings and an ongoing plan for fostering the relationships |
| Status: |  |  |

| Objective 7: Determine if other CBO Partnerships are needed for Model Design and Service Delivery |  |  |
| --- | --- | --- |
| ACTIVITIES/TASKS | TIMELINE | OUTPUTS (Tangible products that result from a program’s activities or tasks) |
| - Determine organizational gaps and identify the services for what type of collaborative relationships may be needed other CBOs |  | - Final report of Organizational Assessment and an understanding of the services offered by potential CBO partners |
| Status: |  |  |
| 7.2 Identify CBO partners if needed |  | - List of identified CBO partners |
| Status: |  |  |
| - Host meetings with potential CBO partners, determine collaborative structure for multi-organization involvement, and a plan for ongoing meetings/ communications |  | - Summary of Collaborative Structure for working together |
| Status: |  |  |
| - Craft and sign Memorandum of Agreement (MOA) for working together, if needed |  | - Agreed upon and signed MOA |
| Status: |  |  |

| Objective 8: Design Service Delivery Model |  |  |
| --- | --- | --- |
| ACTIVITIES/TASKS | TIMELINE | OUTPUTS (Tangible products that result from a program’s activities or tasks) |
| - Research existing models / interventions that meet the needs discovered via RCA, interviews, market scan, etc. |  | - Summary of Model Research findings |
| Status: |  |  |
| - Determine interventions / strategies / key foundational areas of focus based upon RCA findings, market and consumer research, etc. |  | - Final report including Model Design |
| Status: |  |  |
| - Determine model operations, protocols, integration strategies, overall management, staffing, intake / referral, assessment, and service delivery process |  | - Final report including Model Operations |
| Status: |  |  |
| - Define measurements and how performance will be evaluated |  | - Final report including Performance Measurements |
| Status: |  |  |
| - Assess organizational level of readiness for service delivery and determine a plan for capacity building |  | - Final report including Capacity Building for Implementation |
| Status: |  |  |
| - Develop strategy and implementation plan with documented tasks, roles, and timelines |  | - Final report including Strategy and Implementation plan with documented tasks, roles, and timelines |
| Status: |  |  |

| Objective 9: Develop a Budget and Rate Structure |  |  |
| --- | --- | --- |
| ACTIVITIES/TASKS | TIMELINE | OUTPUTS (Tangible products that result from a program’s activities or tasks) |
| - Define services/ interventions, cost of delivery, volume, staffing, wages, expenses, training, rate structure, etc., and develop financial model to reflect a variety of situations |  | - Final plan defining Budget and Rate Structure |
| Status: |  |  |

| Objective 10: Develop an Approach to Marketing |  |  |
| --- | --- | --- |
| ACTIVITIES/TASKS | TIMELINE | OUTPUTS (Tangible products that result from a program’s activities or tasks) |
| - Define and craft messaging around new service / model in a manner that is important to potential partners and develop marketing material |  | - Final plan defining Communication Strategy and Marketing Material |
| Status: |  |  |
| - Determine additional training / support needed to promote services on an ongoing basis |  | - Marketing Training |
| Status: |  |  |
| - Determine strategies for education, outreach, and the development of new business |  | - Final plan defining Business Development plan including projections, target partnerships, strategies per partnership, roles, and timelines |
| Status: |  |  |

| Objective 11: Finalize the Business Plan |  |  |
| --- | --- | --- |
| ACTIVITIES/TASKS | TIMELINE | OUTPUTS (Tangible products that result from a program’s activities or tasks) |
| - Create a business planning framework and a plan that includes (executive summary, target market, service description, organizational structure, partnerships & alliances, budget, implementation plan, outreach plan, growth plan, etc.) |  | - Business Plan - Outline for Further Proposal Development |
| Status: |  |  |

| Objective 12: Formalize a partnership with a Healthcare or Managed Care provider |  |  |
| --- | --- | --- |
| ACTIVITIES/TASKS | TIMELINE | OUTPUTS (Tangible products that result from a program’s activities or tasks) |
| - Finalize structure of the partnership including an outline of services, implementation plan, communication plan, performance standards, and an agreed upon and signed legal agreement |  | - Formalized partnership |
| Status: |  |  |

| Objective 13: Participate in Evaluation Activities |  |  |
| --- | --- | --- |
| ACTIVITIES/TASKS | TIMELINE | OUTPUTS (Tangible products that result from a program’s activities or tasks) |
| 13.1 As developed and implemented by The SCAN Foundation participate in evaluation activities. |  | - Formalized partnership |
| Status: |  |  |

| Objective 14: Additional Activities |  |  |
| --- | --- | --- |
| ACTIVITIES/TASKS | TIMELINE | OUTPUTS (Tangible products that result from a program’s activities or tasks) |
| 14.1 |  |  |
| Status: |  |  |