## Timeline
Tasks
Start | End | Duration | Label | Vert. Position | Vert. Line
2018-03-28 | 2018-04-11 | 15 | Task 1 Mar 28 - Apr 11 | -25 | -25
2018-04-12 | 2018-05-01 | 20 | Task 2 Apr 12 - May 1 | -40 | -15
2018-05-02 | 2018-05-25 | 24 | Task 3 May 2 - May 25 | -55 | -15
2018-04-28 | 2018-07-12 | 76 | Task Label 4 | -80 | -80
2018-06-15 | 2018-07-04 | 20 | Task Label 5 | -30 | -30
2018-07-05 | 2018-08-03 | 30 | Task Label 6 | -45 | -15
2018-08-10 | 2018-09-10 | 32 | Task Label 7 | -20 | -20
2018-09-11 | 2018-09-15 | 5 | Task Label 8 | -60 | -40
2018-09-16 | 2018-10-06 | 21 | Task Label 9 | -75 | -15
Insert new rows above this one
Milestones
Date |  |  | Label | Position
2018-04-02 |  |  | Start, Apr 2 | 30
2018-05-25 |  |  | Milestone #1 | 25
2018-08-03 |  |  | Milestone #2 | 20
2018-10-06 |  |  | Deliver, Oct 6 | 15
Insert new rows above this one
Formulas:
End = [Start]+[Duration]-1
Start = [End, row above]+1

## About
PROJECT TIMELINE by Vertex42.com
https://www.vertex42.com/ExcelTemplates/project-timeline.html
About This Template
This template uses a scatter chart with data labels and error bars to create a project timeline that shows both milestones and tasks with durations. Unlike a Gantt chart, which shows each task on a separate row, you control the vertical positioning of tasks within the timeline. You can specify the length of the vertical leader line to help show task dependencies.
This type of project timeline is mainly useful for a general overview of a project rather than showing a detailed work breakdown structure.
More Templates
Visit Vertex42.com to download other timeline and project management templates.
More Timeline Templates
More Project Management Templates
About Vertex42
Vertex42.com provides professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.