## User stories status
User story | Category | Implemented | Release | Notes
sto_1: Login into ODN | Data Publisher, ODN Administrator | Yes | v1.0.1 (update)
sto_2: New catalog record in catalog | Data Publisher | Yes | v0.9.0
sto_3: New associated pipeline created manually | Data Publisher | Yes | v0.9.0
sto_4: New associated pipeline created in wizard | Data Publisher | Obsolete |  | OUTDATED - wizards will not be implemented
sto_5: New associated pipeline as modified copy of an existing pipeline | Data Publisher | Yes | v0.10.0
sto_6: Modification of an associated pipeline manually | Data Publisher | Yes | v0.9.0
sto_7: Modification of an associated pipeline in wizard | Data Publisher | Obsolete |  | OUTDATED - wizards will not be implemented
sto_8: Modification of dataset metadata | Data Publisher | Yes | v0.9.0
sto_9: Pipeline scheduling management | Data Publisher | Obsolete |  | Implemented in sto_24
sto_10: Dataset resource(s) created/updated on demand | Data Publisher | Yes | v0.9.0
sto_11: Make dataset publicly available | Data Publisher | Yes | v0.9.0
sto_12: Make dataset publicly invisible | Data Publisher | Yes | v0.9.0
sto_13: Catalog records browser | Data Publisher | Yes | v0.11.0 (update)
sto_14: Catalog records search using keywords | Data Publisher | Yes | v0.11.0 (update)
sto_15: Datasets browser | Data Publisher | No
sto_16: Catalog records filtering | Data Publisher | Yes | v0.11.0 (update)
sto_17: List of available resources for a dataset | Data Publisher | Yes | v0.9.0
sto_18: Download latest version of file dump | Data Publisher | Yes | v0.9.0
sto_19: Download any version of file dump | Data Publisher | No
sto_20: Publicly available catalog record browser | Data Consumer | Yes | v0.9.0
sto_21: Publicly available catalog records search using keywords | Data Consumer | Yes | v0.9.0
sto_23: Publicly available catalog records filtering | Data Consumer | Yes | v0.9.0
sto_24: Pipeline scheduling information | Data Publisher | Yes | v0.9.0
sto_25: Social media sharing | Data Consumer | Yes | v0.9.0
sto_26: Comments for dataset | Data Consumer | No
sto_27: List of available resources for a public dataset | Data Consumer | Yes | v0.9.0
sto_28: Download latest version of public dataset file dump | Data Consumer | Yes | v0.9.0
sto_29: Download any version of public dataset file dump | Data Consumer | No
sto_30: Metadata about public catalog | Data Consumer | No
sto_31: New user and its role | ODN Administrator | Yes | v1.0.1
sto_32: Modify user's profile and its role | ODN Administrator | Yes | v1.0.1
sto_33: Modify user's own user profile | Data Publisher | Yes | v1.0.1
sto_34: Delete user | ODN Administrator | No
sto_35: Retrieving DCAT metadata about dataset via public catalog API | Data Consumer | On hold |  | DCAT not supported. Upstream CKAN support needed.
sto_36: Retrieving DCAT metadata about dataset via internal catalog API | Data Publisher | On hold |  | DCAT not supported. Upstream CKAN support needed.
sto_37: Downloading DCAT metadata about dataset from public catalog manually | Data Consumer | On hold |  | DCAT not supported. Upstream CKAN support needed.
sto_38: Downloading DCAT metadata about dataset from internal catalog manually | Data Publisher | On hold |  | DCAT not supported. Upstream CKAN support needed.
sto_39: Retrieving VoID metadata about dataset via public catalog API | Data Consumer | On hold |  | DCAT not supported. Upstream CKAN support needed.
sto_40: Retrieving VoID metadata about dataset via internal catalog API | Data Publisher | On hold |  | DCAT not supported. Upstream CKAN support needed.
sto_41: Pipeline monitoring | Data Publisher | Obsolete |  | Implemented in sto_53
sto_42: Pipeline debugging | Data Publisher | Yes | v1.0.1
sto_43: Add external catalog for update | Data Publisher | Yes | v0.11.0 (update)
sto_44: Modify external catalog for update | Data Publisher | Yes | v0.11.0 (update)
sto_45: Delete external catalog for update | Data Publisher | Yes | v0.10.0
sto_46: New associated pipeline as copy of an existing pipeline | Data Publisher | Obsolete |  | Implemented in sto_5
sto_47: Associate an existing non-associated pipeline | Data Publisher | Yes | v0.9.0
sto_48: Termination of dataset maintenance | Data Publisher | No
sto_49: Termination of publication of dataset | Data Publisher | No
sto_50: Dataset resource(s) created/updated automatically when data processing done | Data Publisher | Yes | v0.10.0
sto_51: Logout from ODN | Data Publisher, ODN Administrator | Yes | v1.0.1 (update)
sto_52: ODN installation | ODN Administrator | Yes | v0.9.0
sto_53: Last publication status of a pipeline | Data Publisher | Yes | v0.9.0
sto_54: Modification of name and description of an associated pipeline | Data Publisher | Obsolete |  | Implemented in sto_6
sto_55: Retrieving public data via SPARQL endpoint | Data Consumer | In progress |  | Will be implemented in ODN v1.1.0
sto_56: Retrieving data via SPARQL endpoint | Data Publisher | In progress |  | Will be implemented in ODN v1.1.0
sto_57: Atom/RSS feed | Data Consumer | No
sto_58: ODN catalog theme installation | ODN Administrator | Yes | v0.9.0
sto_59: Retrieving public data from dataset via REST API | Data Consumer | Yes | v1.0.1
sto_60: Retrieving data via REST API | Data Publisher | Yes | v1.0.1
sto_61: Add visualization to dataset | Data Publisher | In progress |  | Will be implemented in ODN v1.1.0
sto_62: Add application | Data Publisher | No
sto_63: Modify application | Data Publisher | No
sto_64: Delete application | Data Publisher | No
sto_65: Browse applications | Data Consumer | No
sto_66: Publish data file without transformation (wizard) | Data Publisher | Obsolete |  | OUTDATED - wizards will not be implemented
sto_67: Publish tabular data file as 4* RDF file (wizard) | Data Publisher | Obsolete |  | OUTDATED - wizards will not be implemented
sto_68: Publish tabular data file as 5* RDF data accessible via SPARQL queries (wizard) | Data Publisher | Obsolete |  | OUTDATED - wizards will not be implemented
sto_69: Management of default public catalog for publicly available datasets | ODN Administrator | Yes | v0.10.0
sto_70: GUI language management | ODN Administrator | Yes | v1.0.1
sto_71: Instant manual synchronization with external catalog | Data Publisher | Yes | v1.0.1 (update)
sto_72: Instant manual synchronization with public catalog | Data Publisher | Yes | v0.10.0
sto_73: Associate a pipeline for mirroring of data | Data Publisher | No
sto_74: Default organization | ODN Administrator | No
sto_75: Retrieve list of datasets contained in public catalog via API | Data Consumer | Yes | v0.9.0
sto_76: Search the list of datasets contained in public catalog via API | Data Consumer | No
sto_77: Self-registration of public catalog users | Data Consumer | No
sto_78: Disassociate a pipeline | Data Publisher | Yes | v0.11.0
sto_79: Verify the configuration of external catalog | Data Publisher | No
sto_80: Management of default external catalog for publicly available datasets | ODN Administrator | No
sto_81: Export pipeline as zip file | Data Publisher | Partially | v1.0.1 | Initial implementation
sto_82: Import pipeline from zip file containing no DPU templates | Data Publisher | Partially | v1.0.1 | Initial implementation
sto_83: Import pipeline from zip file containing DPU templates | Data Publisher | Partially | v1.0.1 | Initial implementation
sto_84: Export DPU template(s) as zip file | Data Publisher | Partially | v1.0.1 | Initial implementation
sto_85: Import DPU template(s) from zip file | Data Publisher | Partially | v1.0.1 | Initial implementation
sto_86: Default set of DPU templates | Data Publisher | Yes | v1.0.1
sto_87: Create visualization | Data Publisher | In progress |  | Will be implemented in ODN v1.1.0
sto_88: Replicate file dump of public dataset | Data Consumer | No
sto_89: Configure DPU dynamically | Data Publisher | No
sto_90: Publish tabular data file as 5* RDF file (wizard) | Data Publisher | Obsolete |  | OUTDATED - wizards will not be implemented
sto_91: Publish tabular data file as 4* RDF data accessible via SPARQL queries (wizard) | Data Publisher | Obsolete |  | OUTDATED - wizards will not be implemented
sto_92: Anonymize source tabular data by skipping rows and/or columns | Data Publisher | No
sto_93: Upgrade ODN | ODN Administrator | No
sto_94: Delete pipeline execution data | ODN Administrator | No
sto_95: External catalog for metadata update only | Data Publisher | No
sto_96: ODN uninstallation | ODN Administrator | No