## About this Template
Notes on how to complete this Project Financial Plan Template
Introduction
This template is for use by all Capital Projects under the remit of CRG to define the Projects Financial and Resource budgets and on-going costs. It is presented to CRG initially at approval stage along with the Business case and again at appropriate Stage Gates and change requests. This is a living document that should be updated during the project life cycle and should reflect any changes that may occur (including scope and costs). The template is intended for use by all CRG managed Capital projects including IS, Change Management and Construction projects. There will be a number of projects that need to amend the template (for example, large construction projects that have on-going costs over longer than 5 years). Not all worksheets have to be completed by all projects and not all sections of worksheets have to be completed. Project Details, Version History and Project Summary are required and an appropriate selection of remaining worksheets for any project. Each month the project's budgets are tracked against the actuals held on Oracle Projects system. The Project Manager/Project Sponsor complete this template before presentation to CRG at each required Stage Gate. Budget costs are defined in a format compatible with Oracle Projects set up. This includes The lowest level of expenditure must have a corresponding Expenditure Type/Expense code defined on Oracle. Each
https://www.tcd.ie/local/pmo/assets/Documents/PMO%20handbook%20v1%204%20Issued.pdf
Oracle Projects
The College financial system for managing Capital projects is Oracle Projects. All project financial activities will use Oracle Projects - Budget structure, Purchase Orders, Invoice processing, BI reporting. Refer to the FSD and FIS websites for training or details relating to use of Oracle Projects.
Notation Comments
1. Throughout the spreadsheet, the project details at the top of the worksheets are automatically updated from the 'Project Details' Worksheet
2. Financial estimates are in €, with cent not being required. 3. VAT is shown separately for all financials estimate. Current Standard Rate VAT ia defined for all VAT rates. Amend to non standard VAT rate if appropriate. Use of non-standard VAT rates may need to be verified by the College Taxation Officer.
4. Calculated fields are shaded in Grey.
5. Fields shaded in Blue have been done for visual effect / ease of reading. The project sponsor / project manager can change any of the formatting in the spreadsheet as per their own specific requirements.
6. Fields shaded in Orange require initial update by the project sponser/project manager.
7. Fields shaded on Green are not changeable.
8. Fields shaded in Pink are Task level budgets which can be used where a more detailed budget breakdown is not available. This is likely to be used during initiation phase or high level design phase of a project.
Project Details Worksheet
The following fields have been standardised throughout the spreadsheet to support ease of completion. They can be easily replaced by updating them in the 'Project Details' worksheet. Simply type the required replacement value in the relevant field. PMO can provide the Project ID. FIS Project Number will not be available until the project has been approved by CRG, issued to FSD and created on Oracle Projects. Use the Version No and Issue Date to reflect different versions created during the project life cycle.
[Project Short Name]
[Project ID]
[Oracle Project Number]
[EOG Champion’s Name]
[Project Sponsor’s Name]
[Project Manager’s Name]
[Version No]
[Issue Date]
This worksheet should also contain a brief description of the project, funding details and Sponsor signoff. FSD will only set up or amend project details on the basis of a Sponsor's approval.
Version History Worksheet
This should be updated with the details of changes made to the spreadsheet to support tracking. New versions should be released to support Stage Gate and any Change Requests until project completion.
Project Summary Worksheet
The worksheet will automatically calculate the overall financial estimate for each type of project cost and on-going cost completed in the detailed financial worksheets. It summarises the financial information into a format that can be used to present to the CRG / EOG / Board for review or approval. For larger projects, addition financial information and modelling may be required. The development of such information / models will be supported by the Finance Partners / FSD.
Assumptions Worksheet
This should be updated with the details of assumptions made during the development of the Project Financial Plan in order to support tracking how the final details where reached. It will help the project sponsor, project manager, and project team have a firm view on how the Project Financials Plan was developed, where information came from, and track input from any reviewers, etc.
During the development of the project plans it may be necessary to make assumptions around areas that are not fully clarified or finalised. These assumptions should be documented for future reference and validation.
All assumptions should be validated, proven or disproved, and closed, as soon as possible after they have been identified.
Assumptions change over time and the latest version of the project plans should reflect this.
Financial Worksheets
The Financial Worksheets will be used by FSD to set up budgets in Oracle Projects. Each financial worksheet contains details of expenditure types within tasks relevant to that particular worksheet. Expenditure types listed are a selection of what is available in Oracle Projects. Additional expenditure types can be added (assuming they exist in Oracle Projects; lists are available in the FIS website). Task level information is used by FSD to structure the project. Where a Financial Plan is presenting for the first time to CRG it is sufficient to provide budget details in the 'Approved Project Spend(Baseline figure)'. Where a Financial Plan is presenting at Stage Gate the Proposed Spend/Seeking Approval should be populated. This column will then become the Baseline for the next Stage Gate. The Total Project Cost column should be populated with Approved in Principle amounts or Project estimates. These values will not be used to populate any values in Oracle Projects.
Costs (IS) - Captures the estimated IS costs related to projects which support the delivery of the business solution. Most projects will require input from IS so it is important that these costs are provided and confirmed by IS before initial presentation to CRG and at each project
Costs (Resources) - Captures the estimated man-days effort & standardised man-day costs / fixed price costs related to projects which support the delivery of the business solution. If appropriate, it also includes details of Training costs which incur additional costs. All projects will be required to complete this information.
Costs - Construction (can be New Build, Decant, Refurb or a mixture) - Captures the estimated costs related to the refurbishment / update / change of existing buildings, and that of new build projects which support the delivery of the business solution. Not all projects will have such costs, so completion of this tab will only be required where appropriate.
Costs (Misc) - Captures any other miscellaneous costs identified related to the project which support the delivery of the business solution.Not all projects will have such costs, so completion of this tab will only be required where appropriate.
On-going Costs (Operational) - Captures the specific On-going Operational costs that the business will incur when the project has completed its delivery. For example, there may be a need for additional resources to perform new processes, etc. All projects will be required to complete this information, even if the resulting costs result in nil being reported.
Costs (IS) Worksheet
The project sponsor or project manager should contact the ISS department to seek their support and input, working closely with them in developing and completing the required financials for any IT activities.
Project IS
If, as part of the project, any existing technology needs to be updated or changed, or new technology needs to be developed / purchased, etc, the relevant costs will need to be included in this section.The % contingency can vary depending on the perceived level of uncertainty around the estimates or the specific project. Contingency can be included at worksheet level or at task level.
Costs (Resources) Worksheet
The worksheet is divided into Internal and External resources. Both sections are based on resource days using rates extracted from the Daily Rates worksheet. Internal Rates are defined per the College Salary/Pay scales. External rates should be populated on a project basis.
Project Resource Contingency % row
Most organisations will add a % contingency to the financial / resource estimates to allow for a 'reasonable' amount of risk and uncertainty around the estimation process. The % contingency can vary depending on the perceived level of uncertainty around the estimates or the specific project. As a norm, 10%-20% is usually allocated.
The % resource contingency is set to 15% as a default in this template, but can be easily changed to the required % by simply entering the required % contingency for the particular project in the shown % contingency field at the bottom of the worksheet. The resulting € value will be automatically calculated and updated throughout the spreadsheet.
Costs (New Build), Costs (Refurb), Costs(Decant) Worksheets
These worksheets are divided into a number of sections which may or may not be relevant to your particular project. Complete the appropriate sections.
New Build
If, as part of the project, there is a need to design & build a new building/ major construction is required, the relevant estimated costs will need to be included in this section.
The project sponsor or project manager should contact the Estates and Facilities department to seek their support and input, working closely with them in developing and completing the required financials.
Refurbishment
If, as part of the project, there is a need to refurbish / update / change an existing building, the relevant estimated costs will need to be included in this section.
The project sponsor or project manager should contact Estates and Facilities & ISS departments to seek their support and input, working closely with them in developing and completing the required financials.
Decant
If, as part of the project, there is a need to decant out of / in to new or existing accommodation, the relevant estimated costs will need to be included in this section.
The project sponsor or project manager should contact Estates and Facilities & ISS departmentsto seek their support and input, working closely with them in developing and completing the required financials.
Project Construction Contingency % row
Most organisations will add a % contingency to the financial estimates to allow for a 'reasonable' amount of risk and uncertainty around the estimation process. The % contingency can vary depending on the perceived level of uncertainty around the estimates or the specific project. Within TCD, 20%-30% is allocated to construction projects estimated costs at the early stages of the project. This % is reduced as the project progresses and the construction contracts are concluded (and price agreed with external contractors).
The contingency can be easily changed to the required % by simply entering the required % contingency for the particular task or worksheet in the appropriate field. The resulting € value will be automatically calculated.
Overall Project Costs (Construction) and Overall Project Costs (Construction) (including Contingency) rows are automatically calculated by the worksheet.
Costs (Misc) Worksheet
During the development of the project plans, miscellaneous costs that are not directly related to resource costs or standard project costs may be identified. If this happens, then this worksheet is used to capture estimates for these costs. An example of this might be travel & expenses of the project team members which directly relates to the project activities.
Not all projects will have such cost or need to complete this worksheet. But all projects should carefully consider if these types of costs exist as if they are not budgeted for, they can very quickly eat into the approved project budget.
For each project deliverable include the deliverable Name, Description, Unit Cost (€) and Quantity (#), the Total is calculated automatically in the spreadsheet. Include any notes deemed relevant. If required by your project, the worksheet can be updated by adding, updating or deleting the content / examples that exists on the worksheet.
If NOT required by your project, please zeroise all amounts (giving a €0 Overall Miscellaneous Project Costs total).
This a free text worksheet as it is very difficult to determine what exactly might need to be included in these types of costs.
The € amount shown in the "Overall Miscellaneous Project Costs" cell at the bottom of the worksheet is automatically included in the Project Summary worksheet.
On-going Costs (Operational) Worksheet
When the project is delivered, the business will need to operate the solution as part of their normal operations. But there may be an on-going (incremental) operational costs associated with this operation. For example, if TCD deliver a new buiding, it may be necessary to recruit additional resources to service the building, or have new IT systems which require licensing & support - all giving rise to additional (incremental) on-going cost.
All incremental on-going / operational costs should be included in this worksheet. Completing the worksheet is similar in approach to filling the various Project Costs worksheets (see notes above), the key difference being that the on-going costs consider the costs over a 5 year period post project implementation. Larger projects may need to extend this out to a long time period.
Other key differences are outlined below.
Resources (Project) section
As part of preparing the Business Case, and during the Initiation & Strategic Planning phase (& on-going throughout the project lifecycle) required project & post-project resource effort is estimated and reviewed.
Post-implementation project resource effort estimates by resource grade are captured in this worksheet.
Resources (On-going) Year 1 Breakdown:
Summary information, by resource grade, should be input into either the Year 1 Breakdown Resources (On-going), Internal Resources, Man-days row or the Resources, External Resources, Man-days row depending on if the resources are internal TCD or external to TCD. The worksheet will then automatically calculate the on-going costs for those resources for the cost by grade (Year 1) and the on-going costs in the Project Summary worksheet.
Resource (On-going) - cost by grade, by year
By inputting the resource estimates as above, the calculate € values are updated in the Year 1 summary totals. These totals can not be altered directly in the Year 1 summary row.
The worksheet also updates Year 2 - Year 5 € totals to reflect the same € values as that of Year 1. If required, Year 2 - Year 5 values can be manually updated / over ridden to reflect the actual € estimated.

## Project Details
Project Financials Plan - Project Details
Project Name: | Sample Capital Project | [* per PMO Register ]
Project ID: | YY-123 | [* per PMO Register ]
Oracle Project Number | 12450 | [* Complete when No. has been assigned by FSD ]
EOG Champion: | Update Champion Name | [* per Business Case ]
Project Sponsor: | Update Sponsor Name | [* per Business Case ]
Project Manager: | Update PM Name | [may not be known at approval stage, If not add TBC ]
Version No: | V0 1
Issue Date | DD/MM/YYYY | [* In format DD/MM/YYYY]
Brief Description: | (Example) The overall objective of this program is to stabilise the Registry and ensure that it can provide the services required to:- - Support the student lifecycle - Enable the College to grow student numbers with confidence that the structures, processes and systems in the Registry can support that growth - Meet the needs of current and future students for a high quality service - Impact positively on the reputation of the College - Reduce the significant risks associated with the current environment (and highlighted in the START Review report) - Provide a solid foundation for future enhancement of the SITS system (G2 functionality) to support College needs |  |  | [* Provide a brief description of the project ]
Please consider and indicate any areas that may need to review this document in advance of submission to the CRG / EOG / Board for approval.
REVIEWS: Have the following functions reviewed these project financials?
| Reviewer name | Business Area | Y, N, N/A
Estates and Facilities
ISS
Commercial Revenue Unit
Finance
HR
Disability Services
Legal
PMO
Funding details:
| Source | Account Cost Code/Source of funds |  | Amount €
| Internal |  |  | 0 | [* At least one source of funding is required for a project. Define all levels, both internal and external]
| Internal |  |  | 0
| Source | Funder Name | Grant ID | Amount €
| External |  |  | 0
| External |  |  | 0
Approved Project Spend:
| Source (CRG/EOG/Board) |  | Date | Amount | [* Include details of approvals at various stage gates and change requests. Each time an approval to spend is granted generate a new version of the spreadsheet ]
Sponsor Approval
[* Sponsor to physically sign this section prior to CRG. It will then be sent to FSD for project set up on Oracle ]
| Name | Signature |  | Date

## Version History
Project Financials Plan - Version History
Project Name: | Sample Capital Project
Project ID: | YY-123
Oracle Project Number | 12450
EOG Champion: | Update Champion Name
Project Sponsor: | Update Sponsor Name
Project Manager: | Update PM Name
Version No: | V0 1
Issue Date: | DD/MM/YYYY
Version No: | Version Date: | Revised By: | Description of change
V0.1 | DD/MM/YY |  | Initial Plan for Presentation to CRG at Project Initiation | [* Update version history each time a new version is prepared. This might be due to Stage gate approval or Change Request, for example. ]
V0.2
V0.3
V0.4
V0.5
V0.6
V1.0
V1.1
V1.2
V1.3

## Project Summary
Project Financials - Summary
| Project Name: | Sample Capital Project
| Project ID: | YY-123
| Oracle Project Number | 12450
| EOG Champion: | Update Champion Name
| Project Sponsor: | Update Sponsor Name
| Project Manager: | Update PM Name
| Version No: | V0 1
| Issue Date: | DD/MM/YYYY
NOTE: All financials are VAT inclusive on this page.
Task No | COSTS |  | Approved Project Spend (Current Baseline) | On-going Costs Year 1 | On-going Costs Year 2 | On-going Costs Year 3 | On-going Costs Year 4 | On-going Costs Year 5 | Total On-going Costs Year 1 - 5 | Approved Project Spend & On-going Year 1-5 | Proposed Project Spend/ Seeking Approval (Future Baseline) | Total Project Cost (Approved in principle OR Estimate)
Capital Costs
| Costs - IS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Costs - Misc |  | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0
| Costs - New Build |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Costs - Refurb |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Costs - Decant |  | 0 | N/A | N/A | N/A | N/A | N/a | N/A | 0 | 0 | 0
Resource Costs
| Resources (Internal) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Resources (External) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PMO Funding Levy @ | 2% | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0
| Overall Costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FOR INFO
Project Totals (included in above numbers)
| Contingency |  | 0
| VAT |  | 0
| Inflation |  | 0

## Assumptions
Financial Planning Assumptions
Project Name: | Sample Capital Project
Project ID: | YY-123
Oracle Project Number | 12450
EOG Champion: | Update Champion Name
Project Sponsor: | Update Sponsor Name
Project Manager: | Update PM Name
Version No: | V0 1
Issue Date: | DD/MM/YYYY
No: | Details / Description of Assumption
1 | Working days per year calculated in this template at 220
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56

## Costs (IS)
Project Costs - IS
|  | Project Name: | Sample Capital Project
|  | Project ID: | YY-123
|  | Oracle Project Number | 12450
|  | EOG Champion: | Update Champion Name
|  | Project Sponsor: | Update Sponsor Name
|  | Project Manager: | Update PM Name
|  | Version No: | V0 1
|  | Issue Date: | DD/MM/YYYY
|  | IS (Project Cost) |  |  |  |  | Approved Project Spend (Current Baseline) |  | Proposed Spend/ Seeking Approval (Future Baseline) | Total Project Cost (Approved in principle OR Estimate to be validated)
| Task | Expenditure Type |  |  | Unit Cost € | Qty | Total €
| Hardware | Higher level project cost estimate (breakdown to be provided later) | [5 empty] | 0 | 0 | 0
|  | Laptops/PC |  |  | 0 | 0 | 0 |  | 0 | 0
|  | Peripherals |  |  | 0 | 0 | 0 |  | 0 | 0
|  | Servers |  |  | 0 | 0 | 0 |  | 0 | 0
|  | Maintenance |  |  | 0 | 0 | 0 |  | 0 | 0
|  | Network Router |  |  | 0 | 0 | 0 |  | 0 | 0
|  | Network Switch |  |  | 0 | 0 | 0 |  | 0 | 0
|  | Wireless Access point |  |  | 0 | 0 | 0 |  | 0 | 0
|  | Data Storage |  |  | 0 | 0 | 0 |  | 0 | 0
|  | Data Cable |  |  | 0 | 0 | 0 |  | 0 | 0
|  | Telephone Switch |  |  | 0 | 0 | 0 |  | 0 | 0
|  | Telephone handsets |  |  | 0 | 0 | 0 |  | 0 | 0
|  | Mobile handsets |  |  | 0 | 0 | 0 |  | 0 | 0
|  | Telephone Cable |  |  | 0 | 0 | 0 |  | 0 | 0
|  | Fibre Optic links install |  |  | 0 | 0 | 0 |  | 0 | 0
|  | Fibre Optic links recurring |  |  | 0 | 0 | 0 |  | 0 | 0
|  | Line Rental |  |  | 0 | 0 | 0 |  | 0 | 0
|  | Storage(SAN) |  |  | 0 | 0 | 0 |  | 0 | 0
|  | Hardware Install |  |  | 0 | 0 | 0 |  | 0 | 0
|  | Hosting Costs |  |  | 0 | 0 | 0 |  | 0 | 0
|  | Load Balancers |  |  | 0 | 0 | 0 |  | 0 | 0
[6 empty] | Sub-total |  | 0 | 0 | 0
[6 empty] | VAT @ | 23% | 0 | 0 | 0
Task No | Hardware |  |  |  |  | Sub-total |  | 0 | 0 | 0
|  |  |  | Contingency @ |  |  | 20% | 0 | 0 | 0
[7 empty] | Total Hardware | 0 | 0 | 0
| Software |  |  |  | 0 | 0 |  | 0 | 0 | 0
|  | Software Licenses |  |  | 0 | 0 | 0 |  | 0 | 0
|  | Software recurring |  |  | 0 | 0 | 0 |  | 0 | 0
|  | Software install |  |  | 0 | 0 | 0 |  | 0 | 0
|  | Software monitoring |  |  | 0 | 0 | 0 |  | 0 | 0
[6 empty] | Sub-total |  | 0 | 0 | 0
[6 empty] | VAT @ | 23% | 0 | 0 | 0
Task No | Software |  |  |  |  | Sub-total |  | 0 | 0 | 0
[6 empty] | Contingency @ | 20% | 0 | 0 | 0
|  | Total Software | [5 empty] | 0 | 0 | 0
| Managed Services |  |  |  | 0 | 0 |  | 0 | 0 | 0
|  | Contract Cost |  |  | 0 | 0 | 0 |  | 0 | 0
|  | Contract Legal |  |  | 0 | 0 | 0 |  | 0 | 0
|  | Contract Procurement |  |  | 0 | 0 | 0 |  | 0 | 0
|  | Hosting |  |  | 0 | 0 | 0 |  | 0 | 0
[6 empty] | Sub-total |  | 0 | 0 | 0
[6 empty] | VAT @ | 23% | 0 | 0 | 0
Task No | Managed Services |  |  |  |  | Sub-total |  | 0 | 0 | 0
|  | Contingency @ |  |  |  |  | 20% | 0 | 0 | 0
|  | Total Managed Services | [5 empty] | 0 | 0 | 0
| IS Prof Services |  |  |  | 0 | 0 |  | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 |  | 0 | 0
[5 empty] | 0 | 0 | 0 |  | 0 | 0
[5 empty] | 0 | 0 | 0 |  | 0 | 0
[5 empty] | 0 | 0 | 0 |  | 0 | 0
[6 empty] | Sub-total |  | 0 | 0 | 0
[6 empty] | VAT @ | 23% | 0 | 0 | 0
Task No | IS Prof Services |  |  |  |  | Sub-total |  | 0 | 0 | 0
|  | Contingency @ |  |  |  |  | 20% | 0 | 0 | 0
|  | Total IS Prof Services | [5 empty] | 0 | 0 | 0
[6 empty] | Contingency at | 10% | 0 | 0 | 0 | [*Contingency can be set at either worksheet or lower level ]
[6 empty] | Overall IS - TOTAL |  | 0 | 0 | 0
FOR INFO
Project Totals (included in above numbers)
| Contingency |  |  |  | 0
| VAT |  |  |  | 0
| Inflation |  |  |  | 0

## Costs (Resources)
|  | Project Name: | Sample Capital Project
|  | Project ID: | YY-123
|  | Oracle Project Number | 12450
|  | EOG Champion: | Update Champion Name
|  | Project Sponsor: | Update Sponsor Name
|  | Project Manager: | Update PM Name
|  | Version No: | V0 1
|  | Issue Date: | DD/MM/YYYY
Internal Resources
|  | Resources (Project Cost) |  |  | Approved Project Spend (Current Baseline) |  | Proposed Spend/ Seeking Approval (Future Baseline) | Total Project Cost (Approved in principle OR Estimate to be validated)
| Task | Expenditure Type |  | Man Days | Total € |  | Total € | Total €
| Internal Resources |  |  |  |  | 0 | 0 | 0
|  | Professor |  | 0 | 0 |  | 0 | 0
|  | Associate Professor |  | 0 | 0 |  | 0 | 0
|  | Snr Lecturer |  | 0 | 0 |  | 0 | 0
|  | Lecturer |  | 0 | 0 |  | 0 | 0
|  | Snr Admin 1 |  | 0 | 0 |  | 0 | 0
|  | Snr Admin 2 |  | 0 | 0 |  | 0 | 0
|  | Snr Admin 3 |  | 0 | 0 |  | 0 | 0
|  | Admin 1 |  | 0 | 0 |  | 0 | 0
|  | Admin 2 |  | 0 | 0 |  | 0 | 0
|  | Admin 3 |  | 0 | 0 |  | 0 | 0
|  | Snr Exec Officer1/2 |  | 0 | 0 |  | 0 | 0
|  | Executive Officer |  | 0 | 0 |  | 0 | 0
|  | Other 1 |  | 0 | 0 |  | 0 | 0
|  | Other 2 |  | 0 | 0 |  | 0 | 0
|  | Other 3 |  | 0 | 0 |  | 0 | 0
Task No | Internal Resources |  |  | Sub-total |  | 0 | 0 | 0
|  |  |  | Contingency | 10% | 0 | 0 | 0
[5 empty] | Total Internal Resources | 0 | 0 | 0
External Resources
| Task | Expenditure Type |  | Man-Days | Cost
| External Resources |  |  |  |  | 0 | 0 | 0
|  | Steering Committee Chair |  | 0 | 0 |  | 0 | 0
|  | Programme Manager |  | 0 | 0 |  | 0 | 0
|  | Project Manager |  | 0 | 0 |  | 0 | 0
|  | AN Other 1 |  | 0 | 0 |  | 0 | 0
|  | AN Other 2 |  | 0 | 0 |  | 0 | 0
|  | AN Other 3 |  | 0 | 0 |  | 0 | 0
|  | AN Other 4 |  | 0 | 0 |  | 0 | 0
|  | AN Other 5 |  | 0 | 0 |  | 0 | 0
|  | AN Other 6 |  | 0 | 0 |  | 0 | 0
|  | AN Other 7 |  | 0 | 0 |  | 0 | 0
|  | AN Other 8 |  | 0 | 0 |  | 0 | 0
|  | AN Other 9 |  | 0 | 0 |  | 0 | 0
|  |  |  | Sub-total |  | 0 | 0 | 0
|  |  |  | VAT@ | 23% | 0 | 0 | 0
Task No | External Resources |  |  | Sub-total |  | 0 | 0 | 0
|  |  |  | Contingency | 10% | 0 | 0 | 0
[5 empty] | Total External Resources | 0 | 0 | 0
|  |  | Overall Total: Resources |  |  | 0 | 0 | 0
FOR INFO
Project Totals (included in above numbers)
|  | Contingency |  | 0
|  | VAT |  | 0
|  | Inflation |  | 0

## Daily Rates
Project Daily Rates - Internal & External
Internal TCD Daily Rates
Based On Salary Scales As At 1 January 2010
Source: HR - February 2012
Cost | Daily
Grade | Rate
Professor | 767
Associate Professor | 570
Snr Lecturer | 495
Lecturer | 322
Snr Admin 1 | 717
Snr Admin 2 | 564
Snr Admin 3 | 504
Admin 1 | 409
Admin 2 | 297
Admin 3 | 243
Snr Exec Officer1/2 | 261
Executive Officer | 195
Other 1 | 1
Other 2 | 1
Other 3 | 1
External Consultancy Rates |  | [Rates to be reviewed on a project by project basis]
Based On : ????????
Source: ???????
Rates shown are exclusive of VAT.
Daily
Role / Lot | Rate
Steering Committee Chair | 1
Programme Manager | 1
Project Manager | 1
AN Other 1 | 1
AN Other 2 | 1
AN Other 3 | 1
AN Other 4 | 1
AN Other 5 | 1
AN Other 6 | 1
AN Other 7 | 1
AN Other 8 | 1
AN Other 9 | 1

## Costs (New Build)
Project Costs - Construction (New Build) Related
|  | Project Name: | Sample Capital Project
|  | Project ID: | YY-123
|  | Oracle Project Number | 12450
|  | EOG Champion: | Update Champion Name
|  | Project Sponsor: | Update Sponsor Name
|  | Project Manager: | Update PM Name
|  | Version No: | V0 1
|  | Issue Date: | DD/MM/YYYY
|  | New Build (Project Cost) |  |  | Approved Project Spend (Current Baseline) |  | Proposed Spend/ Seeking Approval (Future Baseline) | Total Project Cost (Approved in principle OR Estimate to be validated)
| Task | Expenditure Type |  |  | Total €
| Professional / Design Fees |  |  |  |  | 0 | 0 | 0
|  | Architect |  |  | 0 |  | 0 | 0
|  | PM/QS |  |  | 0 |  | 0 | 0
|  | C&S Engineer |  |  | 0 |  | 0 | 0
|  | M&E Engineer |  |  | 0 |  | 0 | 0
|  | Archaeologist |  |  | 0 |  | 0 | 0
|  | Project Consultants |  |  | 0 |  | 0 | 0
|  | Surveying |  |  | 0 |  | 0 | 0
|  | PSDP Project Supervisor Design stage |  |  | 0 |  | 0 | 0
|  | Assigned Certifier |  |  | 0 |  | 0 | 0
|  | Clerk of Works |  |  | 0 |  | 0 | 0
|  | (other expenditure types available on Oracle) |  |  | 0 |  | 0 | 0
|  | Sub-total |  |  |  | 0 | 0 | 0
|  | VAT @ |  |  | 23% | 0 | 0 | 0
Task No | Professional / Design Fees | Sub-total |  |  |  | 0 | 0 | 0
|  | Contingency @ |  |  | 10% | 0 | 0 | 0
|  | Total Prof/ Design Fees |  |  |  | 0 | 0 | 0
| Works Contract |  |  |  |  | 0 | 0 | 0
|  | Demolition |  |  | 0 |  | 0 | 0
|  | Construction |  |  | 0 |  | 0 | 0
|  | Fit out |  |  | 0 |  | 0 | 0
|  | Civil Works |  |  | 0 |  | 0 | 0
|  | Mechanical Works |  |  | 0 |  | 0 | 0
|  | ESB Charges |  |  | 0 |  | 0 | 0
|  | Electrical Works |  |  | 0 |  | 0 | 0
|  | Irish Rail Charges |  |  | 0 |  | 0 | 0
|  | (other expenditure types available on Oracle) |  |  | 0 |  | 0 | 0
|  | Sub-total |  |  |  | 0 | 0 | 0
|  | VAT @ |  |  | 23% | 0 | 0 | 0
Task No | Works Contract | Sub-total |  |  |  | 0 | 0 | 0
|  | Contingency @ |  |  | 10% | 0 | 0 | 0
|  | Total Works Contract |  |  |  | 0 | 0 | 0
| Statutory Fees |  |  |  |  | 0 | 0 | 0
|  | Planning Permission |  |  | 0 |  | 0 | 0
|  | Fire Certificate |  |  | 0 |  | 0 | 0
|  | Disability Access Cert (DAC) |  |  | 0 |  | 0 | 0
|  | (other expenditure types available on Oracle) |  |  | 0 |  | 0 | 0
|  | Sub-total |  |  |  | 0 | 0 | 0
|  | VAT @ |  |  | 23% | 0 | 0 | 0
Task No | Statutory Fees | Sub-total |  |  |  | 0 | 0 | 0
|  | Contingency @ |  |  | 10% | 0 | 0 | 0
|  | Total Statutory Fees |  |  |  | 0 | 0 | 0
| Local Authority Charges |  |  |  |  | 0 | 0 | 0
|  | Local Authority Contribution |  |  | 0 |  | 0 | 0
|  | DCC Levy |  |  | 0 |  | 0 | 0
|  | (other expenditure types available on Oracle)) |  |  | 0 |  | 0 | 0
|  |  |  | Sub-total |  | 0 | 0 | 0
|  | VAT @ |  |  | 23% | 0 | 0 | 0
Task No | Local Authority Charges | Sub-total |  |  |  | 0 | 0 | 0
|  | Contingency @ |  |  | 10% | 0 | 0 | 0
|  | Total Local Auth. Fees |  |  |  | 0 | 0 | 0
| TCD Direct Costs |  |  |  |  | 0 | 0 | 0
|  | Utilities |  |  | 0 |  | 0 | 0
|  | Removals |  |  | 0 |  | 0 | 0
|  | Buildings Office Costs / Charges |  |  | 0 |  | 0 | 0
|  | Demolition |  |  | 0 |  | 0 | 0
|  | (other expenditure types available on Oracle) |  |  | 0 |  | 0 | 0
|  | Sub-total |  |  |  | 0 | 0 | 0
|  | VAT @ |  |  | 23% | 0 | 0 | 0
Task No | TCD Direct Costs | Sub-total |  |  |  | 0 | 0 | 0
|  | Contingency @ |  |  | 10% | 0 | 0 | 0
|  | Total TCD Direct Fees |  |  |  | 0 | 0 | 0
| Other - General |  |  |  |  | 0 | 0 | 0
|  | Loose furniture & Fittings |  |  | 0 |  | 0 | 0
|  | Comms Equipment |  |  | 0 |  | 0 | 0
|  | Landscaping costs |  |  | 0 |  | 0 | 0
|  | Cobbles related works |  |  | 0 |  | 0 | 0
|  | Asbestos |  |  | 0 |  | 0 | 0
|  | Signage |  |  | 0 |  | 0 | 0
|  | Rent |  |  | 0 |  | 0 | 0
|  | Premises Costs |  |  | 0 |  | 0 | 0
|  | Equipment-Rental/Least - Other |  |  | 0 |  | 0 | 0
|  | (other expenditure types available on Oracle) |  |  | 0 |  | 0 | 0
|  | Sub-total |  |  |  | 0 | 0 | 0
|  | VAT @ |  |  | 23% | 0 | 0 | 0
Task No | Other - General | Sub-total |  |  |  | 0 | 0 | 0
|  | Contingency @ |  |  | 10% | 0 | 0 | 0
|  | Total Other - General Fees |  |  |  | 0 | 0 | 0
|  |  |  | Contingency at | 10% | 0 | 0 | 0 | [*Contingency can be set at either worksheet or lower level ]
|  |  |  | Overall Total - New Build |  | 0 | 0 | 0
Task No | Inflation
|  | Total Inflation |  |  | 1% | 0 | 0 | 0
|  |  |  | Overall Total with Inflation - New Build |  | 0 | 0 | 0
FOR INFO
Project Totals (included in above numbers)
|  | Contingency |  |  | 0
|  | VAT TOTAL |  |  | 0
|  | Inflation |  |  | 0

## Costs (Refurb)
Project Costs - Construction (Refurb) Related
|  | Project Name: | Sample Capital Project
|  | Project ID: | YY-123
|  | Oracle Project Number | 12450
|  | EOG Champion: | Update Champion Name
|  | Project Sponsor: | Update Sponsor Name
|  | Project Manager: | Update PM Name
|  | Version No: | V0 1
|  | Issue Date: | DD/MM/YYYY
|  | Refurb (Project Cost) |  |  | Approved Project Spend (Current Baseline) |  | Proposed Spend/ Seeking Approval (Future Baseline) | Total Project Cost(Approved in principle OR Estimate to be validated)
| Task | Expenditure Type |  |  | Total €
| Professional / Design Fees |  |  |  |  | 0 | 0 | 0
|  | Architect |  |  | 0 |  | 0 | 0
|  | PM/QS |  |  | 0 |  | 0 | 0
|  | C&S Engineer |  |  | 0 |  | 0 | 0
|  | M&E Engineer |  |  | 0 |  | 0 | 0
|  | Archaeologist |  |  | 0 |  | 0 | 0
|  | Project Consultants |  |  | 0 |  | 0 | 0
|  | Surveying |  |  | 0 |  | 0 | 0
|  | PSDP Project Supervisor Design stage |  |  | 0 |  | 0 | 0
|  | Assigned Certifier |  |  | 0 |  | 0 | 0
|  | Clerk of Works |  |  | 0 |  | 0 | 0
|  | (other expenditure types available on Oracle) |  |  | 0 |  | 0 | 0
|  | Sub-total |  |  |  | 0 | 0 | 0
|  | VAT @ |  |  | 23% | 0 | 0 | 0
Task No | Professional / Design Fees | Sub-total |  |  |  | 0 | 0 | 0
|  | Contingency @ |  |  | 10% | 0 | 0 | 0
|  | Total Prof/ Design Fees |  |  |  | 0 | 0 | 0
| Works Contract |  |  |  |  | 0 | 0 | 0
|  | Demolition |  |  | 0 |  | 0 | 0
|  | Construction |  |  | 0 |  | 0 | 0
|  | Fit out |  |  | 0 |  | 0 | 0
|  | Civil Works |  |  | 0 |  | 0 | 0
|  | Mechanical Works |  |  | 0 |  | 0 | 0
|  | ESB Charges |  |  | 0 |  | 0 | 0
|  | Electrical Works |  |  | 0 |  | 0 | 0
|  | Irish Rail Charges |  |  | 0 |  | 0 | 0
|  | (other expenditure types available on FIS) |  |  | 0 |  | 0 | 0
|  | Sub-total |  |  |  | 0 | 0 | 0
|  | VAT @ |  |  | 23% | 0 | 0 | 0
Task No | Works Contract | Sub-total |  |  |  | 0 | 0 | 0
|  | Contingency @ |  |  | 10% | 0 | 0 | 0
|  | Total Works Contract |  |  |  | 0 | 0 | 0
| Statutory Fees |  |  |  |  | 0 | 0 | 0
|  | Planning Permission |  |  | 0 |  | 0 | 0
|  | Fire Certificate |  |  | 0 |  | 0 | 0
|  | Disability Access Cert (DAC) |  |  | 0 |  | 0 | 0
|  | (other expenditure types available on FIS) |  |  | 0 |  | 0 | 0
|  | Sub-total |  |  |  | 0 | 0 | 0
|  | VAT @ |  |  | 23% | 0 | 0 | 0
Task No | Statutory Fees | Sub-total |  |  |  | 0 | 0 | 0
|  | Contingency @ |  |  | 10% | 0 | 0 | 0
|  | Total Statutory Fees |  |  |  | 0 | 0 | 0
| Local Authority Charges |  |  |  |  | 0 | 0 | 0
|  | Local Authority Contribution |  |  | 0 |  | 0 | 0
|  | DCC Levy |  |  | 0 |  | 0 | 0
|  | (other expenditure types available on FIS) |  |  | 0 |  | 0 | 0
|  |  |  | Sub-total |  | 0 | 0 | 0
|  | VAT @ |  |  | 23% | 0 | 0 | 0
Task No | Local Authority Charges | Sub-total |  |  |  | 0 | 0 | 0
|  | Contingency @ |  |  | 10% | 0 | 0 | 0
|  | Total Local Auth. Fees |  |  |  | 0 | 0 | 0
| TCD Direct Costs |  |  |  |  | 0 | 0 | 0
|  | Utilities |  |  | 0 |  | 0 | 0
|  | Removals |  |  | 0 |  | 0 | 0
|  | Buildings Office Costs / Charges |  |  | 0 |  | 0 | 0
|  | Demolition |  |  | 0 |  | 0 | 0
|  | (other expenditure types available on FIS) |  |  | 0 |  | 0 | 0
|  | Sub-total |  |  |  | 0 | 0 | 0
|  | VAT @ |  |  | 23% | 0 | 0 | 0
Task No | TCD Direct Costs | Sub-total |  |  |  | 0 | 0 | 0
|  | Contingency @ |  |  | 10% | 0 | 0 | 0
|  | Total TCD Direct Fees |  |  |  | 0 | 0 | 0
| Other - General |  |  |  |  | 0 | 0 | 0
|  | Loose furniture & Fittings |  |  | 0 |  | 0 | 0
|  | Comms Equipment |  |  | 0 |  | 0 | 0
|  | Landscaping costs |  |  | 0 |  | 0 | 0
|  | Cobbles related works |  |  | 0 |  | 0 | 0
|  | Asbestos |  |  | 0 |  | 0 | 0
|  | Signage |  |  | 0 |  | 0 | 0
|  | Rent |  |  | 0 |  | 0 | 0
|  | Premises Costs |  |  | 0 |  | 0 | 0
|  | Equipment-Rental/Least - Other |  |  | 0 |  | 0 | 0
|  | (other expenditure types available on Oracle) |  |  | 0 |  | 0 | 0
|  | Sub-total |  |  | 0 | 0 | 0 | 0
|  | VAT @ |  |  | 23% | 0 | 0 | 0
|  | Sub-total |  |  |  | 0 | 0 | 0
Task No | Other - General | Contingency @ |  |  | 10% | 0 | 0 | 0
|  | Total Other - General Fees |  |  |  | 0 | 0 | 0
|  |  |  | Contingency at | 10% | 0 | 0 | 0 | [*Contingency can be set at either worksheet or lower level ]
|  |  |  | Overall Total - Refurb |  | 0 | 0 | 0
Task No | Inflation
|  | Total Inflation |  |  | 1% | 0 | 0 | 0
|  |  |  | Overall Total with Inflation - Refurb |  | 0 | 0 | 0
FOR INFO
Project Totals (included in above numbers)
|  | Contingency |  |  | 0
|  | VAT TOTAL |  |  | 0
|  | Inflation |  |  | 0

## Costs (Decant)
Project Costs - Construction (Decant) Related
|  | Project Name: | Sample Capital Project
|  | Project ID: | YY-123
|  | Oracle Project Number | 12450
|  | EOG Champion: | Update Champion Name
|  | Project Sponsor: | Update Sponsor Name
|  | Project Manager: | Update PM Name
|  | Version No: | V0 1
|  | Issue Date: | DD/MM/YYYY
|  | Decant (Project Cost) |  |  | Approved Project Spend (Current Baseline) |  | Proposed Spend/ Seeking Approval (Future Baseline) | Total Project Cost (Approved in principle OR Estimate to be validated)
| Task | Expenditure Type |  |  | Total €
| Professional / Design Fees |  |  |  |  | 0 | 0 | 0
|  | Architect |  |  | 0 |  | 0 | 0
|  | PM/QS |  |  | 0 |  | 0 | 0
|  | C&S Engineer |  |  | 0 |  | 0 | 0
|  | M&E Engineer |  |  | 0 |  | 0 | 0
|  | Archaeologist |  |  | 0 |  | 0 | 0
|  | Project Consultants |  |  | 0 |  | 0 | 0
|  | Surveying |  |  | 0 |  | 0 | 0
|  | PSDP Project Supervisor Design stage |  |  | 0 |  | 0 | 0
|  | Assigned Certifier |  |  | 0 |  | 0 | 0
|  | Clerk of Works |  |  | 0 |  | 0 | 0
|  | (other expenditure types available on Oracle) |  |  | 0 |  | 0 | 0
|  | Sub-total |  |  |  | 0 | 0 | 0
|  | VAT @ |  |  | 23% | 0 | 0 | 0
Task No | Professional / Design Fees | Sub-total |  |  |  | 0 | 0 | 0
|  | Contingency @ |  |  | 10% | 0 | 0 | 0
|  | Total Prof/ Design Fees |  |  |  | 0 | 0 | 0
| Works Contract |  |  |  |  | 0 | 0 | 0
|  | Demolition |  |  | 0 |  | 0 | 0
|  | Construction |  |  | 0 |  | 0 | 0
|  | Fit out |  |  | 0 |  | 0 | 0
|  | Civil Works |  |  | 0 |  | 0 | 0
|  | Mechanical Works |  |  | 0 |  | 0 | 0
|  | ESB Charges |  |  | 0 |  | 0 | 0
|  | Electrical Works |  |  | 0 |  | 0 | 0
|  | Irish Rail Charges |  |  | 0 |  | 0 | 0
|  | (other expenditure types available on FIS) |  |  | 0 |  | 0 | 0
|  | Sub-total |  |  |  | 0 | 0 | 0
|  | VAT @ |  |  | 23% | 0 | 0 | 0
Task No | Works Contract | Sub-total |  |  |  | 0 | 0 | 0
|  | Contingency @ |  |  | 10% | 0 | 0 | 0
|  | Total Works Contract |  |  |  | 0 | 0 | 0
| Statutory Fees |  |  |  |  | 0 | 0 | 0
|  | Planning Permission |  |  | 0 |  | 0 | 0
|  | Fire Certificate |  |  | 0 |  | 0 | 0
|  | Disability Access Cert (DAC) |  |  | 0 |  | 0 | 0
|  | (other expenditure types available on FIS) |  |  | 0 |  | 0 | 0
|  | Sub-total |  |  |  | 0 | 0 | 0
|  | VAT @ |  |  | 23% | 0 | 0 | 0
Task No | Statutory Fees | Sub-total |  |  |  | 0 | 0 | 0
|  | Contingency @ |  |  | 10% | 0 | 0 | 0
|  | Total Statutory Fees |  |  |  | 0 | 0 | 0
| Local Authority Charges |  |  |  |  | 0 | 0 | 0
|  | Local Authority Contribution |  |  | 0 |  | 0 | 0
|  | DCC Levy |  |  | 0 |  | 0 | 0
|  | (other expenditure types available on FIS) |  |  | 0 |  | 0 | 0
|  |  |  | Sub-total |  | 0 | 0 | 0
|  | VAT @ |  |  | 23% | 0 | 0 | 0
Task No | Local Authority Charges | Sub-total |  |  |  | 0 | 0 | 0
|  | Contingency @ |  |  | 10% | 0 | 0 | 0
|  | Total Local Auth. Fees |  |  |  | 0 | 0 | 0
| TCD Direct Costs |  |  |  |  | 0 | 0 | 0
|  | Utilities |  |  | 0 |  | 0 | 0
|  | Removals |  |  | 0 |  | 0 | 0
|  | Buildings Office Costs / Charges |  |  | 0 |  | 0 | 0
|  | Demolition |  |  | 0 |  | 0 | 0
|  | (other expenditure types available on FIS) |  |  | 0 |  | 0 | 0
|  | Sub-total |  |  |  | 0 | 0 | 0
|  | VAT @ |  |  | 23% | 0 | 0 | 0
Task No | TCD Direct Costs | Sub-total |  |  |  | 0 | 0 | 0
|  | Contingency @ |  |  | 10% | 0 | 0 | 0
|  | Total TCD Direct Fees |  |  |  | 0 | 0 | 0
| Other - General |  |  |  |  | 0 | 0 | 0
|  | Loose furniture & Fittings |  |  | 0 |  | 0 | 0
|  | Comms Equipment |  |  | 0 |  | 0 | 0
|  | Landscaping costs |  |  | 0 |  | 0 | 0
|  | Cobbles related works |  |  | 0 |  | 0 | 0
|  | Asbestos |  |  | 0 |  | 0 | 0
|  | Signage |  |  | 0 |  | 0 | 0
|  | Rent |  |  | 0 |  | 0 | 0
|  | Premises Costs |  |  | 0 |  | 0 | 0
|  | Equipment-Rental/Least - Other |  |  | 0 |  | 0 | 0
|  | (other expenditure types available on Oracle) |  |  | 0 |  | 0 | 0
|  | Sub-total |  |  |  | 0 | 0 | 0
|  | VAT @ |  |  | 23% | 0 | 0 | 0
Task No | Other - General | Sub-total |  |  |  | 0 | 0 | 0
|  | Contingency @ |  |  | 10% | 0 | 0 | 0
|  | Total Other - General Fees |  |  |  | 0 | 0 | 0
|  |  |  | Contingency at | 10% | 0 | 0 | 0 | [*Contingency can be set at either worksheet or lower level ]
|  |  |  | Overall Total - Decant |  | 0 | 0 | 0
Task No | Inflation
|  | Total Inflation |  |  | 1% | 0 | 0 | 0
|  |  |  | Overall Total with Inflation - Decant |  | 0 | 0 | 0
FOR INFO
Project Totals (included in above numbers)
|  | Contingency |  |  | 0
|  | VAT TOTAL |  |  | 0
|  | Inflation |  |  | 0

## Costs (Misc)
Project Costs - Miscellaneous
|  | Project Name: | Sample Capital Project
|  | Project ID: | YY-123
|  | Oracle Project Number | 12450
|  | EOG Champion: | Update Champion Name
|  | Project Sponsor: | Update Sponsor Name
|  | Project Manager: | Update PM Name
|  | Version No: | V0 1
|  | Issue Date: | DD/MM/YYYY
|  | Miscellaneous (Project Cost) |  |  |  | Approved Project Spend (Current Baseline) |  | Proposed Spend/ Seeking Approval (Future Baseline) | Total Project Cost (Approved in principle OR Estimate to be validated)
| Task | Expenditure Type | Description/Notes | Unit Cost € | Qty | Total € |  | Total € | Total €
| Misc | [5 empty] | 0 | 0 | 0
|  | Non-pay items |  | 0 | 0 | 0 |  | 0 | 0
|  | (other Expense code available on Oracle) |  | 0 | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 |  | 0 | 0
[5 empty] | Sub-total |  | 0 | 0 | 0
[5 empty] | VAT@ | 23% | 0 | 0 | 0
Task No | Misc |  |  |  | Sub-total |  | 0 | 0 | 0
[5 empty] | Contingency at | 10% | 0 | 0 | 0
[5 empty] | Overall Total |  | 0 | 0 | 0
|  | Expenditure Type | Description/Notes | Unit Cost € | Qty | Total €
| Training | [5 empty] | 0 | 0 | 0
|  | Conference/Seminar fees |  | 0 | 0 | 0 |  | 0 | 0
|  | External short courses |  | 0 | 0 | 0 |  | 0 | 0
|  | Staff Training and Development |  | 0 | 0 | 0 |  | 0 | 0
|  | Staff Training Course fees |  | 0 | 0 | 0 |  | 0 | 0
|  | (other Expense code available on Oracle) |  | 0 | 0 | 0 |  | 0 | 0
[5 empty] | Sub-total |  | 0 | 0 | 0
[5 empty] | VAT@ | 23% | 0 | 0 | 0
Task No | Training |  |  |  | Sub-total |  | 0 | 0 | 0
[5 empty] | Contingency at | 10% | 0 | 0 | 0
[5 empty] | Overall Total |  | 0 | 0 | 0
| Travel | Expenditure Type | Description/Notes | Unit Cost € | Qty | Total €
[7 empty] | 0 | 0 | 0
|  | Domestic Subsistence |  | 0 | 0 | 0 |  | 0 | 0
|  | Domestic Taxi travel |  | 0 | 1 | 0 |  | 0 | 0
|  | International Air Travel |  | 0 | 0 | 0 |  | 0 | 0
|  | International Accomodation |  | 0 | 0 | 0 |  | 0 | 0
|  | (other Expense code available on Oracle) |  | 0 | 0 | 0 |  | 0 | 0
[5 empty] | Sub-total |  | 0 | 0 | 0
[5 empty] | VAT@ | 23% | 0 | 0 | 0
Task No | Travel |  |  |  | Sub-total |  | 0 | 0 | 0
[5 empty] | Contingency at | 10% | 0 | 0 | 0
[5 empty] | Overall Total |  | 0 | 0 | 0
[5 empty] | Contingency at | 10% | 0 | 0 | 0 | [*Contingency can be set at either worksheet or lower level ]
[5 empty] | Overall Total: Miscellaneous Project Costs |  | 0 | 0 | 0
FOR INFO
Project Totals (included in above numbers)
|  | Contingency |  |  | 0
|  | VAT TOTAL |  |  | 0
|  | Inflation |  |  | 0

## On-going Costs (Op)
Operational Costs - On-going
Project Name: |  | Sample Capital Project
Project ID: |  | YY-123
Oracle Project Number |  | 12450
EOG Champion: |  | Update Champion Name
Project Sponsor: |  | Update Sponsor Name
Project Manager: |  | Update PM Name
Version No: |  | V0 1
Issue Date: |  | DD/MM/YYYY
Resources (On-going Cost)
YEAR 1 BREAKDOWN
Resources (On-going Cost) |  |  | On-Going Cost
Internal Resources |  | Man Days | Total €
Professor |  | 0 | 0
Associate Professor |  | 0 | 0
Snr Lecturer |  | 0 | 0
Lecturer |  | 0 | 0
Snr Admin 1 |  | 0 | 0
Snr Admin 2 |  | 0 | 0
Snr Admin 3 |  | 0 | 0
Admin 1 |  | 0 | 0
Admin 2 |  | 0 | 0
Admin 3 |  | 0 | 0
Snr Exec Officer1/2 |  | 0 | 0
Executive Officer |  | 0 | 0
Other 1 |  | 0 | 0
Other 2 |  | 0 | 0
Other 3 |  | 0 | 0
| Sub-total | 0 | 0
| Contingency | 20% | 0
|  | Total Internal Resources | 0
External Resources |  | Man-Days | Cost
Steering Committee Chair |  | 0 | 0
Programme Manager |  | 0 | 0
Project Manager |  | 0 | 0
AN Other 1 |  | 0 | 0
AN Other 2 |  | 0 | 0
AN Other 3 |  | 0 | 0
AN Other 4 |  | 0 | 0
AN Other 5 |  | 0 | 0
AN Other 6 |  | 0 | 0
AN Other 7 |  | 0 | 0
AN Other 8 |  | 0 | 0
AN Other 9 |  | 0 | 0
| Sub-total | 0 | 0
| VAT@ | 23% | 0
| Sub-total |  | 0
| Contingency | 20% | 0
|  | Total External Resources | 0
YEAR 1 - 5 BREAKDOWN INTERNAL RESOURCES
Description |  |  |  | Year 1 |  | Year 2 |  | Year 3 |  | Year 4 |  | Year 5 |  | Year 1 - 5 Totals
Professor |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Associate Professor |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Snr Lecturer |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Lecturer |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Snr Admin 1 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Snr Admin 2 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Snr Admin 3 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Admin 1 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Admin 2 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Admin 3 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Snr Exec Officer1/2 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Executive Officer |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Other 1 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Other 2 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Other 3 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | Sub-total |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | Contingency | 10% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | Total Internal Resources | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
YEAR 1 - 5 BREAKDOWN EXTERNAL RESOURCES
Description |  |  |  | Year 1 |  | Year 2 |  | Year 3 |  | Year 4 |  | Year 5 |  | Year 1 - 5 Totals
Steering Committee Chair |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Programme Manager |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Project Manager |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
AN Other 1 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
AN Other 2 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
AN Other 3 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
AN Other 4 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
AN Other 5 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
AN Other 6 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
AN Other 7 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
AN Other 8 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
AN Other 9 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Sub-total |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
VAT on External Resources |  |  | 23% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Sub-total |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | Contingency | 10% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | Total External Resources | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Year 1 - 5 Total Resources |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
IS (On-going Cost)
Description |  |  |  | Year 1 |  | Year 2 |  | Year 3 |  | Year 4 |  | Year 5 |  | Year 1 - 5 Totals
Hardware
Laptops/PC |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Peripherals |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Servers |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Maintenance |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Network Router |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Network Switch |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Wireless Access point |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Data Storage |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Data Cable |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Telephone Switch |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Telephone handsets |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Mobile handsets |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Telephone Cable |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Fibre Optic links install |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Fibre Optic links recurring |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Line Rental |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Storage(SAN) |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Hardware Install |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Hosting Costs |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Load Balancers |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Software | [13 empty] | 0
Software Licenses |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Software recurring |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Software install |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Software monitoring |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Managed Services | [13 empty] | 0
Contract Cost |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Contract Legal |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Contract Procurement |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Hosting |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
IS Prof Services | [13 empty] | 0
|  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Sub-total |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
VAT@ |  |  | 23% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Sub-total |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Contingency |  | 20% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
IS (On-going Cost) - Total |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
CONSTRUCTION (On-going Cost)
New Build (On-going Cost) - Incremental
Description |  |  |  | Year 1 |  | Year 2 |  | Year 3 |  | Year 4 |  | Year 5 |  | Year 1 - 5 Totals
Cleaning |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Telephone |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Electricity |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Water charge |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Security |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Insurance |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Maintenance |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Window Cleaning |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
IS Charges |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Sub-total |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
VAT@ |  |  | 23% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Sub-total |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | Contingency | 10% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
New Build (On-going Cost) - Total |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Refurbishment (On-going Cost) - Incremental
Description |  |  |  | Year 1 |  | Year 2 |  | Year 3 |  | Year 4 |  | Year 5 |  | Year 1 - 5 Totals
Cleaning |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Telephone |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Electricity |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Water charge |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Security |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Insurance |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Maintenance |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Window Cleaning |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Leased Assets |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
IS Charges |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Sub-total |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
VAT@ |  |  | 23% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Sub-total |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | Contingency | 20% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Refurbishment (On-going Cost) - Total |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Decant (On-going Cost) - Decremental
|  |  |  | Year 1 |  | Year 2 |  | Year 3 |  | Year 4 |  | Year 5 |  | Year 1 - 5 Totals
Cleaning |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Telephone |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Electricity |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Water charge |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Security |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Insurance |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Maintenance |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Window Cleaning |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Leased Assets (Photocopiers) |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
IS Charges |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Sub-total |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
VAT@ |  |  | 23% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Sub-total |  |  |  | 0.23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Contingency |  | 20% | 0.046 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0.046
Decant (On-going Cost) - Total |  |  |  | 0.276 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0.046
|  |  |  | Year 1 |  | Year 2 |  | Year 3 |  | Year 4 |  | Year 5 |  | Year 1 - 5 Totals
Overall On-going Operational Costs |  |  |  | 0.276 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0.276
FOR INFO
Project Totals (included in above numbers)
Contingency | [7 empty] | 0.046
VAT TOTAL | [7 empty] | 0
Inflation | [7 empty] | 0