[image: image1.png]



Five-Year Operating Plan

First Annual Update – June 2016

I C A N N | Five-Year Operating Plan First Annual Update | Draft for Public Comment March 2016

Introduction

[image: image2.jpg]Objectives Goals
Core foundational strategies Desired deliverables to meet
upon which goals are based . organization-wide objectives ’

Portfolios Projects
Cross-functional work Atemporary endeavor that
undertaken in support of . has a defined beginning and
goals to fulfill core end and a specific set of

deliverables and services deliverables.




ICANN developed a multiyear planning framework based on extensive input from the ICANN Community during the development of its Strategic Plan. The framework includes the following three elements:

I. Five-Year Strategic Plan FY16-FY201 – To be updated every five years or earlier if appropriate. It includes a vision and mission, strategic objectives, goals, Key Success Factors, and strategic risks. ICANN’s Board adopted the current Strategic Plan on 16 October 2014.

AI. Five-Year Operating Plan FY16-FY20 – To be updated each year. It includes:

· a five-year planning calendar
· strategic goals with corresponding Key Performance Indicators
· dependencies
· five-year phasing
· a list of portfolios, and
· a five-year financial model
BI. Annual Operating Plan and Budget – Developed from the ICANN Five-Year Operating Plan and annual community input. It includes portfolios of activities that support the achievement of the goals and objectives with corresponding Key Performance Indicators, dependencies, budgets, and projects.

This is the first annual update to the Five-Year Operating Plan, which was adopted by the Board on 28 April 2015.

ICANN acknowledges that stakeholder bandwidth and support remains a key dependency to meeting the goals outlined in ICANN’s portfolio of work..

[image: image3.jpg]PLANNING CALENDAR
STRATEGIC PLAN

Consult LS ®
Develop
Consult @0 0
o [¢]

Approve
5-YR OPERATING PLAN”

Develop ° [
Consult [ ()

Update )
Approve (€]
1-YR OPERATING PLAN & BUDGET !

Consult @0
Develop 1-Yr Operating °
Plan & Budget

Consult @0

Approve o [e] [e] [¢] [¢] [©)

Y14 FY'15 FY'16 P17 Y18 FY'19 P20

stakeholder  Board staff




1 ICANN’s financial/fiscal year runs from 1 July to 30 June of the following year. It is described as “FY” followed by the last two digits of the calendar year during which the fiscal year closes
[image: image4.jpg]5YOP Update

FY17 OP&B
Develop

Public
Comment

Review
comments

Report

Adopt

FY16 Q1

FY16 Q2 FY16 Q3

We are here

FY16 Q4



[image: image5.jpg]5-YEAR OPERATING PLAN UPDATE AND FY17 OPERATING PLAN & BUDGET ROADMAP (FOR INTERNAL USE ONLY)

GLs to discuss guidance on 4 Sep for 5-YOPU & FY17-OP&B, then align with B.0.s of each GL team =
===

Community consultations on 5-YOPU and FY17-OP&B process

finalized 5-YOPU and FY17-OP&B process to BFC/ Board to obtain approval for publishing to Stakeholders
30 SEP -6 NOV.

5-YOPU and FY17-OP&B kick-off - Ops Staff and GLs to define high level revenue and expense (run rate) targets
GLs/B.0.s to consult Stakeholders on the potential updates to 5-YOPU and the draft scenarios & cost estimates for FY17-OP&B

At ICANN 54 - Stakeholder consultation on prelim 5-YOPU and FY17 revenue/expense/Initiative assumptions

Gls E Staff to communicate final scenarios and targets to B.0.5

8.0.5 to draft V1 of 5-YO! d FY17-OP&B (in Workfront, WORD & EXCEL) & review with GLs
12 DEC - 8 JAN

B.0.s to refine 5-YOPU and FY17-OP&B based on GL feedback and submit V2 to Ops Staff for consolidation & review

GLs to review V2 of total ICANN 5-YOPU and FY17-OP&S8,

Staff including reconciliation of the two and identify adjustments to be made
ST UETE T
B.0.5 to refine V2 based on GL feedback, submit V3 to Ops Staff for consolidation
Stakeholders Ops Staff to draft 5-YOPU and FY17-OP&B documents
Board ——

BFC/ Board to approve draft 5-YOPU and FY17-OP&8 doc's for public posting
Ops Staff to post draft 5-YOPU and FY-17-OP&8

Public comment period, Stakeholder calls,
public comment responses published

Staff to refine 5-YOPU and

FY17-OP&B ir public comments

BFC to approve FY17-OP&B changes





	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	2


[image: image6.jpg]Stakeholder
Journey

This was introduced to get
more volunteer stakeholders
more actively engaged in ICANN
policy makingand develop a
diverse pipeline of volunteer
talent

Itis reflected in:

- Thewording forthe phasing
and

- Introduction of the
ICANN.ORG development
dependencyin 1.2

IANA Stewardship
Transition
This is reflected in:

Anewimplementation portfolio for
GDDIn2.1

New dependencies for GSEin 1.1
and1.3and GEin4.1

AnewKPI for MSSlin 5.2 and

New phasingin 1.3,4.1.

WHOIS

This work is addressed in three ways:

Aresearch portfolio forOCTOin 2.2
Animplementation portfolio for GDD
in2.3and

An AoC Review in the phasing for MSS|
in5.2




Table of Contents

	Introduction
	2
	

	Reference and Notes
	5
	

	Planning – Community Roles and Responsibilities
	6
	

	Operating Plan – Strategic Goal Level
	12


Summary of Changes ________________________________________________________________________________________________ 12

Strategic Objective 1 – Evolve and Further Globalize ICANN _________________________________________________________________ 16

Strategic Goal 1.1 Further Globalize and Regionalize ICANN Functions __________________________________________________________ 16

Strategic Goal 1.2 Bring ICANN to the world by creating a balanced and proactive approach to regional engagement with stakeholders _____ 18

Strategic Goal 1.3 Evolve Policy Development and Governance Processes, Structures and Meetings to be More Accountable, Inclusive, Efficient, Effective and Responsive _______________________________________________________________________________________________ 20

Strategic Objective 2 – Support a Healthy, Stable and Resilient Unique Identifier Ecosystem _______________________________________ 22

Strategic Goal 2.1 Foster and Coordinate a Healthy, Secure, Stable, and Resilient Identifier Ecosystem ________________________________ 22

Strategic Goal 2.2 Proactively Plan for Changes in the Use of Unique Identifiers, and Develop Technology Roadmaps to Help Guide ICANN Activities ____________________________________________________________________________________________________________ 24

Strategic Goal 2.3 Support the Evolution of the Domain Name Marketplace to be Robust, Stable and Trusted __________________________ 26

Strategic Objective 3 – Advance Organizational, Technological and Operational Excellence _______________________________________ 28

Strategic Goal 3.1 Ensure ICANN’s Long-Term Financial Accountability, Stability and Sustainability __________________________________ 28

Strategic Goal 3.2 Ensure Structured Coordination of ICANN’s Technical Resources ________________________________________________ 30

Strategic Goal 3.3 Advance Organizational, Technological and Operational Excellence _____________________________________________ 32

Strategic Objective 4 – Promote ICANN’s Role and Multistakeholder Approach __________________________________________________ 34

Strategic Goal 4.1 Encourage Engagement with the Existing Internet Governance Ecosystem at National, Regional and Global Levels _______ 34

Strategic Goal 4.2 Clarify the Role of Governments in ICANN and Work with Them to Strengthen their Commitment to Supporting the Global Internet Ecosystem ____________________________________________________________________________________________________ 36

[image: image7.jpg]ICANN OPERATIONS

2
z
=
-
<
=
o
-

Multi-year
PROJECTS




[image: image8.png]@ One World, One Internet

ICANN




	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	3


Strategic Goal 4.3 Participate in the Evolution of a Global, Trusted, Inclusive Multistakeholder Internet Governance Ecosystem that Addresses Internet Issues ________________________________________________________________________________________________________ 37

Strategic Goal 4.4 Promote Role Clarity and Establish Mechanisms to Increase Trust Within the Ecosystem Rooted in the Public Interest ____ 39

Strategic Objective Develop and Implement a Global Public Interest Framework Bounded by ICANN’s Mission ________________________ 41

Strategic Goal 5.1 Act as a Steward of the Public Interest _____________________________________________________________________ 41

Strategic Goal 5.2 Develop and Implement a Global Public Interest Framework Bounded by ICANN’s Mission ___________________________ 43

Strategic Goal 5.3 Empower Current and New Stakeholders to Fully Participate in ICANN Activities ___________________________________ 46

	Five-Year Financial Model
	47


Introduction _______________________________________________________________________________________________________ 47

1 – Approach to Five-Year Financial Model _______________________________________________________________________________ 48

2 – Principles ______________________________________________________________________________________________________ 49

3 – Assumptions ____________________________________________________________________________________________________ 50

4 – Contents of the Financial Model ____________________________________________________________________________________ 51


	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	4



Reference and Notes


1. The ICANN Community encompasses ICANN’s stakeholders—including its Supporting Organizations, Advisory Committees, and Nominating Committee—the Board of Directors, and staff. So, ICANN’s multistakeholder model defines its community.

2. ICANN Portfolio Management System. Below is a high-level composite of ICANN's work structure.


3. Definition of terms can be found in the ICANN online glossary.
4. Key Performance Indicators (KPIs) will be updated over time as they are refined. Typically, KPIs start with one of the following:

$ = Value of

# = Number of

% = Percentage of

5. Portfolios throughout the Five-Year Operating Plan may contain projects that contribute to other Portfolio(s) within the same Goal or another Goals.

6. Relative resource prioritization is a key dependency that applies to all goals.

7. Goal-level risks are described in the Five-Year Strategic Plan. ICANN staff systematically reviews and manages risks on an ongoing basis..


	I C A N N | Five-Year Operating Plan First Annual Update | Draft for Public Comment March 2016
	5


Planning – Community Roles and Responsibilities


The planning process is part of the bottom-up multistakeholder process and requires the collaborative effort of the whole ICANN Community. This includes its Supporting Organizations, Advisory Committees, and Nominating Committee as well as its Board and staff.

This calendar depicts the involvement of the ICANN Community and the timeline of the planning process.


[1] The next Strategic Planning effort for FY21 – FY25 is scheduled to begin in FY19.

[2] The Five-Year Operating Plan is updated each year to reflect actual performance and recent events. Changes are made for the remaining years in the planning cycle. The current Five-Year Operating Plan calendar is available on page 11.


	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	6


[3] The Five-Year Strategic Plan for FY16–FY20 is linked to the Five-Year Operating Plan, which informs the Fiscal-Year Operating Plan and Budget.

The charts below describe how everyone would (or could) be involved in the planning process and include frequency of activities, supporting elements and roles and responsibilities.


	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	7


Strategic Plan Process

	
	
	
	
	
	Community Roles and Responsibilities

	
	Strategic
	Frequency
	Supporting Elements3
	Staff
	
	Board
	Stakeholders

	
	Plan2
	
	
	
	
	
	

	1.
	Consult
	Every 5
	Strategic Plan Kick-off
	
	
	Consult on key challenges and
	Consult on key challenges and

	
	
	years4
	 Accomplishments from
	
	
	opportunities and areas of
	opportunities and areas of

	
	
	
	last planning cycle
	
	
	strategic importance
	strategic importance

	
	
	
	 Environmental analysis,
	
	
	
	

	
	
	
	including SWOT5
	
	
	
	

	2.
	Develop
	Every 5
	Draft Strategic Plan:
	Develop
	
	
	

	
	
	years
	 Accomplishments from
	
	
	
	

	
	
	
	last planning cycle
	
	
	
	

	
	
	
	 Environmental analysis
	
	
	
	

	
	
	
	 Vision, Mission
	
	
	
	

	
	
	
	 Areas of strategic
	
	
	
	

	
	
	
	importance
	
	
	
	

	3.
	Consult
	Every 5
	Public comment and other
	
	
	Consult
	Consult

	
	
	years
	engagements
	
	
	
	

	4.
	Approve
	Every 5
	Final Strategic Plan
	Update based on
	
	Approve
	

	
	
	years
	 same as above, plus:
	consultations and long-
	
	
	

	
	
	
	 Strategic Goals
	term planning work
	
	
	

	
	
	
	 Key Success Factors
	
	
	
	

	
	
	
	(outcomes)
	
	
	
	

	
	
	
	 Strategic Risks
	
	
	
	



2 Five-Year Strategic Plan for FY16–FY20 is linked to the Five-Year Operating Plan, which informs the Fiscal-Year Operating Plan and Budget. The next Strategic Planning effort for FY21 – FY25 is scheduled to begin in FY19.
3 All documents are posted and publically available.
4 The next planning cycle is scheduled to begin in FY19 to allow sufficient time for key planning steps.
5 Environmental analysis is an important aspect of strategic planning. It includes assessment of strengths and weaknesses (internally focused) and opportunities and threats (externally focused).

	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	8


Five-Year Operating Plan Process

	
	
	
	
	Community Roles and Responsibilities

	
	Five-Year
	Frequency
	Supporting Elements7
	Staff
	Board
	Stakeholders

	Operating Plan6
	
	
	
	
	

	1.
	Develop
	Every 5
	 Planning Calendar
	Develop
	
	

	
	
	years
	 Five-Year Financial Model
	
	
	

	
	
	
	 Draft Summary of Five-Year Operating Plan
	
	
	

	
	
	
	 Strategic goals with corresponding Key Performance Indicators,
	
	
	

	
	
	
	dependencies, five-year phasing, and list of portfolios
	
	
	

	2. Consult
	Every 5
	Public comment and other engagements
	
	Consult
	Consult

	
	
	years
	
	
	
	

	3.
	Update
	Each year
	Annual Reporting
	Update based on
	
	

	
	
	
	 Performance as compared to
	consultations
	
	

	
	
	
	 plan for prior Fiscal Year, starting with FY16
	
	
	

	
	
	
	 Explanation of variances
	
	
	

	
	
	
	 Required changes to Five-Year Operating Plan if warranted
	
	
	

	4.
	Approve
	Each year
	Final Summary Five-Year Operating Plan
	
	Approve
	



6 The Five-Year Strategic Plan for FY16–FY20 is linked to the Five-Year Operating Plan, which informs the Fiscal Year Operating Plan and Budget. The Five-Year Operating Plan is updated each year to reflect actual performance and recent events. Changes are made for the remaining years in the planning cycle.
7 The Five-Year Operating Plan will be updated, when appropriate, for the rest of the cycle. No changes to the Five-Year Strategic Plan for FY16 – FY20 are anticipated. They would be made if a critically significant event or development is observed.

	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	9


Fiscal-Year Operating Plan and Budget Process

	
	
	
	
	Community Roles and Responsibilities
	

	
	Fiscal-Year Operating
	Frequency
	Supporting Elements9
	Staff
	Board
	Stakeholders

	
	Plan and Budget8
	
	
	
	
	

	1.
	Consult
	Each year
	 Draft Revenue Model
	
	Consult
	Consult

	
	
	
	 Draft list of Initiatives and
	
	
	

	
	
	
	Engagements
	
	
	

	2.
	Develop
	Each year
	 Draft Fiscal-Year
	Develop/update based on Five-Year Operating Plan,
	
	

	
	
	
	Operating Plan
	consultations and recent history of events
	
	

	
	
	
	 Draft Fiscal-Year Budget
	
	
	

	3.
	Consult
	Each year
	Public comment and other
	
	Consult
	Consult

	
	
	
	engagements
	
	
	

	4.
	Approve
	Each year
	Final Fiscal-Year Operating
	Update based on consultations
	Approve
	

	
	
	
	Plan and Budget
	
	
	



8 Strategic Plan for FY16–FY20 is linked to the Five-Year Operating Plan, which informs the Fiscal-Year Operating Plan and Budget.
9 All documents are posted and publically available

	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	10


ICANN Fiscal-Year Operating Plan Current Calendar


	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	11


Operating Plan – Strategic Goal Level


Summary of Changes

This is the first update to ICANN’s Five-Year Operating Plan and Financial Model. ICANN updates this document each year to take account of what has been achieved and review and refine the planned future work based on what has already been delivered and the changing environment.

The table below provides a high-level overview of changes from the initial Five-Year Operating Plan and Budget. Changes have been made both as a result of ICANN analysis and review and also the Public Comment process. This table describes changes to portfolios, Key Performance Indicators, dependencies, and year-by-year phasing of work.

In each goal section, a status update box has been added to note the work completed and planned to be accomplished during FY16.


	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	12



	
	Goal
	Change Type
	Change Summary
	
	

	
	Number
	
	
	
	

	
	All
	Dependency removed -
	Moved to Reference and Notes and made implicit for all ICANN work
	
	

	
	
	resource prioritization
	
	
	

	
	1.1
	KPI reworded
	Based on work to refine and improve the quality of the measurement
	
	

	
	1.1
	Dependency updated
	IANA Stewardship Transition added as an activity that could change focus
	
	

	
	1.1
	Portfolio renamed
	1.1.2 renamed to “GSE Executive team coordination and administration”
	
	

	
	1.2
	KPI reworded
	Based on work to refine and improve the quality of the measurement
	
	

	
	1.2
	New dependency
	ICANN.ORG development added as a dependency
	
	

	
	1.2
	Phasing – new phrasing
	Introduction of “Stakeholder Journey” in FY17-FY20 activities based on FY16 work with the
	
	

	
	
	
	community
	
	

	
	1.3
	Portfolio moved from here
	Structural Organizational Reviews portfolio moved to 5.2 as there are strong similarities with
	
	

	
	
	
	the AoC Reviews work
	
	

	
	1.3
	New dependency
	Impact of the IANA Stewardship Transition on the Multistakeholder Model
	
	

	
	1.3
	Phasing – new items
	FY17 work now includes work related to the IANA Stewardship Transition and subsequent
	
	

	
	
	
	years include work related to implementing the outcomes of Organizational Reviews
	
	

	
	1.3
	Phasing – items deleted
	Reviews work removed as it is transferred to 5.2
	
	

	
	1.3
	Phasing – new activity
	IANA Stewardship Transition implementation added as an FY17 activity
	
	

	
	1.3
	Phasing – new activity
	Support for At-Large multiyear planning added to FY17 onwards
	
	

	
	2.1
	Portfolio closed
	Root Zone Update System Enhancement portfolio removed as the work is now complete
	
	

	
	2.1
	Portfolio moved from here
	Root Server System Evolution and Security, Stability, and Resiliency of Internet Identifiers
	
	

	
	
	
	moved to 2.2
	
	

	
	2.1
	New portfolios
	Portfolios for GDD Operations and Product Management moved from 2.3 and new portfolios
	
	

	
	
	
	for Global Customer Support and IANA Functions Stewardship Transition Implementation
	
	

	
	2.1
	Portfolio moved here
	GDD registrant engagement work moved here from 2.3
	
	

	
	2.1
	Phasing - changes
	Reports on work originally planned for 4.4 and moved during FY16
	
	

	
	2.1
	Phasing - changes
	FY17 work restructured to take account of portfolio changes
	
	

	
	2.2
	Portfolios moved to here
	Root Server System Evolution and Security, Stability, and Resiliency of Internet Identifiers
	
	

	
	
	
	moved from 2.1
	
	

	
	2.2
	Portfolio removed
	Root Server System Evolution portfolio removed from FY17
	
	

	
	2.2
	KPI reworded
	KPI text refined to focus on ICANN’s contribution to the health of identifiers
	
	

	
	
	
	
	
	

	
	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	13


	
	2.2
	Dependency removed
	Budget related dependency is now moved to Reference and Notes, bullet #6
	
	

	
	2.2
	Phasing - changes
	FY17-20 updated to refer to multiple roadmaps instead of just one
	
	

	
	2.3
	Portfolio removed
	Public Safety Registrations portfolio removed as the work is now being performed in the
	
	

	
	
	
	community
	
	

	
	2.3
	Portfolios moved
	Contractual Compliance portfolios moved to 4.4 so there is separation from GDD
	
	

	
	2.3
	Portfolio renamed
	Registrant Interest Representation portfolio renamed as GDD Registrant Engagement and
	
	

	
	
	
	Support
	
	

	
	2.3
	New portfolios
	New portfolios for WHOIS Coordination and Implementation, Domain Name Services, Next
	
	

	
	
	
	gTLD Round Planning, Universal Acceptance, Registry Services, and Registrar Services
	
	

	
	2.3
	KPIs restructured
	Technical Reputation Index renamed Domain Name Marketplace Health Index and Service
	
	

	
	
	
	Level Targets KPI now solely in 2.1
	
	

	
	2.3
	Phasing - changes
	FY17-FY20 work restructured to take account of portfolio changes
	
	

	
	2.3
	Phasing - changes
	FY17 work related to WHOIS and RDAP added
	
	

	
	3.1
	Portfolio renamed
	Business Excellence and Business Intelligence renamed to Organizational Excellence and
	
	

	
	
	
	Intelligence
	
	

	
	3.1
	Dependency removed
	Budget related dependency is now moved to Reference and Notes, bullet #6
	
	

	
	3.1
	Phasing
	FY17 work updated to include implementation of improvements
	
	

	
	3.1
	Phasing
	FY19-20 updated to refer to the next strategic planning cycle
	
	

	
	3.2
	Portfolios restructured
	New Cybersecurity portfolio. Infrastructure and Maintenance portfolios merged. Root Systems
	
	

	
	
	
	Operations portfolio removed.
	
	

	
	3.2
	Dependency removed
	Budget related dependency is now moved to Reference and Notes, bullet #6
	
	

	
	3.2
	Phasing – changes
	IANA functions measurements work updated to reflect anticipated Post-Transition IANA
	
	

	
	3.2
	KPI reworded
	KPI scope clarified
	
	

	
	3.3
	Portfolio removed
	Business Excellence portfolio removed as this work is now entirely within 3.1
	
	

	
	3.3
	Dependency removed
	Budget related dependency is now moved to Reference and Notes, bullet #6
	
	

	
	3.3
	Phasing
	Updated wording in third bullet to clarify relationship with 5.3
	
	

	
	3.3
	Phasing - changes
	Business Excellence related portfolio removed as it now sits in 3.1
	
	

	
	4.1
	Portfolio removed
	Build Stronger Partnerships with Internet Organizations and Initiatives portfolio removed as
	
	

	
	
	
	project work was moved to other portfolios
	
	

	
	4.1
	KPI changes
	Updated KPI on touch points. KPI on agreements restructured to look at trend data.
	
	

	
	4.1
	Dependencies removed
	Dependencies related to past events removed
	
	

	
	4.1
	Phasing changes
	FY17 work descriptions updated to focus on activities rather than measurements
	
	

	
	4.2
	Dependencies removed
	Dependencies related to past events removed
	
	

	
	
	
	
	
	

	
	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	14


	4.2
	Phasing changes
	FY17-FY20 work reworded to refer to “trust agreements” and focus on activities rather than

	
	
	measurements

	4.3
	KPI reworded
	KPI now refers to participation in the ecosystem

	4.3
	Dependencies removed
	Dependencies related to past events and agreement language, which has been completed,

	
	
	removed

	4.3
	Dependency reworded
	Change in the word order for the MoU language dependency

	4.3
	Phasing changes
	FY17 work restructured, wording changes and FY18 “best practices” work removed

	4.4
	Portfolios restructured
	Work previously in 2.3 now in 4.4 with portfolios renamed and restructured

	4.4
	Dependency reworded
	External dependency explicitly acknowledges “ability to reach consensus, changing laws and

	
	
	regulations”

	4.4
	Phasing changes
	Two FY16 work items were moved to 5.2 mid-year, #2 went to 5.2 and #3 went to 2.1

	4.4
	Phasing changes
	FY17 now refers to “accuracy rates” in measurement to quantify trust, benchmarking and

	
	
	reporting work, implicitly absorbing the long range progress work.

	5.1
	KPI reworded
	Small changes to KPI wording

	5.1
	Dependency updated
	Small change to wording: “public interest” expanded to “public interest understandings”

	5.2
	Portfolios restructured
	Organizational Reviews portfolio moved from 1.3 and all AoC Reviews merged to a single

	
	
	portfolio

	5.2
	New portfolio
	Portfolio for Evolution of Organizational Governance Mechanisms in support of the

	
	
	Multistakeholder Model

	5.2
	New KPI
	New KPI on fulfilling commitments through Reviews

	5.2
	New KPI
	New KPI on IANA Stewardship Transition

	5.2
	Phasing - changes
	Reports on work originally planned for 4.4 and moved mid-year

	5.2
	Phasing - changes
	FY17-FY20 work restructured to take account of portfolio changes

	5.3
	Portfolios restructured
	Portfolios restructured based on work areas instead of outcomes

	5.3
	KPI reworded
	KPI wording improved

	5.3
	Dependency removed
	Budget related dependency is now moved to Reference and Notes, bullet #6

	5.3
	Phasing changes
	Minor changes to wording for FY17 work



	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	15


Strategic Objective 1 – Evolve and Further Globalize ICANN Strategic Goal 1.1 Further Globalize and Regionalize ICANN Functions

Portfolios

1. Raising Stakeholder Awareness of ICANN Worldwide

2. GSE Executive team coordination and administration

3. Language Services

Key Performance Indicators (Metrics)

· Meeting Services Scorecard, engagement with community in major languages and scripts
· % of ICANN organizational functions globalized and available by region
· Stakeholder Engagement scorecard (previously an index) now belongs in Strategic Goal 1.2 beginning with FY17
Dependencies

1. Communications needs may increase or Global Stakeholder Engagement (GSE) focus may shift depending on status of the IANA Stewardship Transition. It also might shift if there is another round of new gTLDs during the Five-Year Operating Plan

Phasing

	
	FY16
	Planned
	Intended Status at the end of FY16
	

	
	
	1.
	Integrate global and regional communications
	1.
	Regional newsletters streamlined and uniform across regions. We are also capturing
	

	
	
	
	strategies.
	
	foreign language social media statistics across the regions in one place.
	

	
	
	2.
	Comprehensive regional engagement plans
	2.
	Communications strategies for the regions now in place
	

	
	
	
	and strategies covering most ICANN regions.
	3.
	Community-driven Engagement Strategies in place for five regions and all
	

	
	
	3.
	Further distribute ICANN functions at Hub
	
	regions/functional areas have yearly work plans. We have started tracking with
	

	
	
	
	Offices.
	
	regional scorecards.
	

	
	
	
	
	4.
	Several departments have added staff and distributed resources to hub and
	

	
	
	
	
	
	engagement offices (for example – Global Customer Service Center in Istanbul hub)
	

	
	
	
	
	
	
	
	

	
	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	
	16
	


FY17
1.
Sustain implementation of communications strategies

2. Wide awareness raising and educational effort if supporting ICANN with another new gTLD round

3. Examine how hubs and engagement offices are supporting ICANN globalization

2. Conduct mapping of community to regional engagement; implement recommendations resulting from examination of ICANN Hub Office and engagement site support of ICANN globalization

FY19
1. Implement integrated global and regional communications strategies in support of ICANN strategies 2. Implement improvements for GSE based on community mapping in FY18

2. Survey community on GSE engagement and support of community engagement at high level

3. Implement improvements on review of GSE web, customer relationship management tools from 2019


	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	17


Strategic Goal 1.2 Bring ICANN to the world by creating a balanced and proactive approach to regional engagement with stakeholders

Portfolios

1. Engage Stakeholders Regionally

2. Broadcast and Engage with Global Stakeholders

Key Performance Indicators (Metrics)

· Global/regional engagement scorecard (this metric includes the regional Engagement Strategies and Fiscal Year work plans for each of the regions and each regional scorecard is balanced against the ICANN objectives)
· Digital services metrics (to be phased in during FY17)
Dependencies

1. Retaining expertise to support ICANN's efforts across the hubs and regions in multiple languages for a diverse range of stakeholders

2. Digital services metrics depend on the ongoing development of ICANN.ORG

Phasing


	FY16
	Planned
	Intended Status at the end of FY16

	
	1.
	Implement Global Stakeholder Engagement (GSE) web tools for
	1.
	Internal collaboration tool adopted and used by all GSE

	
	
	supporting Stakeholder Engagement activities at regional and local
	
	regional/functional teams to support Stakeholder Engagement.

	
	
	level.
	2.
	Several community-driven regional Engagement Strategies

	
	2.
	Examine effectiveness of regional strategies launched in FY13-FY14.
	
	were updated (Africa, LAC and Middle East)

	FY17
	1.
	Examine # of community participants in ICANN programs to enable measurement of the Stakeholder Journey


2. Complete first cycle regional Engagement Strategies and regional plan FY18 1. Conduct mapping of Stakeholder Journey to regional engagement

2. Enhance online ICANN meeting hubs to contribute to and increase engagement during meetings

3. Review effectiveness of ICANN web tools for supporting globalization and regionalization for community


	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	18


FY19
1.
Implement improvements for GSE based on Stakeholder Journey mapping in FY18

2. Increase participation of active participants across technical community, civil society, governments and business stakeholders FY20 1. ICANN participants cover all regions

2. Achieve participation from all sectors of community and support improvement of Stakeholder Journey in contributions to ICANN.

3. Survey community on engagement with, and support of, community at high level

4. Implement improvements on review of GSE web, customer relationship management tools from FY19


	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	19


Strategic Goal 1.3 Evolve Policy Development and Governance Processes, Structures and Meetings to be More Accountable, Inclusive, Efficient, Effective and Responsive

Portfolios

1. Support Policy Development, Policy Related and Advisory Activities

2. Reinforce Stakeholder Effectiveness, Collaboration and Communication Capabilities

3. Evolving Multistakeholder Model

Key Performance Indicators (Metrics)

· # of participants in the policy development and governance processes by type, status and location
· Quality-of-service index (for example, “active” participants in policy development calls and meetings; # of publication subscribers/readers in "print" and on web; # of public comments submitted in ICANN Public Forums; Twitter Subscribers and Tweets; and so on)
Dependencies

1. Making available IT/Online Community Services a part of ensuring that our global stakeholders can access improved tools

2. Dedicated communications strategies and services are required to ensure successful outcomes

3. The legal team may be needed to advise in the policy and decision making process.

4. Final plans to transition stewardship of the IANA functions and the outcomes of work to enhance ICANN’s accountability may impact the Multistakeholder Model

Phasing

	
	FY16
	Planned
	Intended Status at the end of FY16
	

	
	
	1.
	Complete a comprehensive inventory of all
	1.  2, and 3, In FY16, the staff is updating an initial inventory of resources and capabilities
	

	
	
	
	resources and capabilities that ICANN
	available to the community. This inventory helps both the community and staff to assess
	

	
	
	
	provides to the current stakeholder
	the delivery of those capabilities and to analyze and evaluate how those resources are
	

	
	
	
	communities.
	balanced. A Community Engagement and Policy staff team is working to
	

	
	
	2.
	Complete a comprehensive assessment of
	comprehensively align policy development activities of support and engagement
	

	
	
	
	delivery of all resources and capabilities
	matters.
	

	
	
	
	that are provided to the stakeholders.
	
	
	

	
	
	
	
	
	
	

	
	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	20
	


	3.
	Analyze, evaluate and plan for how to
	4.  The staff continues to collaborate with community leaders in the non-contracted house

	
	balance resource abilities and capabilities
	
	of the GNSO to offer tailored secretariat support services to those groups. More

	
	among stakeholders.
	
	experience is needed to confirm the value of a permanent resource, but assessments so

	4.
	Evolve Generic Names Supporting
	
	far confirm the value of this support to community groups.

	
	Organization (GNSO) Secretariat Pilot
	5.  Implementation of the ATRT2 Recommendation 7 started in January 2105. In December

	
	program into permanent support status.
	
	2015, staff published a report assessing the value of the implementation effort. It

	5.
	Assess implementation of Accountability
	
	concluded that the process and operational enhancements to the public comment forum

	
	and Transparency Review Team 2 (ATRT2)
	
	infrastructure provided substantial value and should be continued. The report is on the

	
	Recommendation 7, in preparation for
	
	Community Wiki.

	
	ATRT3
	
	
	

	FY17  1.
	Complete assessment of language services capabilities for proficiency, accuracy consistency and reliability


2. Review ICANN’s Language Services Policy

3. Conduct final Supporting Organization and Advisory Committee special request process

4. Assess effectiveness and value of telecoms vendors

5. Assess implementation of relevant accountability provisions resulting from final plans to transition stewardship of the IANA functions

6. Begin multiyear planning for At-Large general assemblies and summits

FY18
1.
Complete a comprehensive assessment of delivery of all resources and capabilities that are provided to the stakeholders (every two years)

2. Analyze, evaluate and plan for how to balance resource abilities and capabilities among stakeholders (every two years)

3. Assess progress towards five-year goal – toward wide use of improved tools and mechanisms for global participation and representation, including the use of remote participation to engage stakeholders from emerging regions

4. Implement improvements resulting from ICANN Reviews as part of continuous accountability enhancement work

5. Support one or more At-Large general assemblies

	FY19  1.  Implement improvements resulting from ICANN Reviews as part of continuous accountability enhancement work

	2.
	Support one or more At-Large general assemblies

	FY20  1.
	Stakeholders and staff use improved tools and mechanisms for global participation and representation to collaborate. This includes the use

	
	of remote participation to engage stakeholders from emerging regions

	2.
	Implement improvements resulting from ICANN Reviews as part of continuous accountability enhancement work

	3.
	Support an At-Large summit



	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	21


Strategic Objective 2 – Support a Healthy, Stable and Resilient Unique Identifier Ecosystem

Strategic Goal 2.1 Foster and Coordinate a Healthy, Secure, Stable, and Resilient Identifier Ecosystem

Portfolios

1. IANA Department Operations

2. IANA System Enhancements

3. Advice Registry Management

4. Global Domains Division (GDD) Operations

5. Global Customer Support

6. Product Management

7. Implementation of IANA Functions Stewardship Transition and Enhancing ICANN Accountability

Key Performance Indicators (Metrics)

· % of Service Level Targets met across multiple departments including but not limited to IANA, GDD Operations, and Global Customer Support departments
Dependencies

1.
IT department support

Phasing


FY16
Planned

1. Develop and achieve community approval of all domain name system (DNS)/Unique identifiers health metrics.



Intended Status at the end of FY16

1. Adopted Key Performance Indicators for IANA functions (names, numbers, and protocol parameters) after public consultation in 2013 and post monthly reports on measurements for each of the KPIs. Development is underway to collect measurements defined by CWG for Service Level Expectations in processing root zone and root zone data changes.


	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	22


	2.
	Develop and achieve community
	2.
	Moved to Goal 2.2

	
	approval of the stability and resiliency
	3.
	Moved to Goal 2.3

	
	exercises specified.
	4.
	Moved to Goal 2.2

	3.
	Develop and achieve community
	5.
	Moved to goal 2.2

	
	approval of the ICANN legitimacy survey
	
	

	
	designed.
	In FY16, we deployed a Global Customer Support team to provide 24x5 coverage for inquiries

	4.
	Collaborate with community to reduce
	from contracted parties, registrants and the community at large. Both the Global Support and

	
	gap of IPv6 and DNSSEC deployment by
	GDD Operations teams delivered service according to published service level targets. Service

	
	5% year over year (Year over Year).
	delivery against those targets was published on a monthly basis.


5. Develop and achieve community approval of the Identifier registration data access/update system requirements specified

2. Monitor and manage service delivery against targets, identify opportunities for improvement and efficiency

3. Implement process improvements for increased operational efficiency and customer satisfaction

4. Implement system enhancements for increased operational efficiency and effectiveness

FY18
1.
All DNS/Unique identifiers health metrics v1 results reviewed and improvements to metrics and functions are recommended

2. Stability and resiliency exercises repeated, gap analysis performed, and necessary improvements made

3. Collaborate with community to reduce gap of IPv6 and DNSSEC deployment by 5% year over year

4. Identifier registration data access/update system requirements revised and approved by the community FY19 1. All DNS/Unique identifiers health metrics v2 implemented and baselines posted

2. Stability and resiliency exercises repeated, gap analysis performed, and necessary improvements made

3. 4 Collaborate with community to reduce gap of IPv6 and DNSSEC deployment by 5% year over year

4. 5. Revised identifier registration data access/update system implemented and beta tested by the community

FY20
1.
All DNS/Unique identifiers health functions recommendations implemented and v2 metrics are reviewed for progress

2. Stability and resiliency exercises repeated, gap analysis performed, and necessary improvements made

3. Collaborate with community to reduce gap of IPv6 and DNSSEC deployment by 5% year over year.

4. Revised identifier registration data access/update system put into production


	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	23


Strategic Goal 2.2 Proactively Plan for Changes in the Use of Unique Identifiers, and Develop Technology Roadmaps to Help Guide ICANN Activities

Portfolios

1. WHOIS Core Function/Service and Improvements

2. Identifier Evolution

3. Technical Experts Group

4. Security, Stability, and Resiliency of Internet Identifiers

Key Performance Indicators (Metrics)

· Identifier Technologies Health Index will measure ICANN's contribution to health of identifiers in both the ICANN and broader Internet communities
Phasing

	
	FY16
	Planned
	Intended Status at the end of FY16
	

	
	
	1.
	Department fully staffed.
	1.
	Office of the Chief Technology Officer department researchers and administrative staff hired,
	

	
	
	2.
	Draft technology roadmap
	
	although more staff needed.
	

	
	
	
	developed.
	2.
	Roadmap for evolution for Root Zone Management System has been drafted based on
	

	
	
	3.
	Relationships with
	
	requirements from the CWG. Implementation of the roadmap has begun with milestones set
	

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	
	
	protocol/technology development
	
	for delivery of SLE measurements and removal of the NTIA authorization module. Project to
	

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	
	
	organizations enhanced.
	
	draft technology roadmap initiated.
	

	
	
	4.
	Ratio of registered domain names to
	3.
	Relationship with IETF, 

 HYPERLINK "https://www.dns-oarc.net/" DNS-OARC, and other technology development organizations
	

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	
	
	active IP addresses base lined.
	
	enhanced by increased participation. ISOC invited ICANN staff to teach joint sessions on
	

	
	
	
	
	
	
	
	
	
	
	

	
	
	5.
	Ratio of registered domain names to
	
	ICANN-related topics to policy attendees (fellows) to IETF. Relationships with RIRs still being
	

	
	
	
	Internet users regionally and globally
	
	developed.
	
	
	

	
	
	
	base lined
	4.
	Ratios being established.
	

	
	
	
	
	5.
	Ratios being established.
	

	
	FY17
	1.  Additional technology roadmaps approved by community
	

	
	
	2.
	At least five identifier technology-related white papers are published
	

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	24
	


3.
Demonstrate growth in ratios in developing regions

FY18
1.
Implementation of year one of technology roadmaps done

2. At least two more identifier technology-related white papers are published

3. Demonstrate growth in ratios in developing regions

2. Additional identifier technology-related white papers are published

3. Demonstrate growth in ratios in developing regions

2. Implementation of year three of technology roadmap done

3. Additional identifier technology-related white papers are published

4. Demonstrate growth in ratios in developing region


	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	25


Strategic Goal 2.3 Support the Evolution of the Domain Name Marketplace to be Robust, Stable and Trusted

Portfolios

1.
Registration Directory Services Analysis and Development GDD Registrant Engagement and Support

2.
Placeholder

3.
GDD Technical Services

4.
Internationalized Domain Names

5.
New gTLD Program

6.
Domain Name Services

7.
Next gTLD Round Planning

8.
Universal Acceptance

9.
Registry Services

10. Registrar Services

Key Performance Indicators (Metrics)

 Domain Name Marketplace Health Index

Dependencies

1.
IT resources availability and prioritization

Phasing

	
	FY16
	Planned
	
	Intended Status at the end of FY16
	

	
	
	1.
	Multistakeholder satisfaction survey
	
	1.
	Development of customer satisfaction on track for completion by end of FY16. Baseline to
	

	
	
	
	baseline completed.
	
	
	include results from Global Support and IANA ratings.
	

	
	
	2.
	Baseline of Domain Name industry
	
	2.
	Development of Domain Name Marketplace Health Index on target. Baseline to be
	

	
	
	
	segments defined
	
	
	completed by end of FY16
	

	
	FY17
	In FY17, we will continue to support the development of a robust, stable and trusted domain marketplace by:
	

	
	
	1.
	Ongoing development and monitoring of the Domain Name Marketplace Health Index
	

	
	
	2.
	Improve customer satisfaction by reducing survey gap by at least 10% year over year
	

	
	
	
	
	
	
	
	
	

	
	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	
	26
	


3. Show stable healthy year over year growth in the domain name industry
4. Finish the current round of the New gTLD Program and a committed plan toward the start of a subsequent round year over year
5. Conclude policy work on WHOIS improvements and the Next Generation Registry Directory Services
6. Develop implementation plans for new WHOIS policies or Next Generation Registration Directory Services as appropriate

2. Improve customer satisfaction by reducing survey gap by at least 10% year over year
3. Show stable healthy year over year growth in the domain name industry
2. Improve customer satisfaction by reducing survey gap by at least 10% year over year
3. Show stable healthy year over year growth in the domain name industry
2. Improve customer satisfaction by reducing survey gap by at least 10% year over year
3. Show stable healthy year over year growth in the domain name industry

	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	27


Strategic Objective 3 – Advance Organizational,

Technological and Operational Excellence

Strategic Goal 3.1 Ensure ICANN’s Long-Term Financial

Accountability, Stability and Sustainability

Portfolios

1. Strategic and Operating Planning

2. Organizational Excellence and Intelligence

3. Finance and Procurement

4. Enterprise Risk Management

5. Support Operations

Key Performance Indicators (Metrics)

· Financial accountability, stability and sustainability indices (composite index of ratios and metrics) including but not limited to:
· Actual to budget Reserve Fund balance and utilization, and financial performance metrics
· Internal control performance indicators
· % project completion indices (with emphasis on major projects)
· % comparisons of actual to target succession plan readiness
· % comparisons of actual to target enterprise risk management roadmap achievements
· On-time delivery index of the ICANN Planning process (includes: ICANN Five-Year Strategic Plan for FY16-FY20, Five-Year Operating Plan, Fiscal-Year Operating Plan and Budget, achievements and progress reporting)
Dependencies

1. IT system implementation roadmap enabling efficiency and advancement in analytics, metric tracking/reporting/review, process improvement implementation, and mitigation assessment and implementation

2. Community bandwidth and focus to provide direction and feedback


	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	28


Phasing

	FY16
	Planned
	Intended Status at the end of FY16

	
	1.
	Refine the FY15 model – financial framework, roadmap, targets and
	1.
	Developed roadmap to complete Five-Year Operating Plan

	
	
	metrics - with target to achieve within three years the foundation for
	
	update and FY17 Operating Plan and Budget

	
	
	Key Success Factors (KSFs) (outcome) supported by adequate system
	2.
	Launched and to complete FY16 total organization continuous

	
	
	advancement in place.
	
	improvement internal assessment based on EFQM

	
	2.
	Align with budget availability and IT system implementation
	
	organization excellence framework, and identify gaps and

	
	
	roadmap.
	
	develop improvement roadmap

	
	3.
	Review and obtain approval by Board, staff and stakeholders
	3.
	Launched Dashboard reporting beta, progressed to Version 1

	
	
	
	
	and continue on advancements on metrics, contents and

	
	
	
	
	systems

	
	
	
	4.
	Continue to conduct and refine quarterly stakeholders calls

	
	
	
	
	increasing accountability and transparency

	
	
	
	5.
	Completed FY15 financial reporting and annual audit with no

	
	
	
	
	deficiencies noted

	
	
	
	6.
	Concluded enterprise risk management maturity assessment

	
	
	
	
	and working on deriving maturity targets to refine risk

	
	
	
	
	management discipline.

	
	
	
	7.
	Selected ERP system and begin to launch implementation

	FY17
	1.  Achieve financial roadmap targets
	
	

	
	2.
	Review operational processes and implement improvements
	
	

	
	3.
	Modify roadmap as needed
	
	

	FY18
	1.  Achieve the foundation for Key Success Factors (outcome) supported by adequate system advancement in place

	
	2.
	Continue to improve and achieve elevated target performance levels as per roadmap

	
	3.
	Modify roadmap as needed
	
	

	FY19
	1.  Continue to improve and achieve elevated target performance levels as per roadmap

	
	2.
	Modify roadmap as needed
	
	

	
	3.
	Initiate strategic planning process
	
	

	FY20
	1.  Complete roadmap as planned
	
	

	
	2.
	Reassess and plan for future years
	
	

	
	3.
	Conclude strategic planning process and develop Five-Year Operating Plan
	



	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	29


Strategic Goal 3.2 Ensure Structured Coordination of ICANN’s Technical Resources

Portfolios

1. Cybersecurity Hardening and Control

2. IT Infrastructure and Service Scaling

3. Root Systems Operations

Key Performance Indicators (Metrics)

· % of global IT infrastructure uptime (scaling from 99.9% in FY 2016 to 99.999 % in 2020 for ICANN community engagement and information web services)
Phasing

	
	FY16
	Planned
	Intended Status at the end of FY16
	

	
	
	1.
	Develop and socialize a suite of uptime metrics for IT Services.
	1.
	Metrics for all areas of IT have been developed and socialized
	

	
	
	2.
	Define, divide and socialize IT services into a three-tier
	
	internally
	

	
	
	
	classification.
	2.
	All IT services were classified and this has been socialized
	

	
	
	3.
	Define, socialize and adopt a baseline Lean Process Capability
	3.
	The process capabilities were documented and reviewed
	

	
	
	
	metric for IANA functions.
	4.
	A baseline for availability was established
	

	
	
	4.
	Measure and record a baseline for the IANA functions.
	5.
	A project delivery metric has been developed and socialized. This is
	

	
	
	5.
	Define, develop and socialize a metric for on-time, on-budget IT
	
	published monthly internally
	

	
	
	
	projects delivery.
	
	
	
	

	
	FY17
	1.  Measure and record a baseline for IT Services uptime by tier
	
	
	
	

	
	
	2.
	Reflective of Post-Transition IANA, measure and record a new baseline of capabilities and costs for IANA functions year over year
	

	
	
	3.
	Report on metric for on-time, on-budget IT projects delivery
	
	
	
	

	
	FY18
	1.  Drive IT Services uptime for Tier 1 towards 99.99% availability
	
	
	
	

	
	
	2.
	Measure and compare metric for the IANA functions against baseline for year over year improvement
	

	
	
	3.
	Report on metric for on-time, on-budget IT projects delivery, driving to improvement year over year on performance
	

	
	FY19
	1.  Drive IT Services uptime for Tier 1 to 99.999% availability
	
	
	
	

	
	
	2.
	Drive uptime for Tier 2 towards 99.99% availability
	
	
	
	

	
	
	
	
	
	
	
	

	
	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	
	30
	


3. Measure and compare metric for the IANA functions against baseline for year over year improvement

4. Report on metric for on-time, on-budget IT projects delivery, driving to improvement year over year on performance FY20 1. Maintain IT Services uptime for Tier 1 to 99.999% availability

2. Maintain uptime for Tier 2 to 99.99% availability or better

3. Drive uptime for Tier 3 towards 99.9% availability or better

4. Measure and compare metric for the IANA functions against baseline for year over year improvement

5. Report on metric for on-time, on-budget IT project delivery, driving to improvement year over year on performance


	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	31


Strategic Goal 3.3 Advance Organizational, Technological and Operational Excellence

Portfolios

1. Talent Management

2. ICANN Technical University

Key Performance Indicators (Metrics)

· % of achievement in comparison to best practice benchmark metrics of global diverse culture, and knowledge levels of Board, staff and stakeholders
· % of completion - actual to target implementation milestones of global development programs to advance the knowledge and expertise of staff, Board and stakeholders
Dependencies

1. IT system implementation roadmap enabling efficiency and advancement in analytics, metric tracking/reporting/review, process improvement implementation, and mitigation assessment and implementation

2. Community bandwidth and focus to provide direction and feedback

Phasing

	
	FY16
	Planned
	Intended Status at the end of FY16
	

	
	
	1.
	Build on the FY15 achievements related to this goal
	1.
	Board Operations continues to improve the Board’s training program and is
	

	
	
	
	KSFs (outcome).
	
	on track with plan and Chairman’s direction
	

	
	
	2.
	Complete first internal European Foundation for
	2.
	On target with staff talent management roadmap implementation. This
	

	
	
	
	Quality Management (EFQM) radar evaluation &
	
	includes the revamp of the new hire orientation program, continuous
	

	
	
	
	assessment of key areas of focus, identify gaps and
	
	improvement of staff communication, elevating quality of management
	

	
	
	
	developed mitigation/ improvement roadmap.
	
	development and training, and the development of succession plan
	

	
	
	3.
	Identify benchmark organizations and derive key
	3.
	Supported, and collaborated where needed, on cross-functional efforts to
	

	
	
	
	benchmarking metrics
	
	“Empower current and new stakeholders to fully participate in ICANN
	

	
	
	
	
	
	activities” as part of the stakeholder-endorsed Strategic Goal 5.3. These
	

	
	
	
	
	
	programs include:
	

	
	
	
	
	
	•   The development and implementation of an internship framework
	

	
	
	
	
	
	
	
	

	
	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	
	32
	


· Development and Public Responsibility Department (DPRD) programs that address participation needs such as NextGen@ICANN, the Fellowship Program, the Newcomer Program, and the Community Onboarding Mentor Pilot Program

· the relaunch of an improved Online Learning Platform (OLP) ICANN Learn

· Supporting academic outreach efforts by the community and the Global Stakeholder Engagement (GSE) team.

2. Identify gaps and implement mitigation FY18 1. Identify gaps and continue to improve

2. Advance on applying systems to refine measurements

3. Collaborate with stakeholders on progress evaluation and improvements FY19 1. Continue evaluation against best practice and advance

FY20  1.  Continue evaluation against best practice and advance


	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	33


Strategic Objective 4 – Promote ICANN’s Role and Multistakeholder Approach

Strategic Goal 4.1 Encourage Engagement with the Existing Internet Governance Ecosystem at National, Regional and Global Levels

Portfolios

1.
Coordination of ICANN Participation in Internet Governance (IG)

Key Performance Indicators (Metrics)

· This is a compound index measuring the # of touch points between ICANN and national governments, regional governmental entities, and Intergovernmental organizations, and international organizations.
· Measurement of quarterly engagement comparing to previous fiscal year quarterly engagement to show trend data
Dependencies

1. Successful NTIA IANA functions Stewardship Transition

2. Revision of MoUs to more clearly recognize ICANN’s role

Phasing

	
	FY16
	Planned
	Intended Status at the end of FY16
	

	
	
	1.
	Increase % participation rates from documented
	1.
	WSIS outcome and participation were successfully concluded which led to
	

	
	
	
	
	
	
	
	
	
	
	
	

	
	
	
	baseline established in FY15.
	
	continued follow-up in CSTD, 

 HYPERLINK "http://www.itu.int/" ITU and other forums
	

	
	
	
	
	
	
	
	
	
	
	

	
	
	2.
	Increase # of demonstration projects in the regions
	2.
	Active participation at IGFs at the global regional and national levels
	

	
	
	
	reflecting collaboration with organizations active in
	3.
	Continued support for the multistakeholder model in global IG forums
	

	
	
	
	the IG ecosystem
	
	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	
	
	
	
	
	

	
	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	
	34
	


4. Active engagement to support a positive outcome in the OECD Ministerial meeting

5. Increased total participation rates for FY16 compared to the baseline established in FY15. In addition participation data was collated to compare FY activity by quarters to show trends

6. Joint projects were added as key regional metrics

FY17
1.
Continuation of FY16 activities to increase % participation rates documented as baseline established in FY16

2. Continuation of FY16 activities to support the development of global acceptance by stakeholders of the IANA Stewardship Transition FY18 1. Third year review of strategy and mapping exercises

	
	2.
	Evolution of global and regional work plans to reflect outcome of review

	FY19
	1.
	Increase from baseline participation rates documented as baseline established in FY18

	FY20
	1.
	Strong fully structured working relationships with organizations and entities active in the IG following a successful IANA Stewardship

	
	
	Transition



	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	35


Strategic Goal 4.2 Clarify the Role of Governments in ICANN and Work with Them to Strengthen their Commitment to Supporting the Global Internet Ecosystem

Portfolios

1. Support GAC Engagement

2. Engagement with Governments and Intergovernmental Organizations

Key Performance Indicators (Metrics)

· Increase # of GAC members (level of actual active participation and level of representation at ICANN meetings)
Phasing

	
	FY16
	Planned
	Intended Status at the end of FY16
	

	
	
	1.
	Updated Government Engagement Strategy is reflected in the work plan for
	1.
	Effective regional webinars were held increasing
	

	
	
	
	each region.
	
	regional awareness and participation
	

	
	
	2.
	Baseline determination completed to map existing entities within the
	2.
	Active engagement to work toward successful ICANN
	

	
	
	
	Internet governance (IG) ecosystem and their posture toward ICANN and the
	
	55 High-Level Government Meeting and African
	

	
	
	
	multistakeholder model
	
	Ministerial meeting
	

	
	
	
	
	3.
	Active engagement to work toward GAC support for the
	

	
	
	
	
	
	IANA Stewardship Transition process
	

	
	
	
	
	4.
	Effective participation in GAC and ICANN work
	

	
	FY17
	1.  Increase the # of governmental entities actively participating in ICANN
	
	
	
	

	
	FY18
	1.  Third year review of strategy
	
	
	
	

	
	
	2.
	Revise global and regional work plans to reflect outcome of strategy review
	
	
	
	

	
	FY19
	1.  Increase # of governmental entities actively participating in ICANN
	
	
	
	

	
	FY20
	1.
	Enhanced relationships with governments that encourage them to support the adoption of the multistakeholder IG approaches on national,
	

	
	
	
	regional and global levels
	
	
	
	

	
	
	
	
	
	
	
	

	
	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	
	36
	


Strategic Goal 4.3 Participate in the Evolution of a Global, Trusted, Inclusive Multistakeholder Internet Governance Ecosystem that Addresses Internet Issues

Portfolios

1.
Support Internet Governance (IG) Ecosystem Advancement

Key Performance Indicators (Metrics)

· Quarterly trend data showing cumulative participation in IG Ecosystem Evolution
Phasing


	FY16  Planned
	Intended Status at the end of FY16

	1.
	Increase in # of cooperation agreements with respective Internet
	1.
	Worked to develop and finalize cooperation agreements with

	
	organizations and regional and national multistakeholder IG
	
	Intergovernmental Organizations/International Organizations (such

	
	approaches over baseline established in FY 2015.
	
	as GSMA, 

 HYPERLINK "http://www.cto.int/" CTO, 

 HYPERLINK "http://www.osce.org/" OSCE and others)

	
	
	
	
	
	
	
	
	
	

	2.
	Increase # national IG multistakeholder approaches over
	2.
	Increased participation of governments and IGOs in ICANN work

	
	baseline established in 2015
	3.
	Promoted multistakeholder model for IG at national and regional

	
	
	
	levels


FY17
1. Identification of potential best practices among national and regional multistakeholder IG approaches. These are to be highlighted in outreach work for further adoption of multistakeholder model IG governance mechanisms

2. Establish a baseline measurement of projects and work reflecting collaboration with respective Internet organizations FY18 1. Year three review of the goals and delivery strategy for those goals

2. Evolution and improvement of global engagement work plan based on completed review

3. Continuation of FY17 projects and work to reflect collaboration with respective Internet organizations FY19 1. Revise global strategy and goals reflected in regional strategies and work plans

2. Increase in # of projects and work reflecting collaboration with respective Internet organizations over baseline established in FY18 FY20 1. ICANN involvement, consistent with its mission and within its mandate, in a full implementation of a distributed trusted fully inclusive

multistakeholder IG ecosystem


	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	37


2.
Perception that technical and non-technical IG issues are successfully addressed using multistakeholder model


	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	38


Strategic Goal 4.4 Promote Role Clarity and Establish Mechanisms to Increase Trust Within the Ecosystem Rooted in the Public Interest

Portfolios

1. Contractual Compliance Functions

2. Contractual Compliance Initiatives and Improvements

3. Contractual Compliance and Safeguards

4. Strategic Initiatives

Key Performance Indicators (Metrics)

· Develop a framework that generates institutional confidence in ICANN and builds trust over time
· Assemble and refine Accountability-related KPIs as a means of measuring ICANN's accountability
· Implement means of measuring long-range progress
Dependencies

1. External: ICANN Community, ability to reach consensus, changing laws and regulations

2. Internal: Policy, GSE, Communications and Legal (in the context of the Board)

3. Touch points with Board, staff and stakeholders

Phasing

	
	FY16
	Planned
	Intended Status at the end of FY16
	

	
	
	1.
	Assess current practices and documentation.
	FY16 is on target –
	

	
	
	2.
	Assemble and refine Accountability-related KPIs, in line with Accountability Framework
	1.
	On-going effort for continuous
	

	
	
	
	proposed by One World Trust in response to recommendations of Accountability and
	
	improvement
	

	
	
	
	Transparency Review Teams to implement a means of measuring ICANN's accountability.
	2.
	This work moved to 5.2 mid-year and is
	

	
	
	3.
	Identify and propose best practices.
	
	reported there
	

	
	
	4.
	Propose measurements and benchmarks
	
	
	
	

	
	
	
	
	
	
	
	

	
	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	
	39
	


3.
This work moved to 2.1 mid-year and is

reported there

4.
Measurement metrics for contractual

compliance service level targets are

included in the ICANN Beta KPI Dashboard
FY17
1.
Implement agreed-upon plan and practices

2. Implement ongoing measurement, benchmarking and reporting of accuracy rates FY18 1. Implement agreed-upon plan and practices.

2. Implement ongoing measurement, benchmarking and reporting FY19 1. Implement agreed-upon plan and practices.

2. Implement ongoing measurement, benchmarking and reporting FY20 1. Assess and adjust plan and practices as needed


	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	40


Strategic Objective Develop and Implement a Global Public Interest Framework Bounded by ICANN’s Mission Strategic Goal 5.1 Act as a Steward of the Public Interest

Portfolios

1. Legal Advisory Function

2. Public Interest Decision Making

3. Legal Internal Support

4. Support ICANN Board

Key Performance Indicators (Metrics)

· # of ICANN decisions and advice (Board, staff and stakeholders) that are rationalized based on common consensus-based definition(s) and understandings of public interest within ICANN's remit
Dependencies

1. Community, Board and staff involvement in the dialogue regarding the public interest understandings, definitions and framework to hold as an ICANN standard

Phasing

	
	FY16
	Planned
	Intended Status at the end of FY16
	

	
	
	1.
	Create Framework for ICANN Supporting Organizations
	1.  A High Interest Session on this topic was held at ICANN55 where discussions
	

	
	
	
	and Advisory Committee to assist them in assessing
	took place on next steps and planning. Detailed progress on this
	

	
	
	
	how their actions are aligned to the public interest
	collaborative dialogue- along with details on developments to date are on
	

	
	
	
	
	the Community Wiki
	

	
	
	
	
	
	
	
	

	
	FY17
	1.
	Measure and baseline the % of actions by ICANN in decision making and how rationales are including the public interest assessments as part
	

	
	
	
	of decision making
	
	
	
	
	

	
	FY18
	1.
	Increase from the baseline the % actions by ICANN in decision making and how rationales are including the public interest assessments as
	

	
	
	
	part of decision making
	
	
	
	
	

	
	
	
	
	
	
	
	
	

	
	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	41
	


	FY19
	1.
	Continue to increase on the % actions by ICANN in decision making and how rationales are including the public interest assessments as part

	
	
	of decision making

	FY20
	1.
	Reach goal of all material actions including a consideration of decision making and how rationales are including the public interest

	
	
	assessments as part of decision making



	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	42


Strategic Goal 5.2 Develop and Implement a Global Public Interest Framework Bounded by ICANN’s Mission

Portfolios

1. Affirmation of Commitments (AoC) Reviews

2. Organizational Reviews

3. Conflicts of Interest and Organizational Ethics

4. IANA Functions Stewardship Transition and Enhancing ICANN Accountability

5. Accountability and Transparency Mechanisms

Key Performance Indicators (Metrics)

· Public interest framework index (for example, ICANN’s Documentary Information Disclosure Policy and correspondence posted on time, compliance with the conflict of interest policy and compliance with the Board Code of Conduct)
· Develop a framework for increasing trust in ICANN’s fulfilment of its commitments through efficient and effective Reviews:
· Broad and diverse participation in ICANN Reviews
· Community engagement in using ICANN Reviews to drive continuous improvement in accountability, transparency and organizational effectiveness (such as community participation in public comments pertaining to Reviews and other forms of engagement)
· Transmission of all Board approved proposals from the ICG and CCWG-Accountability to NTIA
· Completion of all community proposals that meet NTIA criteria for the IANA transfer for Chartering Organization approval
Dependencies

1. Stakeholder Community, Board and staff agreement on a clear, actionable Accountability and Ethical Framework

2. Final plans to transition stewardship of the IANA functions and the outcomes of work to enhance ICANN’s accountability

3. Community participation in conducting Reviews

Phasing


FY16
Planned

1. Create and publish revised Accountability and Ethical Framework and develop baseline



Intended Status at the end of FY16

1. Work supporting the IANA Stewardship Transition continued with the IANA Stewardship Transition Coordination Group finalizing its proposal on schedule and

	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	43


	metrics to measure to demonstrate impact on
	
	
	the CCWG-Accountability sought consensus from its six Chartering Organizations

	
	
	
	
	
	
	
	
	
	
	
	
	

	organization
	
	
	with delivery of final proposal in February 2016

	
	2.
	
	ATRT2 implementation is proceeding on-schedule with quarterly updates published

	
	
	
	
	
	
	
	
	
	
	
	

	
	3.
	
	The Competition, Consumer Trust and Consumer Choice Review started on

	
	
	
	
	
	
	
	
	
	
	

	
	
	
	schedule.

	
	4.
	
	Community feedback has been respected and the Second Security, Stability and

	
	
	
	Resiliency of the DNS Review and the Second WHOIS Policy Review have been

	
	
	
	delayed

	
	5.
	The independent examiner report on the review of the Generic Names Supporting

	
	
	Organization was published and the review of the At-Large Organization is

	
	
	
	scheduled
	
	

	
	6.
	
	The reviews process has been enhanced based on best practices and improved

	
	
	
	reviews web pages have been published
	
	

	
	
	
	
	
	
	
	
	
	
	
	
	


FY17
1. Measure against the baseline metrics developed in FY16 and show increase in acceptance and impact of Accountability and Ethical Framework

2. Continue to review for improvements and enhancements. Measure and baseline the % of actions by ICANN in decision making and how rationales are including the public interest assessments as part of decision making

3. Complete the first AoC Review on Competition, Consumer Choice and Trust in new gTLDs

4. Launch and conduct the second AoC Review on Security, Stability and Resiliency

5. Launch and conduct the second AoC Review on WHOIS

6. Preparation for and launch the third AoC Review on Accountability and Transparency

FY18
1.
Meet increased metrics developed in FY16-FY17 and show increase in acceptance and impact of Accountability and Ethical Framework

2. Continue to review for improvements and enhancements

3. Implementation of the recommendations from the first AoC Review on Competition, Consumer Choice and Trust in new gTLDs

4. Conclude the second AoC Review on Security, Stability and Resiliency and plan implementation

5. Conclude the second AoC Review on WHOIS and plan implementation

6. Conduct the third AoC Review on Accountability and Transparency

FY19
1.
Meet increased metrics developed in FY16-FY18 and show increase in acceptance and impact of Accountability and Ethical Framework

2. Continue to review for improvements and enhancements

3. Implement recommendations from the second AoC Review on Security, Stability and Resiliency in New gTLDs

4. Implement recommendations from the second AoC Review on WHOIS

5. Plan implementation of the recommendations from the third AoC Review on Accountability and Transparency

FY20
1.
Reach five-year goals in acceptance and impact on organization set out in the Accountability and Ethical Framework.

2.
Continue to review for improvements and enhancements.


	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	44


3. Continue to review for improvements and enhancements.

4. Plan for second AoC Review on Competition, Consumer Choice and Trust in New gTLDs

5. Complete implementation of the recommendations from the second AoC Review on Security, Stability and Resiliency and plan for third Review

6. Complete implementation of the recommendations from the second AoC Review on WHOIS and plan for third Review

7. Implement the recommendations from the third AoC Review on Accountability and Transparency


	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	45


Strategic Goal 5.3 Empower Current and New Stakeholders to Fully Participate in ICANN Activities

Portfolios

1. Development and Public Responsibility Tools

2. Development and Public Responsibility Programs

3. Development and Public Responsibility Collaborations

4. Development and Public Responsibility New Program Development

Key Performance Indicators (Metrics)

· Level of stakeholder participation for development and public responsibility programs, tools, and collaborations
Dependencies

1. Clear understanding of the definition in relation to ICANN's mandate and mission

2. Engagement and support both with and for other ICANN internal departments

3. SO/AC buy-in and support for approach

4. Working relationships with Governments in developing and underdeveloped regions as key points of access.

Phasing

	
	FY16
	Planned
	Intended Status at the end of FY16
	

	
	
	1.
	Establish engagement baseline for under-
	1.  Development and Public Responsibility Department efforts to address current critical
	

	
	
	
	represented countries and communities and
	multistakeholder gaps can be tracked through the ICANN Beta Dashboard. Additional
	

	
	
	
	
	
	
	
	

	
	
	
	other underrepresented groups and address
	work is underway to increase understanding of current gaps and underrepresented
	

	
	
	
	critical engagement gaps
	groups, along with potential remedies in the form of programs, tools, or collaborative
	

	
	
	
	
	efforts in the greater ecosystem.
	

	
	FY17
	1.  Increase access, knowledge, and capability of priority groups through a fully operational Development and Public Responsibility
	

	
	
	
	Department
	
	
	
	
	

	
	FY18
	1.
	Continue improvement of increased access, knowledge, and capability of target audiences and consolidation of regional strategies
	

	
	FY19
	1.
	Continue improvement of increased access, knowledge, and capability of target audiences
	

	
	FY20
	1.
	Assess efforts and impact on target audiences and plan for evolution of operations to continue to address evolving community needs
	

	
	
	
	
	
	
	
	
	

	
	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	46
	


Five-Year Financial Model


Introduction

The financial model provides a long-term perspective on ICANN’s high-level revenue and expenses trends. It is a forward looking perspective based on assumptions.

The benefit of building such a model is to raise strategic questions, suggest possible trends, and to provide a tool for management to plan organizational activities. As events and activities unfold, adjustments may become necessary and will naturally impact the five-year financial model.

The financial model is not:

· the result of a detailed budget-like exercise
· a public position statement
· fixed for a long time

	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	47


1 – Approach to Five-Year Financial Model


	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	48


2 – Principles

The five-year financial model should:

· Reflect a conservative approach.
· Assume that incoming funds should equal or exceed outgoing funds.
· Assume that the level of outgoing funds reflects the costs of the resources required to achieve the Strategic and Operating Plans.
· Include an assumption on maintaining the appropriate level of cash reserve.
· Be developed and communicated with clear assumptions.
· Provide the sensitivity of fluctuations (for example, scenarios).
· Define aggregates (envelopes), not itemized components.

	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	49


3 – Assumptions

Revenue Assumptions

· Market and historical trends impacting the evolution of registration volumes, separately for historical top-level domains (previous to the current round) and for new TLDs
· For new TLDs, registration volumes exceeding the billing threshold for the registry transaction-based fees
· Number of active TLDs (delegated in the root), including resulting from a subsequent generic TLD (gTLD) application round
· Fee per unit
· Contributions received from country code TLD (ccTLD) operators and Regional Internet Registries
· Sponsorship contribution received
· Revenues for the New gTLD Program: driven by the duration, the annual amount of application expenses, and the level of application refunds
Expenses Assumptions

· Year-on-year variation of operating and capital expenses
· Non-cash expenses (for example, depreciation of fixed assets)
· Special/large, multi-year projects and related expenses, for example
· IANA Stewardship Transition
· infrastructure expansion or improvements
· Expenses for the New gTLD Program divided between evaluation costs, historical development costs repayment, and hard-to-predict costs (including risks).
· Evaluation costs to be split into direct costs by phase (initial evaluation, extended evaluation, other phases), and overhead (new gTLD team costs, administration costs, and costs allocation).

	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	50


4 – Contents of the Financial Model

ICANN’s planning process is moving towards a multiyear planning approach. The first steps towards this are a review of planning for multiyear projects.

This step will inform the development of the financial model.

Financial statements

· Statement of Operations (“P and L”)
· Statement of Cash flows
Assumptions, including scenarios

Risks and Opportunities


	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	51



	I C A N N | Five-Year Operating Plan First Annual Update | June 2016
	52



Headquarters

Los Angeles, CA, USA

12025 Waterfront Drive

Suite 300

Los Angeles, CA

90094-2536

USA

Phone: +1 310 301 5800

Fax: +1 310 823 8649

Hub Offices

Istanbul, Turkey

Hakki Yeten Cad. Selenium

Plaza No:10/C K:10

34349 Fulya, Besiktas,

Istanbul

Turkey

Phone: +90 212 999 6222

Singapore

South Beach Tower

38 Beach Road

Unit 04-11

Singapore 189767

Phone: +65 6816 1288

Fax: +65 6822 6212



Engagement Offices Beijing, China

For Global Support Inquiry Contact:

+86 10 5904 5561

Brussels, Belgium

6 Rond Point Schuman

Bt. 1

Brussels B-1040 Belgium

Phone: +32 2 894 7400

Geneva, Switzerland Regus Center Rue du Rhone 14

1204 Geneva

Switzerland

Phone: +41 22 819 1844

Fax: +41 22 819 1900



Montevideo, Uruguay La Casa de Internet de Latinoamérica y el Caribe Rambla República de México 6125

Montevideo, 11400

Uruguay

Phone: +598 2604 2222 ext 5701

Fax: +598 2604 2222 ext 4112

Seoul, Korea

17F IT Venture Tower West Wing

135, Jungdae-ro, Songpa-gu,

Seoul, 138-950

Korea, Republic of

Phone: +82 2 405 6592

Fax: +82 2 405 6593

Washington, D.C., USA

801 17th Street, NW, Suite 400

Washington, DC 20006

USA

Phone: +1 202 570 7240

Fax: +1 202 789 0104

I C A N N | Five-Year Operating Plan First Annual Update | Draft for Public Comment March 2016



53

