## Office Move Checklist - Suddath
Preparing to move your office or business can be a challenge for anyone; the key to success is preparation. Break the complex process down into manageable parts or stages. Use this office move checklist as a guide to keep you organized and on track.
CATEGORY | PREPARATION TASKS | TARGET COMPLETION | TASK OWNER | TASK COMPLETE
1. Project Development and Space Selection
1.1 | Move timeline and project schedule
1.2 | Employee census and occupancy review
1.3 | Site survey and facility review of current and proposed locations
1.4 | Desired square footage needed at new location
1.5 | Floor plan for new space that identifies work stations, equipment centers, offices, conference room needs, fixtures, and other support spaces
1.6 | Architect for new construction, upgrades and/or buildouts
1.7 | Office relocation budget
2. Technology
2.1 | IT infrastructure assessment of current and proposed locations
2.2 | Inventory of all technology assets
2.3 | Evaluation of current cabling and network via industry best practices
2.4 | Evaluation of technology upgrades for potential project consolidation
2.5 | Inventory of critical business and support applications
2.6 | Evaluation of network downtime options versus redundant hardware and applications during cut over
2.7 | Desktop relocation support strategy and resources
2.8 | Evaluation of power, AC, ventilation, network and equipment positioning requirements
3. Furniture Selection
3.1 | Furniture selection criteria and specifications
3.2 | Comprehensive furniture inventory
3.3 | Evaluation of furniture options: Reuse existing furniture Repurpose existing furniture Purchase new furniture Purchase refurbished options Sell/decommission old furniture
4. Telecom
4.1 | Evaluation of phone system: order new or relocate existing
4.2 | Phone numbers: order new or transfer existing through carrier
4.3 | Data services: order new or transfer existing (POTS, T-1, ISDN, DSL)
5. Security
5.1 | Master employee roster and access levels
5.2 | List of specialty areas that require restricted access
5.3 | List of areas that require enhanced fire suppression
5.4 | Monitoring services for employees and new facility
5.5 | Security system: select or transfer existing monitoring services
5.6 | Security plan for vacated space until turnover
6. Communication
6.1 | Internal communications plan for employees
6.1.1 | New building rules
6.1.2 | Parking procedures
6.1.3 | Move dates
6.1.4 | Move and packing procedures
6.1.5 | Network outage and contingency plan
6.1.6 | Revise telephone and fax numbers
6.1.7 | Required HR postings
6.2 | External communications plan for customers, suppliers, service/utility providers and other pertinent vendors (e.g. accountant, attorney, insurance agent, etc.)
6.2.1 | New address and phone numbers
6.2.2 | Stationery and business cards
6.2.3 | Building signage
6.2.4 | Vehicle signage
6.2.5 | Vehicle registrations
6.2.6 | Update website and collateral to reflect new information
6.2.7 | Revise advertising (including Yellow Pages and other directories)
6.2.8 | Notify post office
6.2.9 | Message scripts for communicating with external constituents
7. Document Management
7.1 | Secure off-site storage needs
7.2 | Plan for on-site storage needs
7.3 | Update filing requirements for employees
7.4 | Determine filing space for departments
7.5 | Document destruction: select or notify vendor of new location
7.6 | Dispose of or archive old files (consider sensitive documents)
8. Move Preparation
8.1 | Select department move coordinators
8.2 | Identify building restrictions for move hours
8.3 | Schedule elevator access at origin and destination
8.4 | Schedule parking and unloading at new site
8.5 | Obtain any special moving and/or parking permits
8.6 | IT staff onsite during the disconnect and reconnect of servers and data centers or consider outside support
8.7 | Arrange to have sensitive items packed and moved
8.7.1 | Computers
8.7.2 | Telephone equipment
8.7.3 | Networking equipment and servers
8.8 | Seating assignments at new location
8.9 | Packing needs for employees
8.1 | Common area packing requirements
8.11 | Plan for protection of confidential information
8.12 | Packing schedule: determine what can be packed in advance vs. last minute so your business can continue to operate as efficiently as possible with the least amount of interruption
8.13 | Communicate packing/labeling guidelines – professional movers will provide custom packing instructions and labels
8.14 | Packing supplies: ask your mover about crate rental vs. corrugated material – saves time, money and is better for the environment
8.15 | Ensure boxes or containers are properly packed and labeled with office location or name, importance, and contents
8.16 | Protection of floors, walls and elevators
9. Vendors
9.1 | Moving
9.2 | Furniture installation/reconfiguration
9.3 | Architectural
9.4 | Cabling
9.5 | Telephone/data (POTS, T-1, ISDN, DSL)
9.6 | Network (upgrade, back up, prepare for move)
9.7 | Security system
9.8 | Secure document destruction and removal
9.9 | Janitorial
9.1 | Plant watering
9.11 | Vending
9.12 | Courier